## Slide 1: SFTAS PROGRAMME UPDATE
20th January 2021
NIGERIA GOVERNORS’ FORUM (NGF)
STATES FISCAL TRANSPARENCY, ACCOUNTABILITY AND SUSTAINABILITY(SFTAS) TECHNICAL ASSISTANCE PROJECT
Presented by:
Olanrewaju Ajogbasile
Senior Programme Manager,
NGF HelpDesk & SFTAS TA
oajogbasile@ngf.org.ng
+2349083411461

## Slide 2: Highlights
SFTAS PROGRAMME UPDATE
1. A substantial Program Restructuring in response to COVID-19 has been completed.
  April to May: Consultations with States on new COVID-19 responsive DLIs.
  July: States start implementation of new DLIs, supported by NGF technical assistance.
  October: Completion of Restructuring by WB and FMFBNP to add new DLIs to the Program.
2. Additional Financing of US$750 million – The Board Approved the AF on 14 Dec 2020.
  FMFBNP agreed for the Additional Financing to remain on-granted to States
The SFTAS Program for Results has been expanded:

## Slide 3: Highlights
SFTAS PROGRAMME UPDATE
SFTAS Results and Disbursements to Date
Program DLIs | Performance Year | Verification and Disbursement Status | # States Receiving Grants | Total USD Million
2018 APA (Original DLIs 1-9) | 2018 | Verified Disbursed April 2020 | 24 States | 120.60
New DLI 13 (13.1 Amended 2020 Budget) | 2020 | Verified Disbursed Oct 2020 | 35 States | 175.00
2019 APA (Original DLIs 1-9) | 2019 | Verified, Disbursed Dec 2020 | 32 States | 239.60
New DLI 11 (11.1 Tax Compliance Relief) | 2020 | Verified Disbursed Dec 2020 | 34 States | 85.00
New DLI 12 (12.1 Emergency procurement) | 2020 | Under Verification Target Disbursement February 2021 | 24-28 States | 60 to 70
2020 APA (Original DLIs 1-9) | 2020 | To be verified and disbursed Q4 CY2021 |  | 
New DLIs 10-13 Results | 2021 | To be verified and disbursed Q4 CY2021 |  | 
2021 APA (Original DLIs 1-9) | 2021 | To be verified and disbursed Q3 CY2022 |  | 
Total Disbursement in CY2020 from Original PforR Financing USD 700 million |  |  |  | 620.2
Program targets for results and disbursements for the Original DLIs for 2018 and 2019 have been exceeded.
States have also performed strongly on the new COVID-19 responsive DLIs with 35 and 34 States achieving the Amended 2020 Budget and Tax Compliance Relief Program DLIs
The FMFBNP and the World Bank are concluding the verification of the assessment results for DLI 12 (Emergency procurement guideline and increased participation of SMEs) – Est. February 2021.
The Original Program For Results financing of USD 700 million has been nearly fully disbursed by the end of CY2020 and will soon be fully drawn down

## Slide 4: Highlights
SFTAS PROGRAMME UPDATE
2020 APA Eligibility Criteria Part 1:
Upcoming deadline:
States are expected to prepare their FY2021 State budget under the National Chart of Accounts (minimum of administrative, economic and function segment classifications), get the budget approved by the State Assembly, assented to by the Governor and published online by 31st January 2021.”
All 36 States met the second part of the 2020 Eligibility Criteria (EC) having published online IPSAS-compliant 2019 audited financial statements by 31 August 2020.

## Slide 5
SUMMARY STATUS AS OF 20TH JANUARY – WITH 11 DAYS TO GO
**States that do not meet the 2020 EC will NOT be eligible to receive grants for any 2020 Original DLIs (2020 APA) or NEW COVID-19 responsive DLIs that are to be achieved in CY2021.
  Any of the 2020 Original DLIs (2020 APA, total max ~US$15 million) AND
  Any of the new COVID-19 responsive DLIs to be achieved in CY2021 (total max ~ US$11 million)
Key Messages
16 States have published online their Approved FY2021 budgets while 20 States have not yet published. Many of the 20 States that are yet to publish their budgets is because they are addressing NCoA issues, working with NGF.
NGF has provided TA to 35 States on NCoA with 22 States already complete and 13 States near completion.
States should ensure that the NCoA compliant budget document published online is consistent with the Approved budget (Appropriation Law assented to by the Governor) published online.

## Slide 6
SUMMARY STATUS AS OF 19 JANUARY – WITH 12 DAYS TO GO
Grade | Color | Status of the publication online of the approved FY21 Annual State Budget | # of States | Status of NCoA compliance | # of States
Green |  | Online publication of the FY2021 budget approved by the State Assembly and assented to by the Governor | 16- Abia, Bauchi, Benue, Ekiti, Imo, Jigawa, Kaduna, Kano, Katsina, Kogi, Nasarawa, Ondo, Oyo, Plateau, Delta and Zamfara`State | NGF TA complete – either doing final review or cleared for publication | 22- Adamawa, Akwa Ibom, Bauchi, Benue, Delta, Ebonyi, Edo, Ekiti, Enugu, Jigawa, Kaduna, Katsina, Kebbi, Kogi, Kwara, Nasarawa, Ondo, Osun, Oyo, Rivers, Yobe and Zamfara State
Yellow |  |  |  | NGF TA is ongoing | 13- Sokoto, Taraba, Ogun, Plateau, Kano, Imo, Gombe, Borno, Cross River, Abia, Lagos, Niger and Bayelsa State.
Red |  | FY2021 Approved Budget NOT yet published online | 20- Adamawa, Akwa Ibom, Anambra, Bayelsa, Borno, Cross River, Ebonyi, Edo, Enugu, Gombe, Kebbi, Kwara, Lagos, Niger, Ogun, Osun, Rivers, Sokoto, Taraba and Yobe State | NGF yet to receive budget document & CoA from State for review. | 1- Anambra State
SUMMARY STATUS AS OF 20TH JANUARY – WITH 11 DAYS TO GO
****States should review carefully their Status and ensure they are “Green” on both requirements before 31st January 2021

## Slide 7
THANK YOU

## Slide 8: CONTACTS
Programme Coordination Unit
Mr. Stephen Okon,
The SFTAS-National Program Coordinator,
Director Home Finance Department,
Federal Ministry of Finance, Budget and Planning
Central Business District, Abuja.
stephenokon117@yahoo.com
08065643949
Mr. Ali Mohammed,
The Deputy National Program Coordinator
ali4m1968@gmail.com
07033337112
Please copy enquires to:
Mr. Ibrahim Mohammed,
SFTAS Communication Specialist
mibrahim@sftas.org.ng
08035993754
Office of the Auditor-General for the Federation as the IVA
Mr. Ayodeji Ogunyemi
SFTAS Senior Quality Assurance Advisor
ayodeji.ogunyemi@oaugf.ng
08146505040
Please copy enquires to:
sftas@oaugf.ng
oluwatosin.akomolafe@oaugf.ng
Nigeria Governors’ Forum
Olanrewaju Ajogbasile
Senior Programme Manager, NGF HelpDesk & SFTAS TA
oajogbasile@ngf.org.ng
+2349083411461
Please copy enquires to:
saffun@ngf.org.ng
Zabiola@ngf.org.ng
Debt Management Office
Elizabeth Ekpenyong
Head – Strategic Programmes Department
eekpenyong@dmo.gov.ng
0805 7051158
Please copy enquires to:
Mrs. Olubunmi Siyanbola ,
SFTAS DMO Program Manager
bunmisiyanb@yahoo.com
08033462383
OGP
Mr. Andrew Onyeanakwe
Program Manager SFTAS OGP
Andrew.Onyeanakwe@ogpnigeria.gov.ng
08033138503