## Slide 1: NGWA-GBV 2021 WORKPLAN

## Slide 2: NGWA-GBV 2021 Workplan
FEBRUARY
February 6th FGM day
Monthly Zoom meeting February 7th
Webinar on: GBV Coordinating Mechanisms (February 25th)
Project Memo to UNFPA
GBV Resource Manual
World Day of Social Justice (20th February)
MARCH
Release GBV Advocacy Video
Announce GBV Survivor Fund grants for International Women’s Day
International Women's day (8th March)
Project Review meeting with Ford Foundation
Monthly Zoom meeting

## Slide 3: NGWA-GBV 2021 Workplan
APRIL
National Seminar on Role of First Ladies, Abuja (April 8th)
MAY
International Children’s Day (May 25th)
International Day for Menstrual Hygiene (May 28th)
JUNE
1st anniversary NGWA-GBV and in-person meeting
Payment of annual membership dues
Submit annual written reports
International day of Widows (June 23rd)

## Slide 4: NGWA-GBV 2021 Workplan
JUNE Contd
Webinar with Creative Industry to influence GBV messaging (June 29th)
World Day Against Child Labour (12th June)
Day of the African Child (16th June)
International Day for the elimination of sexual violence in Conflict (19th June)
International Day Against Drug Abuse and Illicit Trafficking (26th June)
World Day Against Trafficking in Persons (30th June)
Submission of Ford Foundation report

## Slide 5: NGWA-GBV 2021 Workplan
JULY
Webinar with Traditional and Religious leaders, July 7th
AUGUST
International Youth Day (12th August)
World Humanitarian Day (19th August)
Monthly Zoom meeting August 22nd
SEPTEMBER
World Day of Charity (September 5)
World Suicide Day (10th September)
Monthly Zoom meeting September26th

## Slide 6: NGWA-GBV 2021 Workplan
OCTOBER
Submit reports
International day of the Elderly (1st October)
World Mental Health Day (10th October)
International day of the Girl Child (11TH October)
International day for Rural Women (15th October)
Webinar on GBV and Mental Health
Monthly Zoom meeting October 24th
NOVEMBER
Publication of annual report
16 days of Activism programs (25th Nov – 10th Dec)
GBV Survivor Fund announcements
Monthly Zoom meeting November 21st
DECEMBER
NGWA-GBV 2nd AnnuaI Conference December 2nd 2021
In-person meeting/End of year dinner: December 3rd
Human Rights Day (10th December)