## Sheet1
Adamawa State Committee on Food and Nutrition (SCFN)
Detailed Implementation Workplan
This workplan describes the strategies that will be used to achieve the goal and objectives of the multisectoral SCFN approach. As a result, state the goal, objectives, strategies, and activities that will be applied to address nutrition problems in the state (e.g., how activities contribute to strategies, how strategies support objectives, and how objectives lead to the achievement of the overall goal).
SCFN Goal: (state the multisectoral goal of the SCFN to be addressed) To improve the nutritional status throughout the lifecycle of the people of Adamawa state with a focus on vulnerable groups especially children under-five years of age, women of reproductive age and people with special nutritional needs.
SCFN Objectives: (list the objectives that will lead to attaining the goal above) 1. To improve food security at the state, LGA, community and household levels 2. To promote the delivery of effective and high-quality nutrition related interventions for the people of Adamawa State 3. To increase the knowledge of nutrition among the populace To strengthen nutrition research, monitoring and evaluation 4. To incorporate food and nutrition considerations into the state and local government sectoral development plans 5. To promote optimum nutrition for people in especially difficult circumstances, including PLWHA
Strategies | Activities | Results/Outputs/Indicator | Duration | Source of Funds | Responsible Departments/Stakeholders
FY'21
[6 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Strategy 1: Maternal Nutrition
1.1 BCC (Behavior change communiction) - On promotion of dietary practices that support maternal nutrition including IYCF | The sensitization of public via radio and television on Nutrition issues forthnightly on 1 radio and Tv station | 1hour monthly dedicated to sensitization on nutrition issues | Forthnightly | No funds required | MOI | bar: FY'21 Jan to FY'21 Dec
| Sensistization of pregnant women on Nutrition issues in hospitals and clinics on Monthly basis | 3 facilities sensitized monthly | Quaterly | Budget | NAFDAC | bar: FY'21 Jan; FY'21 Apr; FY'21 Jul; FY'21 Oct
| Utilization of the Air time forthnightly to sensitize on CMAM, IYCF, Family planning, Nutrition in ANC/pregnant mothers | 1 hour monthly used for sensitization | Forthnightly | Ministry running cost | SMOH | bar: FY'21 Jan to FY'21 Dec
| Setting Up Nutrition Clubs with community based organization such as home base care volunteers , women groups, mosques & Churches groups, and young peoples club | 5 clubs per LGA (105 Clubs in the state) | 1 month | ADSPHCDA/PHCA & LGA | ADSPHCDA/PHCA & LGA | bar: FY'21 Feb
1.2 Service Delivery | Conduct MNCH week to increase coverage of nutrition commodities to pregnant women and children | 2 MNCH week conducted anually | Bi anually | SOML | SMOH | bar: FY'21 Mar; FY'21 Aug
| Seeting up Nutrition demostraion gardens in household, schhols, churches, mosques, & Clinics | 5 Nutrition Dmostration Gardens per LGA (105 Demo Garden in the state) | 1 month | LGA Chairman and Director Agric and Natural Resources | ADSPHCDA/PHCA & LGA | bar: FY'21 Mar
1.3 capacity buildng Maternal nutrition and IYCF | Training health workers and community volunteers, IYCF support groups, Chips on exclusive breast feeding complementary feeding, martenal and child nutrition, child Hygene, & use of MUAC | To reach out to the vulnarables groups | 3 Month | ADSPHCDA/LGA | ADSPHCDA/PHCA | bar: FY'21 Apr to FY'21 Jun
1.4 Advocacy and resource mobilization | Holding Nutrition campaigns at local Schools, clinics, mosque, & churches | To reduced maternal and child Mortality by 20% | 6 months | ADSPHCDA/PHCA & LGA | ES, Director HEWA, Nutrition focal Person, DMCH | bar: FY'21 Feb to FY'21 Jul
| Advocate to Executive and Legislative Arm of Govt. | Number of Advocacy visits conducted | Quarterly | MDA/Partners | SCFN | bar: FY'21 Jan; FY'21 May; FY'21 Aug; FY'21 Oct
1.5 Coordination and Multisectoral partnership | Inauguration of Local Government Food and Nutrition Committee | Implementation of the activities at the LG levels | Two months | Joint Account Allocation Committee | MLG&CA | bar: FY'21 Feb
| Quarterly Coordination meeting | Number of Quaterly meetings held | Quarterly | ASPC | Planning commission | bar: FY'21 Mar; FY'21 Jun; FY'21 Sept; FY'21 Dec
| Food and Nutrition activities to be captured in the 21 LGAs annual Budget | Number of LGAs with Nutrition budget allocated | Annual | Joint Account Allocation Committee | MLG&CA | bar: FY'21 Feb to FY'21 Dec
Strategy 2: IYCF Interventions
2.1 BCC
2.2 Capacity Building | Food demonstration in 21 LGAs in a year | 11 LGAs in first Quarter | Quaterly | SOML | SMOH | bar: FY'21 Mar
2.3 Advocacy and Resource mobilization
2.4 Coordination and Multi-sectoral partnership
2.5 Private sector engagement
Strategy 3: Management of SAM interventions
3.1. Service deliver | Treatment of SAM cases in all OTP sites across 21 LGAs | Number of cases treated | Monthly | UNICEF | SMOH | bar: FY'21 Jan to FY'21 Dec
Strategy 4: Micrfonutrient deficiency and control interventions
4.1 Service Delivery
Strategy 5: Adolescent Nutrition
5.1 BCC
Strategy 6: Poverty reduction
6.1 Capacity Building | Train 500 women and youth on skill acquisition | 125 women and Youth trained quarterly tailoring, salon, poultry… | Quarterly | MoSD | MoSD | bar: FY'21 Mar; FY'21 Jun; FY'21 Sept; FY'21 Dec
6.2 Coordination and Multi sectoral partnership
Strategy 7: Food Security
7.1 Capacity Building | Good Agricultural practices and general use of farm inputs/equipment, reviving of Young Farmers Club in various Secondary Schools across the state, and encouraging Households to key into Backyard gardening | Knowledge of farmers on modern agricultural production will be improved | 3 months | Government | Ministry of Agriculture | bar: FY'21 Feb to FY'21 Apr
Strategy 8: Water and sanitation
8.1 BCC | provision of portable drinking water and water for agriculture and sanitation | Number of Wards/LGAs provided with water source | continous | Government and Development Partners | AD, RUWASSA and MOWR | bar: FY'21 Jan to FY'21 Dec
8.2 Capacity building | Re-training of staff on hygiene promotion | Number of staff trained | continous | Government and Development Partners | AD, RUWASSA and MOWR | bar: FY'21 Jan to FY'21 Dec