## Sheet1
2020 SCFN WORK PLAN ON NUTRITION
IMO STATE 2021 STATE COMMITTEE ON FOOD AND NUTRITION (SCFN) WORK PLAN
INTERVENTION | ACTIVITIES | OBJECTIVE | INDICATOR | TIME FRAME | COST | PARTNERS
HOME GROWN SCHOOL FEEDING | Monthly random on the spot monitoring of Home Grown School Feeding (HGSF) programme | To improve on HGSF service delivery | No of monitoring conducted | Feb-November | 240000 | NHGSF
| Yearly assessment of Home Grown School Feeding (HGSF) Programme and reorientation of food vendors | To improve on HGSF service delivery | No of food vendors adhering to guideline | June- July | 950000 | NHGSF
| Organise Nutrition week | To educate Imo State populace on the importance of good dietary habit | No of sectoral nutrition activties carried out | June- July | 4705000 | FMOH, UNICEF
Form and strengthen Local Government Committee on Food and Nutrition | Form and strengthen Local Government Committee on Food and Nutrition | To enhance Food and Nutrition coordination in the State | No of LGAs with functional Food and Nutrition Committee | Jan-Dec | 2740500 | SCFN, UNICEF, Cs-SUN, FMBED
Organize Quarterly meeting State Committee on Food and Nutrition (SCFN) | Organize quarterly meeting State Committee on Food and Nutrition (SCFN) | To strengthen SCFN | No of meetings held in a year. | Jan-Dec | 500000 | SCFN, UNICEF, Cs-SUN, FMBED
Disseminate Imo State costed multi sectoral strategic plan of action for nutrition and Imo State Food and Nutrition Policy | Disseminate Imo State costed strategic plan of action for nutrition and Nutrition Policy | To encourage non sectoral nutrition action | No of partners supporting nutrition activities in the State | Jan-February | 5000000
ADVOCACY | Advocate for the establishment of 3 Agro-based cottage industries for the production of complementary food packages for value addition. | To improve nutritional value of locally produced complementary foods | No of cottage industries established | January-August | 100000 | SCFN, UNICEF, Cs-SUN, FMBED
| Establishment of biofortified crop farms in Primary school farms in Imo State - orange fleshed sweet potatoes (OFSP), Vit A cassava and Vit A maize. | To increase awreness on the cultivation and consumption of Vitamin A biofortified foods | No of schools that have vit A biofortified farms | January-August | 100000
| legislation of the extension of maternity leave to six months, inclusion of two weeks paternity leave and mandatory establishment of creches in both private and public work places. | To Increase the rate of exclusive breastfeeding in Imo State | legislation established | January-August | 100000 | SCFN, UNICEF, Cs-SUN, FMBED
Sensitization and Awareness creation on appropriate eating habits | Celebrate the World Food Day and World Breasting Week | To create awareness on adequate eating practices | WFD and WBW celebrated | August-December | 3000000 | SCFN UNICEF, CS-SUN, FAO
Monitoring and supportive supervision of MIYCN at the health facilities | Develop Checklist for MIYCN monitoring at the Health facilities | To monitor and supervise MIYCN activities and reporting at the health facilities | reporting rate of MIYCN activities | July-December | 1400000 | SCFN
MIYCN food demonstration corners in 3 health facilities at one/zone | Establish food demonstration corners in 3 health facilities at one/zone | To improve appropriate MIYCN practices | no of health facilities with food demonstration corners | July-December | 3000000 | SCFN
TOTAL |  |  |  |  | 21835500