## Sheet1
Ministry/Agency: Animal Heaalth
Objective | Activities | Subactivity | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
To train Fulani women pastoralist on a simple yoghurt Production techniques for value addition. | 1) Construction of yoghurt processing center in 17 different locations of pastoralist settlements 2)Sensitization and training of fulani women on simple technique in yoghurt production. | Capture of beneficiaries and subsequent training | Hon. Commisioner and Permanent Secretary | 1) Seventeen number of yoghurt processing centres contructed. 2) 225 of women trained for simple yoghurt production | 1) 225 women have benefitted from training and sensitization. 2) 17 communuties benefited from milk processing centre | January-December 2020 | Cost of construction, training and sensitization per setlement= 4,296,375 ×17 setlements= 73,033,375 | Kebbi State Government
To improve sheep production among kebbi State youth and women pastoralist | 1) Training on how to upgrade our local breed ( Uda and Yankasa). 2) Provision of 2 female sheep and to each beneficiary and one Balami ram is to go round the whole group | Capture of beneficiaries and subsequent training | Hon. Commisioner and Permanent Secretary | 795 women and youth were trained on sheep multiplication technique and they were provided with 2 female sheep and 1 balami male Ram for each group | 795 pastoralist women and youth benefitted from the program | January-December 2020 | Cost of training and the animal for each group =985,537.5×33= 32,522,737.5 | Kebbi State Government
To improve Goat production among kebbi State youth and women pastoralist | 1) Training on how to upgrade our local breed (Sokoto red ). 2) Provision of 4 female and a male goat to 450 beneficiaries | Capture of beneficiaries and subsequent training | Hon. Commisioner and Permanent Secretary | 450 women and youth were trained on goat multiplication technique and they were provided with 4 female goat and 1 Buck for each | 450 pastoralist women and youth benefitted from the program | January-December 2020 | Cost of training and the provision of animal for each participant =65,087.5×450= 29,289,375 | Kebbi State Government
To improve local chicken production among kebbi state youth and women | 1) Training on how to upgrade our local breed of chicken . 2) Provision of 5 female local chicken and a male cockerels to 482 beneficiaries | Capture of beneficiaries and subsequent training | Hon. Commisioner and Permanent Secretary | 482 women and youth were trained on local chicken upgrade and they were provided with 5 chicken and 1 exotic cockerel each | 482 pastoralist women and youth benefitted from the program | January-December 2020 | Cost of training and the provision of animal for each participant =18,950×482= 9,133,9000 | Kebbi State Government
To upgrade local breeds of cattle among ederly pastoralist in Kebbi State | Each pastoralist is to provide 2 cows for upgrading through Artificial Insemination | Capture of beneficiaries and subsequent training | Hon. Commisioner and Permanent Secretary | Total of 220 cow were inseminated | 110 ederly pastoralist | January-December 2020 | Cost of Artificial Insemination Per 2 cows =174,650×110=19,211,650 | Kebbi State Government
To train bee keepers on modern bee keeping technique | 1)75 people were targeted and trained on modern bee keeping. 2) The participants were provided with modern bee keeping equipments | Capture of beneficiaries and subsequent training | Hon. Commisioner and Permanent Secretary | 75 individual were trained on bee keeping technique | 75 bee keepers | January-December 2020 | Cost of training and provision of modern bee keeping equipments=90,610×75=6,795,750 | Kebbi State Government
To improve pasture production for commercial purposes | 1) 60 participants were trained on how do commercial pasture production. 2) The participants were grouped in to 4 and the were provided with comercial pasture production item | Capture of beneficiaries and subsequent training | Hon. Commisioner and Permanent Secretary | 60 individual were trained on comercial pasture production | 60 pastoralist | January-December 2020 | Cost of training and provision of modern comercial pasture items for each group=794,000×4=3,176,000 | Kebbi State Government
Ministry/Agency: Finance
Objective | Activities | Subactivity | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
To ensure prompts payments | Documentration of approvals obtained for payment |  | PS finance | Release of funds as per approval | 12 Months | Monthly | N200,000.00 monthly for 12 months | Govt. Ministry of finance
Coordination and Multi sectoral partnership | Conduct financial tracking for nutrition intervention at State and LGA levels |  | PS finance | No. of approvals processed and paid | All MDAs | Jan. to Dec.
Ministry/Agency: Water Resources and Rural Development
Objective | Activities | Subactivity | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
To improve water hygiene and sanitation | Provision of chemical for treatment to communities using raw water as source of water supply |  | PS & PM | Quantity of chemical procured supplied | 1. Alluminium supply 220 Tons 2. Hydrated lime 110 Metric Tons 3. H+h Chlorine 200 drums |  | N82,000,000.00 | State Govt.
Water for sanitation and hygiene | Solar powered boreholes to 30 location |  | PS | Number constructed | PHC Needy community | Jan. to Nov. | N109,296.00 | State Govt.
To provide water for livestockand irrigation | Construction of two number earth Dams and irrigation facilities to fulani and farming commuties of Arewa |  | PS | Number of earth Dams constructed | To construct two number earth Dams | Jan. to Dec. | N36,000,000.00 per dam | State Govt.
Provide water for sanitation and home grown school feeding program to enhance nutrition | Rehabilitation and construction of 20 number water scheme to school and localities as per the constituency project for 2021 |  | PS | Number of scheme constructed and rehabilitated | 20 different locations | Jan. to Mar. | N150,000.00 | State Govt.
Provide water for sanitation and home grown school feeding program towards nutrition enhacement | Construction of 50 number hand pumps at varios location including school as part of constituency project for 2021 |  | PS | Number of funds provided to villages | 50 locations | Jan to April | N1,300,000.00 | State Govt.
Ministry/Agency: Budget
Objective | Activities | Subactivity | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
Coordination and Multi sectoral partnership | Conduct quarterly state food and nutrition committee meeting |  | PS Budget | Quarterly meeting on SFNC conducred | SCFN | Quarterly | N320,000.00 | MBEP
Advocacy and Resource Mobilization | Sustain and increase budget for nutrition activities in the state |  | PS Budget |  |  | Yearly
| Create a budget line for nutrition in other state MDAs |  | PS Budget | MDAs Nutrition budhet line created | MDAs | Annually |  | MBEP & MDAs
| Engagement with legistlative arm of Govt. to gain their buy in on nutrition budget |  | PS Budget | Advocacy conducted to the House of Assembly | Legistlature | Once | Not require funding | MBEP
| To advocate for the creation dedicated nutrition budget line in all relevant MDAs at the state & LGA level |  | PS Budget | Budget line created | MDAs LGAs | Annually | Fundings not require | MBEP
Research Monitoring & Evaluation | Develop an M&E plan to monitor & evaluate all the poverty reduction program in the state |  | PS Budget | M&E plan Developed |  | Annually | N3,000,000.00
Ensure Accountabilty and Transparency | Budget tracking for nutrition interventions |  | PS Budget | Monthly expenditure Return/ perfomance report | MDAs expenditure | Quarterly | N50,000.00 | MBEP
| Result based management training for the committee members |  | PS Budget | Training conducted | Committee members | Once | N1,500,000.00 | MBEP & PARTNERS
Ministry/Agency: Animal Health, Hubandry and Fisheries
Objective | Activities | Subactivity | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
To improve the nutrition base of rural household through the production of Noiler chicken | To train women in noiler production Construction of simple poultry houses provision of brooded noiler chicken Provision of feeds/Medication | Identification Sensitization Capture Training | PS & Poultry Product Unit | No. of poultry houses No. of Beneficiaries Production of inputs No. of beneficiaries of 750 brooded noiler chickens per LGA | Group (female) of 15 participants drawn from each LGA i.e 315 beneficient | Feb. to Dec. 2021 |  | KBSG & CBN
| To train rural youth (male) same as in noiler chicken production Provision of funds & medication |  |  |  | Group (male) of 15 participants drawn from each LGA i.e 315 beneficient | Feb. to Dec. 2021
To facilitate increase in production and consumption of fish through support programme to target groups both women and male | Construction of harnested fish ponds Provision of fingerlings Provision of feed and medication Supervision and consultancy |  | PS & Director Fisheries | No. of constructed fish pond per LGA No. of fingerlings provided No. of beneficiaries for fish feed and medication Consultancy and supervision | Female beneficiaries 21 Number Male beneficiaries 21 number | Feb. to Dec. 2021
Promotion of peaceful co-existence betweeen postralist and farmers to facilitate smooth atmosphere for livestock and arable crops production | Facilitate sensitization at community level for peaceful co-existence of these two groups through dialogue Facilitate Bill and law to this effect |  | PS & Director Range Management and Postralist Affairs | No. of awareness session facilitated No. of bills to be formulated | 21 communities across the state 2 Bills on grazing reserve & stock roads | Feb. to Dec. 2021
NB
Ministry/Agency: Women affairs and Social Development (MOWASD)
Objective | Activities | Subactivity | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
Empowering women and youth through sustainable income generation activities for improved health, education and nutrition outcome | Training women and youth (adolescent girls) on vocaional activities such as food processing , knitting, tailoring, soap making, etc. for sustainable income. |  | Permanent Secretary | No. of women and youth empowered through vocational skills | 400 women and youth | Jan- Dec. 2021 | N17,000,000 | State Government
| Provide soft laons to women (especially young mothers) to engage in income generation activities. |  | Permanent Secretary | No. of women and adolescent girls empowered with soft loan that started income generation activities | 100 Women and girls | Jan- Dec. 2021 | N2,000,000 | State Government
Strenghten system capacity to respond to PWDs and vulnerable women through social welfare for improved welfare and nutritonal status | Develop a data base for PWDs that are unable to work |  | Permanent Secretary | Data base developed and PWDs unable to work identified and compiled | Single data base sited at the MOWASD/LGA | April - Decemeber, 2021 | 200, 000 | State Government
| Provision of social welfare grants to the PWDs and vulnerable people (old aged, fistula patients) for improved health and nutrition. |  | Permanent Secretary | No. of women and vulnerable people that accessed social welfare fund | 440 PWDs/Vulnerable women | May - December, 2021 | N60,000,000 | State Government
| Conduct food demonstration for vulnerable women, adolescent girls including fistula clients. |  | Permanent Secretary | No. of women, adolescent girls and fistula clients empowered through food demonstration | 3 demostration at the State and LGA level | June - October, 2021 | 2, 000,000 | State Government
Improve access to education especially for the girl-child, women and PWDs | Support PWDs with skill acquisition and prostethic aids to enable access to education and good nutrition outcome. |  | Permanent Secretary | No. of PWDs supported with different prosthetic aids
| Engage women through awareness creation on the importance of girl child retention in school and improve nutrition for the adolescent girls. |  | Permanent Secretary | No. of women reached with information on benefits of girl child education and improve nutrition for adolescent girls. | 500 women | March - December, 2021 | 100000 | State Government
Ministry/Agency: MINISTRY OF AGRICULTURE AND NATURAL RESOURCES
Objective | Activities | Subactivity | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
-To enhance food availability through all year round farming of nutrient dense food crops and ensure proper consumption by communities. | Production of bio-fortified food crops Facilitate dry season Groundnut production | Sourcing of -Vitamin A fortified & Quality Protein Maize, Improved Soya bean, Sesame and Groundnut varieties. Build partnership with other agro-allied or finance support organization | PS, DAS & Et. ADP | Quantity of improved seeds procured (4 major crops- maize, Soya bean, Sesame, G/nut). Numbers and types of inputs provided. | Maize 2000kg (100 farmers) -Soya bean 2000kg (20 farmers) -Sesame 300kg (60 farmers), G/nut 3000kg (100 farmers). Fertilizers, Agro-chemicals, water pumps | March-Oct 2021
Enhance rural community production and consumptions of vegetables. | Promote home and school gardening | Establish home backyard garden Establish school garden | DAS, DPRS & EXT ADP | Nos of Functional home and school gardens installed. | 20 (10 each for home and school gardens) | April-Dec
Empower MANR to enforce regulation on food safety. -Reduce circulation of dangerous food stuff. | Legislation on pesticide use and Establish a committee between SON, NAFDAC and MANR to enforce Fertilizer and Food Safety | KBHA enact law empowering MANR to test and destroy chemical laden food stuff. Sensitize farmers and general public of hazards and implications of agro-chemicals | Chair SFNC & PS Agric | -A bill passed | 1no. | Feb. – Sept.
-Increase consumption of safe and nutritious food -Support export of crops -Enhance income of producers. | Promote organic production of food crops | Training of farmers on organic cultivation. - Sourcing & demonstration of technologies on organic production. | PS & DAS | --No. of farmers trained -no. of demonstration plots established. | -1000 no of farmers trained. 10 demonstration plots. | April – Dec
Increase food safety to Increase quantity of safe food available to consumers | Hygienic handling of food stuff | Sensitazation Demonstration | PS & DAS | -No of sensitization for a held | Sensitazation session 2 number Demonstration site 3 number | July & Nov.
-Expose farmers to simple adaptable storage methods and technologies. - Reduce use of dangerous chemicals for storage. -Enhance availability of safe food stuff | Safe storage of food crops | Training of farmers on alternative storage methods. -Demonstration of safe storage methods. | PS, DAS, Ext | No of trainings achieved | 100 farmers trained | Sept. Dec
Enhance rural food security | Promote Grains bank | Identify locations & sites. | DAS & Ext | No of banks established | 30 banks
Large scale dissemination of knowledge on improved production technologies | -Field days-Media discuss on food crop production and public food safety. | -Conduct of field days.-Sourcing of relevant resource persons. -Discussions KBTV & KBC | PS & DAS-DAS-DAS & | No. of field days held. Weekly Radio & TV programmes. | 5 no field days 20 weeks | June – Dec
Ministry/Agency: Information National Orientation Agency
Objective | Activities | Subactivity | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
To increase knowledge of nutrition among the populace | 1. Dissemintion of information and communication on IYCF through town hall meeting, compound and Majalisa meetings | 1. Town hall meeting involving men of selected coomuties | NOA ASS Director | No. of men reached through town hall meeting | 50 session in selected commutties | April to June 2021 | N200,000.00 | MBED/SCFN/BAN
|  | 2.Compound meeting involving women of selected commuties |  | No. of women reached through | 2,000 women | April to June 2021 | N200,000.00 | MBED/SCFN/BAN
|  | 3.Engaging men on behavior change on improved nutrition using Majalisa forum |  | No. of men reached in majalisa meeting | 3,000 men | April to June 2021 | N400,000.00 | MBED/SCFN/BAN
| 2. Provide and distrubute IEC materials | 1. Produce gender response IEC materials that encorage husband to support good and healthy nutrition for their families | MOI/NOA Director Information Asst. Dir. NOA | No. of poster and flyers produced and distrubuted | 10,000 posters 10,000 flyers English and hausa | April to Nov. 2021 | N400,000.00 | PARTNERS
|  | 2. Production and airing on nutrition in hausa, fulfude dakarci and kambarci | Director Information | No. of jingles produced and aired | 2 slots per day and 8 months in hausa, fulfude, dakarci and kambarci | April to Nov. 2021 | N700,000.00 | PARTNERS
|  | 3. Translation of food recipes into hausa | Director Information Dir. NOA | Translated copy | 10,000 copies printed | 2021-06-01 | N800,000.00 | PARTNERS
|  | 4. Food demonstration on Radio and TV | Director Information | No.of episode produced and aired | 2 slots weekly for 8 months | April to Dec. 2021 | N600,000.00 | MBED/SCFN/BAN
|  | 5. Nutritional counselling card printing | Director Information Asst. Dir. NOA | No. of cards produced and distrubuted | 10000 | April to Nov. 2021 | N1,200,000.00 | MBED/SCFN/BAN
| 3. Train media personnel on improved reporting of nutrition issues | 1. Training on DRNCD and consequences of unhealthy sedimentary life | Director Information Asst. Dir. NOA | No. of media personnel trained | 40 Media personnel | May | N800,000.00 | MBED/SCFN/BAN
|  | 2. Training of IYCF on maternal nutrition issues | Director Information Asst. Dir. NOA
| 3. Airing of nutrition activities on radio and TV | Demonstration and airing of nutrition programme on Radio and TV | Director Information Asst. Dir. NOA | No. of programs recorded and aired | 16 programes recordedand aired | April to Dec. 2021 | N1,500,000.00 | PARTNERS
Ministry/Agency: Agric and Rural Development Authority
Objective | Activities | Subactivity | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
Incresed production of Vit. A fortified crop to reduce Vit. A deficiency | a. Provision of maize Vit. A fortified seed for farmer 1/2 ha production |  | Kebbi ADP | No. of sites provided with Vit A fortified maize seed | 3 community per LGA (3 * 21)= 63 Sites | June to Sept. 2021 Annually | N150,000 for 1/2 ha * 63 = N9,450,000.00 | Govt/ any possible donor agency
| b. Production of potatoes Vit. A fortified cuttings for farmer 1/2 ha production |  | Kebbi ADP | No. of sites provided with Vit A fortified potatoes seed | 2 community per LGA (2 * 21)= 42 Sites | June to Sept. 2021 Annually |  | Govt/ any possible donor agency
Increased extension agents, support for Eas supporting Vit A fortified crop production and its associate problem | Good Agricultural training for Eas Provision of mobility and allowance support for the Eas |  | Kebbi ADP | No of Eas trained on GAP No. of Eas supported with monthly mobility allowance N20,000.00/month for 5 month | 21EAs | May to September 2021 | 21 Eas @ N100,000.00 each for 5 months = N2,100,000.00 | Govt/ any possible donor agency
Ministry/Agency: Ministry of Health/SPHCDA
Objective | Activities | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
Maternal Nutrition | s
Improved capacity and political will to implement quality gender responsive ANC and IFA supplementation policies/guidelines and program among national and state policy makers | Conduct advocacy workshop with State policy makers for adequate budget allocation and release for IFA procurement and maternal nutrition service support | SNO | 1. # of advocacy meetings held. | Commussioners, Perm. Secs and ES of line Minstries. Members of House Assembly | 2021-02-01 | 1500000 | NI
| Conduct state workshop for the review of costed nutrition plan with adequate budget for procurement of IFAs and maternal nutrition services. | SNO | Costed Nutrition plan reviewed | Commussioners, Perm. Secs and ES of line Minstries. Members of House Assembly | 2021-03-01 | 3000000 | NI
| conduct sensitization meetings with policy makers on multiple micronutrient supplements (MMS) | SNO | Sensitization meeting on MMS conducted for national and state level policy makers (Yes/No). # of policy makers that participated in the sensitization meeting on MMS | SCFN Members,Directors of line Ministries | 2021-02-01 | 2000000 | NI
improved capacity skills and motivation to provide gender sensitive or responsive high quality and timely ANC and IFA supplementation program for pregnant women and adolescents | Conduct training workshop for frontline health workers (FLHW) on the provision of gender responsive ANC & IFA supplementation, nutrition counseling, tracking and monitoring plans | SNO | # of frontline healthcare workers trained on gender responsive ANC service delivery and IFA (disaggregated by sex) | 246 FLHWs | 2021-02-01 | 5000000 | NI
| Conduct training for supply chain managers on forecasting and quantification of stocks to alighn with WHO 2016 guidelines |  | # supply chain managers trained (TOT). | 21 Chain Managers | 2021-03-01 | 1400000 | NI
| conduct supportive supervision of frontline health workers, community based health volunteers/CHIPS | SNO | # of Supportive supervission sessions conducted | 12 Rounds | Jan - Dec | 5000000 | NI
| Procument of IFA commodity to the state, LGA and health facilities |  | # of IFA commodity supplied to the state | 9,000,000 IFA Tablets | March |  | NI
| Select community structures (CHIPS) |  | # of CHIPS volunteers selected . | 2250 CHIPS | April | 2000000 | NI
| Conduct Capacity building for CHIPS on the benefits of improved maternal Nutrition with emphasis on adolescent girls |  | # of CHIPS volunteers trained | 2250 CHIPS | May | 5000000
| Suport CHIPS activities with token |  | # of active CHIPS supported | 2250 CHIPS | April - Dec |  | BHCPF
| Conduct monthly performance review meetings at State level |  | # of meetings held, # of participants attending meeting disaggregated by sex | 12 Meetings | Feb - Dec | 1150000 | SCFN
Improve knowledge and skills of pregnant women (including pregnant adolescents) and their influencers (husbands, mothers in-law,others) on early and complete ANC and IFA consumption.
| Conduct food demonstrations that include proper food handling, preparation methods, and importance of dietary diversity at ANC clinics, OTP sites, and PHC centres |  | # of demostrations conducted across selected facilities | 225 HFs | April- Dec | 10000000 | IHP
BCC Maternal Nutrition | Promote maternal Nutrition through MNCH weeks, World Breastfeeding Week, National Nutrition Day |  | # of caregivers reached during MNCHWs, WBFW, NND | 2,000,000 Caregivers | June & Dec | 2000000 | SPHCDA,NI, BA-N, & UNICEF
| Promote maternal nutrition among women of reproductive age through community structures |  | # of Women of reproductive age reached with Maternal Nutrition msgs | 548,286 WRA | Jan & Dec |  | BA-N, NI
MNCHW
Plan and implement MNCHW | Develop micro plans |  | Microplan developed | 2 | April | 2000000 | NI
| Conduct pre planning meetings |  | # of meetings held | 10 | May and Nov | 0 | SPHCDA
| conduct social mobilization at all levels |  | # of Social mobilizations held | Religion/ Traditional Leaders and Caregivers across the State | On going | 5000000 | NI
| conduct State, LGA and Ward level training |  | # Trainings conducted |  | May& Nov | 7000000 | UNICEF
| monitor MNCHW implementation |  | MNCW implemention moitored |  | May& Nov | 1050000 | SOMLs
Procurement of Albendazole
| Deworming of adolescents using school based approach |  | No. of adolescent dewormed disagregated by sex | 21 Secondary schools | May - December
| Establishment of adolescent friendly corners at PHCs and conduct Iron Folate supplementation of adolescent girls |  | No. of adolescent girls that received iron folate supplementation | 21 PHCs | May - December
CMAM
Admit and treat malnourished children through community based management of acute malnutrition strategy | Procurement of RUTF | Nutrition Specialist | RUTF procured.# of SAM children treated with RUTF | 10,000 cartons | June |  | UNICEF
| Refresher training for health workers and CVs on CMAM in low performing LGAs | SNO | # of HWs and CVs trained on CMAM | 303 HWs and 101 CVs | June | 7300000 | UNICEF
Supportive supervision and monitoring of the CMAM programme by external monitors using smart phones
Routine supportive supervision and monitoring of the CMAM programme by state and LGA monitors
| Transportation of nutrition commodities from state, LGAs and to HFs |  | #of LGAs and HFs that received Nutrition commodities | 225 HFs | Jan-Dec | 3600000 | SPHCDA
IYCF
Support advocacy activities to promote optimal IYCF practices (early initiation of breastfeeding and exclusive, complementary feeding etc) through breastfeeding days (as campiagn)
| Promote Abincinmu Guzurinmu | SNO | # ofcaregivers reached with the strategy |  |  | 20,000,00 | SPHCDA
MNDC
Expand coverage with micronutrient deficiency control supplementation (MNP,Vitamin A and Albendazole | Procure and distribute essential micronutrients (Vit. A, and micronutrient powder through community structures | SNO | # of Vit.A , Albendazole and MNP Procured. # of Children reached with MNP, Albendazole and Vit. A | 893830, 794516 | On-, going | 3,00,0000 | UNICEF,SOMLs
Support BCC activities on iron supplementation, Multiple Micronutrient Poweders (MNP) Zinc/ORS
| Routine monitoring of Vitamin A | SNO | # of children reached with routine Vit.A |  | March-Dec | 5000000 | SOMLs
Objective | Activities | Sub-activities | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
Promote nutrition through MNCH weeks, World Breastfeeding Week, and National Nutrition Day | MNCH-week | 1. Radio jingles, phone-in program, & Rally 3. Procurement and distribute Iron-folate, Zinc Low ORS, MNP & Albendazole to PHCs
| World Breastfeeding Week | Radio jingles, phone-in program, Rally |  | #
| National Nutrition Day | Radio jingles, phone-in program, Rally
To improve proper food handling, preparation, and dietary diversity at among hard to reach communities | To engaged CSO for | Reactivation and trainig of existing support on food demonstration across the 21 LGAs (6grp/LGA)
| Conduct Food demonstration training across the 21 LGA | session at 5 hard to reach Communities per Ward in 5 LGAs with lowest nutritional indices
To improve nutrition surveillance and use of data for decision making.
Ministry/Agency: ocal government and chieftancy affairs
Objective | Activities | Sub-activities | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
Advocacy and resource mobilisation | Increase advocacy to LGAs for creation and funding of LG committee on food and Nutrition |  | P/sec MLGCA | No. of advocacy visits conducted, amount of funds approved and released | 21 LGAs | Jan-Dec 2021 | 2100000 | 21 LGAs
| reactivation of 21LGA committees on food and nutrition |  | P/sec MLGCA | no. of committees inaugurated | 21 LGAs | Quarterly Jan-Dec 2021 | 2100000 | 21 LGAs
Strenghten coordination | conduct of LGFNC quarterly meeting |  | p/sec MLGCA | No. of participants attending the meeting | 21 LGAs | Quarterly | 1500000 | LGAs, LGFNC
Service delivery | procurement and distrition of essential nutrition commodities E.g. RUTF, VIT A, IRON, AMOXICILIN, MICTRONUTRIENT POWDER |  | p/sec MLGCA | Commodities procured and distributed to LGAs | Facility level and designated centers | Jan-Dec 2021 |  | 21 LGAs
Ministry/Agency: NAFDAC
Objective | Activities | Sub-activities | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
Ensure there are local manufacturers / entrepreneurs developing locally sourced prepackaged and packaged food at affordable price | 1. Cousel clients on good manufacturing practices 2. Inspection of facility |  | NAFDAC FS and AN officers | number of producers of prepackaged nutrition complementary foods | Registered complimentary food | 60 days | Counseling is free Inspection and lab on Nafdac tarrif online | no cost
| Laboratory analysis of the produsct | [5 empty] | (50% discount on all MSMEs) prodoced documentation and requirements
Promotes exclusive breast feeding and compliance with international code of marketing of breast milk subtitute | 1. Inspection of wholesales and retail outlets of breast milk subtitute to ensure compliance 2. visit to healthcare facilities especialy ANC 3. survey of healthcare personel, manufacturers, Retailers, Mothers and general public on compliance |  | NAFDAC STAFFS | Zero violation of the code | compliance with the international code of marketing of breast milk subtitute | continous | - | -
| World Breasfeeding week |  | SCFN | Increased awareness | Exclusive breast feeding | continous | - | -
Ensure Vitamin A premix fortification of sugar,veg, oil, flour, magarine/butter and iodine in salt | 1. Animal fortification survey through sampling, lab analysis 2. Enforcement of fortification on regolated products |  | NAFDAC STAFFS | Number of targeted regulated products successfully fortified | All target regulated products to be fortified | continous | NAFDAC budget | -
Ensure women trained on food proccessing, soap making, etc. add value to the products by registering them | 1. Couselling them on good manufacturing practices 2. Inspections if facilities 3. Laboratory analysis of the products |  | NAFDAC STAFFS | Number of women successfully counselled | All women entrepreneurs successfully registered | 60 days | NAFDAC tarriff online | -
Ensure entrepreneurs supplied with tools and machineries for food proccessing add value to the finished products by registering them | 1. Counselling on GMP 2. Inspection 3. Lab analysis |  | NAFDAC STAFFS | Number of applicants received | Registered | 60 days | NAFDAC | Tarriff online
Ministry/Agency: CS - SUN : Civil Society, scalling up Nutrition
Objective | Activities | Sub-activities | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
Advocacy and resource mobilization | conduct advocacy visits on nutrution programme to key decision makers, opinion makers, religious / traditional leaders and the community to generate demand foe nutrition services |  | State coordinator | Reform, Reports, no. of advocacy done | stakeholders on nutrition policy makers, 10 advocacy | Feb - June 2021 | 150000 | partners
Coordination and multisectional partnership | Track the implementation of costed work plan developed at the state level |  | State coordinator CS-SUN |  |  | 2021-03-01 | 100000 | Partners
Capacity building | to promote the perticipation of women In agriculture (livestock, farming,small scale) |  | State coordinator CS-SUN | Reports coorperative formed | 100 women | Mar-Apr 2021 | 1500 | Partners
| ptomotes the formation of cooperative societies in the community |  |  | women engage in livestocks, backyard garden | 100 women
| training of people with sprcial needs on IYCF, people with disabilities, prison inmates |  |  | No. of trained inmates, people with disabilities, WLW HIV | inmates, PWD, WLWHIV, VVF 200
| Formation of committee, IYCF support groups |  |  | No. of SG formed | 5 IYCF SG
BCC | Dissemination of information and comminication on IYCF, through town hall meetings/FSC |  | program officer CS-SUN | No. of townhall meeting held | General public | Apr-Oct 2021 | 400000 | Partners
| conduct public campaign Radio programms on IYCF during world breastfeeding, Nutrition day |  |  | Rally, conducted radio program picture reports | 2 million |  | 700000
| conduct awareness campaign to promote food handling and food preparation and importance of dietery diversity |  |  | picture trainig conduction reports | General public |  | 500000 | Partners
| sensitize and orient seeking on appropriate health |  |  | pictures, number of meetings held | communities |  | 200000
behavior utilization of health services especially for infant and young children through community dialougue
Capacity building | conduct food demonstyration |  | state coordinator CS-SUN | pictures, number of food demonstartion conducted | PWD,prison inmate, WLW HIV | mar - july 2021 | 100000
| Building the capacity of people with special needs on proper diet, food handling and management through food demonstration |  |  | No. of people with special need | 100 VVF Patients |  | 100000
| Form and train LGA food security committees in collaboration with ministry of LG in the 21 LGAs |  | Program officer CS-SUN | No. of food security committee formed | 21 LGAs | Mar-July 2021 | 2000000
Ministry/Agency: Standard Organisation of Nigeria
Objective | Activities | Sub-activities | Person responsible | Indicator | Target | Timeline | Cost | Source of Fund
To monitor the production analysis of package waterto the requirement of the standard for human consumption | Quality assurance | letters of notification for inspecton dispatched to compaies scheduled to visit | SON Staffs | 4 package water producers to be inspected per day | 48 package water producers per month | quarterly | 10,000 per visit | state office allocation
|  | inspections carried out at respectivecompanies scheduled | SON Inspectors
|  | Sample drawn during inspection | SON Inspectors
|  | Sampled analised at the Son Laboratory to the requirements of the standard | SON Laboratory staffs
|  | feedbacks written in respect of the observation raised during inspection and outcome of the analysis results | SON Inspectors
|  | implementation of the feedback | Package water produders
To ensure quality production of local fertilizers and other fertilizers coming into kebbi state | Quality assurance | the same steps as listed above | the same as above | once every quarter | 4 times | every quarter | 10,000 per visit | state office allocation
to ensure quality of post harvest practices and food safety | To sensitize farmers on food safety and post harvest loses |  | SON Staffs | Farmers at the senatorial zones | twice per year | every 6 months | 200000 | state office allocation