## Slide 1
NIGERIA GOVERNORS’ FORUM (NGF)
STATES FISCAL TRANSPARENCY, ACCOUNTABILITY AND SUSTAINABILITY(SFTAS) TECHNICAL ASSISTANCE PROJECT
Date: 19th January 2022
Presented by:
Olanrewaju Ajogbasile
Senior Programme Manager,
NGF HelpDesk & SFTAS TA
oajogbasile@ngf.org.ng
+2349083411461

## Slide 2
S/N | Milestone/Activity | Estimated Timelines* | Responsible
1. | Desk-based work | January – March 2022 | IVA
2. | Field work in the States and collection of data | January – February 2022 | IVA and States
3. | Finalise assessment reports | April 2022 | IVA, States, PCU and WB
4. | Disbursement for original DLIs 1-9 2020 results (2020 APA) - Up to $9-15 million per State | Q2 2022 | WB, PCU and CBN
5. | Disbursement for new COVID-19 DLIs results (Sep -Dec 2021) 4 X DLRs 10.1 (2021), 11.3, 12.2 and 13.3 - Up to $6 million per State | Q2 2022 | WB, PCU and CBN
*The following information have been sent to all States:
Contact details of the IVA team assigned to each State.
Draft itinerary for the in-State field work.
Independent Verification Agent (IVA) APA information request and result submission form. States were required to have submited soft and hard copies to the IVA by 17th January 2022. Further delays may affect the verification and disbursement timelines.
    27 States have responded – Abia, Adamawa, Bauchi, Bayelsa, Benue, Borno, Cross River, Delta, Ebonyi, Edo, Ekiti, Gombe, Imo, Kaduna, Kano, Katsina, Kebbi, Kogi, Kwara, Lagos, Nasarawa, Ogun, Osun, Sokoto, Plateau, Yobe and Zamfara State.
    9 States have not responded – Akwa Ibom, Anambra, Enugu, Jigawa, Niger, Ondo, Oyo, Rivers and Taraba State .
SCHEDULE FOR 2020 ANNUAL PERFORMANCE ASSESSMENT (APA) (DLIs 1 – 9),
NEW 2021 DISBURSMENT LINKED INDICATORS (DLIs 10 – 13, Sep - Dec 2021) ASSESSMENT AND DISBURSEMENT

## Slide 3
S/N | EC/DLI | REQUIREMENT PENDING | DEADLINE | STATUS/MATTERS ARISING
1. | 2021 APA Eligibility Criteria Part I | Prepare their FY2022 State budget under the National Chart of Accounts (minimum of administrative, economic and function segment classifications), get the budget approved by the State Assembly, assented to by the Governor and published online. | 31st January 2022 | All 36 States are on track and leveraging NGF technical assistance.
2. | DLI 1.1 – FY21 Quarterly Budget Implementation Report ($0.3 million) | FY21 quarterly Budget Implementation Reports (BIRs) published on average within 4 weeks of quarter end to enable timely budget management – Q4 BIR due in 2022. | 28th January 2022 | All 36 States are on track and leveraging NGF technical assistance.
3. | DLI 7.2 - Quarterly Debt Reports, Annual state debt sustainability analysis and Medium-term Debt Management Strategy ($0.5million) | Quarterly state debt reports accepted by the DMO on average two months or less after the end of the quarter in 2021. | 28th February 2022 | States are to work with the Debt Management Office (DMO) for technical assistance. On DLI 7.1- Passage of a Debt Management Law ($2million) with Dec 2021 deadline, the following 6 States – Abia, Bayelsa, Delta, Kano, Kebbi and Nasarawa State - are advised to send a gazetted version of their debt management law to the DMO latest by Friday 21st January 2022.
4. | DLI 2.1 – Citizens input in budget ($0.5million) | Citizens’ inputs from formal public consultations are published online, along with the proposed FY22 budget. | 31st January 2022 | States are to work with the Open Government Partnership Secretariat for technical assistance.
UPCOMING ELIGIBILITY CRITERIA (EC) AND DISBURSMENT LINKED INDICATOR (DLI) DEADLINES in 2022

## Slide 4
S/N | EC/DLI | REQUIREMENT PENDING | DEADLINE | STATUS/MATTERS ARISING
5. | DLI 6.2 (2021 result) on e-Procurement (US$2 million): | Implement e-procurement in at least 4 MDAs (incl. Education, Health and Public Works) by 31st December 2021 and have at least 6 months of transactions going through the e-procurement system by 30th June 2022. Publish all contract award information in OCDS format on the online portal for the 4 MDAs For those MDAs without e-procurement: Publish contract award information above a threshold set out in the State’s procurement law/regulation on a monthly basis in OCDS format on the state website or online portal if available | 30th June 2022 | User Adoption Progress: Framework Agreement States: On Track – Kaduna, Edo, Niger, Kogi, Borno, Gombe, Kwara, Ondo, Yobe and Ekiti State. Marginally Behind – Zamfara, Kebbi, Sokoto and Bayelsa State. Significantly Behind – Jigawa and Akwa-Ibom State. Non-Framework Agreement States: On Track – Delta, Abia, Ebonyi, Lagos, Adamawa, Benue, Ogun, Bauchi, Plateau, Oyo and Enugu State. Marginally Behind – Anambra, Cross River, Imo, Kwara and Osun State. Payment Issues: Jigawa and Gombe State have made all payments. Kaduna and Edo State have made some payments but have one or two outstanding milestone payment. Bayelsa, Kano, Niger and Sokoto State have only paid for one milestone out of at least 3 due for payment. Akwa Ibom, Borno, Ekiti, Kebbi, Kogi, Ondo, Yobe and Zamfara State are yet to make any milestone payment to the vendor. All States concerned are also expected to provide evidence of With Holding Tax (WHT) deducted from European Dynamics. Vendor has began charging interest on delayed payments and may resort to withdrawing service where payment continue to delay. This could jeopardise the chances of these framework agreement States in meeting the revised DLI timeline of June FY2022. *Technical advisory is ongoing to framework agreement and non-framework agreement States.
UPCOMING ELIGIBILITY CRITERIA (EC) AND DISBURSMENT LINKED INDICATOR (DLI) DEADLINES in 2022

## Slide 5
Programme Coordination Unit
Mr. Stephen Okon,
The SFTAS-National Program Coordinator,
Director Home Finance Department,
Federal Ministry of Finance, Budget and Planning
Central Business District, Abuja.
stephenokon117@yahoo.com
08065643949
Mr. Ali Mohammed,
The Deputy National Program Coordinator
ali4m1968@gmail.com
07033337112
Please copy enquires to:
Oyinda Adedokun,
Programme Manager
oyindak@yahoo.com
08095360073
Office of the Auditor-General for the Federation as the IVA
Busayo Fawale
Programme Manager
fawale2002@gmail.com
08146505040
Please copy enquires to:
sftas@oaugf.ng
Nigeria Governors’ Forum (NGF)
Olanrewaju Ajogbasile
Senior Programme Manager, NGF HelpDesk & SFTAS TA
oajogbasile@ngf.org.ng
+2349083411461
Please copy enquires to:
saffun@ngf.org.ng
Zabiola@ngf.org.ng
Debt Management Office
Oluwatosin Akomolafe,
SFTAS DMO
Akomolafe.tosin@yahoo.co.uk
08095918519
Open Government Partnership (OGP) Secretariat
Tari Wills
Program Officer I (SFTAS/OGP)
tari.wills@ogpnigeria.gov.ng
08039248859
CONTACT DETAILS:
S/N | EC/DLI | REQUIREMENT PENDING | DEADLINE | STATUS/MATTERS ARISING
6. | DLI 11.3 on Urban property records (US$2.5 million): | Complete and update the property records for at least 50% of properties that have electricity connections in Urban as per criteria set out in the Verification Protocol, stored in an electronic database. Establish institutional arrangements as per criteria set out in the Verification Protocol to use the property records to improve or start the collection of property tax. | 30th June 2022 | 8 States (Anambra, Bauchi, Enugu, Imo, Katsina, Lagos, Rivers and Zamfara State) are yet to assign/release funding for project implementation (procurement of equipment, enumeration exercise, etc.) despite the deadline to have this in place by end of the third week of January 2022 to be eligible for technical support under the DLI. These States need to urgently release funding, communicate the project budget to the PCU latest by Friday 21st 2022. The PCU, World Bank, GIS & TA Firm will begin active TA engagement (including training, software, GIS, data sharing for geospatial data covering imagery, DTM, DSM, and building footprint) with every other State from next week.
UPCOMING ELIGIBILITY CRITERIA (EC) AND DISBURSMENT LINKED INDICATOR (DLI) DEADLINES in 2022