## F&N Security
TEMPLATE FOR THE 2020/2021 GOMBE STATE MULTISECTORAL NUTRITION OPERATIONAL PLAN
THEMATIC AREAS: Food and Nutrition Security
OBJECTIVES
SN | ACTITIVITIES | FREQUENCY | # OF PERSONS | TARGET | PERSONS RESPONSIBLE | QI Q2 Q3 Q4 |  |  |  | UNIT COST | TOTAL COST | INDICATORS | MOVS
1 | Promote improve food processing presevation, packing technology centred on small scale enterpreneurs |  |  |  | MOA
a | Develop and map small scale enterprises | 2days | 110 | small scale enterprises | MOEP | x |  |  |  | 1100000 | 2200000 | # of people mapped | Reports of the mapping
b | 2 days Capacity Building for Small scale enterprises | 3 batches | 110 | small scale enterprises | BOI |  | x |  |  | 1100000 | 2200000
c | Provision of implements/equitpment | 1 | 110 | small scale enterprises | BOI |  | x |  |  | 30000 | 3300000
d | Mentoring of the trainess | 4 |  | small scale enterprises | SCFN |  | x | x | x | 27272.7 | 300000
2 | awareness creation on proper use of agro chemicals in production and storage | 4 |  | Farmers | MOI | x | x | x | x | 60000 | 240000
3 | Conduct Capacity Building in Improved farming and preservation technology for women and youth Groups | 1 | 22 | Youth and Women Groups | MOA |  | x |  |  | 79236.4 | 1743200
4 | Conduct sensitization consumers and Household decision makers on the benefits of biofortified drugs and fortified food | 4 |  | House hold heads | MOI | x | x | x |  | 60000 | 240000
5 | Conduct trainingss for farmers in the use of genetically modified crops for faster harvest | 1 | 22 | farmers | MOA |  | x |  |  | 4752.2 | 104592
6 | Conduct 2 days training workshop for farmers to identify markets linkages for their produce | 2 | 22 | Farmers | MOA |  | x |  |  | 7131.3 | 156888
7 | Conduct trainings for women and youth Groups on food hygiene and quality food preparation | 15 | 440 | women and youths | MOH |  |  | x |  | 4793000 | 4793800
8 | Dessiminate media messages on food hugiene and quality food preparation | 4 |  |  | MOI | x | x | x | x | 60000 | 240000
9 | Facilitate mass purchase of agricultural produce by government at harvest, the storge and subsequent sale at control prices to keep food prices within reasonable limits |  |  | Communities | MOA | [5 empty] | 140000000
| Implement School feeding program in all primary schools to improve nutritional status |  |  | School children | MOE | [5 empty] | 200000000
| Provide seeds for gentically modifies crops for use by 55 local farmers |  | 55 | local farmers | MOA |  |  |  |  | 50000 | 2750000
| provisions of mini silos solar drier and fish smoking eqitpments to small holder farmers | 1 | 55 | Farmers | MOA |  |  |  |  | 100000 | 5500000
| provision of subsidised(fertilizers, ipmroved seeds , insecticides , herbicides ) to farmers group |  |  | Farmers | MOA |  |  |  |  | 2954545.5 | 32500000
| re trained teachers in primart and secondary schools on Nutrition education |  | 55 | Teachers | MOE |  |  |  |  | 34864 | 1917520
| Support farmers with irrigation facilities to improve all year crop production |  | 330 | Farmers | MOA/MOWR |  |  |  |  | 50000 | 16500000
| Support the creation of food and Nutrition clubs in all primary and secondary schools |  | 3 | Pri. & Sec. School | [5 empty] | 33333.3 | 100000
| Support the estbalishment of school gardening in secondary schools in the state |  | 3 | Schools | MOE |  |  |  |  | 183333.3 | 550000
| Train extension workers on dietry diversification, Nutrition Education, traditional method of food processing and storage | 2 | 55 | extension workers | MOA |  |  |  |  | 30858 | 1697190
| Train extension workers on improve farming techniques | 2 | 55 |  | MOA |  |  |  |  | 30858 | 1697190
| train staff of regulatory agencies in newer methodologies for quality assurance | 3 | 15 | NAFDAC, SON, MOH | MOH |  |  |  |  | 63917.3 | 958760
| Train street food vendors on safe production of street food | 3 | 33 | Food Vendors | MOH |  |  |  |  | 29053.3 | 958760
| Training of farmers groups on improved method of poultry production, fisheries and small ruminants | 2 | 22 | Farmers | MOA,Water Resources ,Husbandry |  |  |  |  | 7131.3 | 156888
| training of women on establishment of back yard gardens and provisions of start up funds as capital | 1 | 22 | Women Groups | MOA |  |  |  |  | 42049.3 | 1387628
422192416

## Research in F&N
TEMPLATE FOR THE 2019/2020 GOMBE STATE NUTRITION OPERATIONAL PLAN
THEMATIC AREAS: Research in Food and Nutrition
OBJECTIVES
SN | ACTITIVITIES | FREQUENCY | # OF PERSONS | TARGET | PERSONS RESPONSIBLE | QI Q2 Q3 Q4 | UNIT COST | TOTAL COST | INDICATORS | MOVS
1 | Develop Food and Nutrition Reseach Agenda(Prioity Areas for further Research ) in Gombe State
a | Advert and engagement of a Consultant | [5 empty] | 250000 | 250000
b | Mapping and Selection of Reasech Team | [5 empty] | 0 | 0
c | Training of the Reseach Team | 1 | 20 | GSU,FUK,HOR | MOH |  | 61200 | 1224000
2 | Capacity of Tertiary Institutions in Condcuting Research in Food and Nutrition in Gombe State | 1 | 20 | GSU,FUK,HOR | MOH |  | 13893.75 | 277875
2 | Conduct annual disssemination of research result in food and Nutrition in Gombe State | 1 | 50 | stakeholders | SCFN |  | 4420 | 221000
3 | Conduct periodic (yearly) Food consumption and Nutrition Survey for policy imapct
a | Development of the Survey | [6 empty] | 144000
b | Conduct Survey in all the LGAs | 3 | 55 | Enumaerators | SCFN |  | 15000 | 1650000
c | Analysis of the data | 3 | 20 | reseachesr | SCFN |  | 30000 | 600000
d | Production of survey reports |  | 10000 |  | SCFN |  | 500 | 500000
e | Dessemination meeting |  | 150 |  |  |  | 12240 | 1836000
4 | Conduct periodic, yearly semi quaterly assurance utilization coverage and evualuation of food and nutrition Programs | 4 | 20 | reseachesr | SCFN |  | 250000 | 1000000
5 | Conduct quaterly advocacy visits to lawmakers for increase funding for reseach in food and nutrition in Gombe State | 4 | 20 | GSHA | SCFN |  | 45000 | 180000
6 | Conduct Research in the Identified areas in Fodd and Nutrition in Gombe State
a | Development of the Survey | [6 empty] | 144000
b | Conduct Survey in all the LGAs | 3 | 55 | Enumaerators | SCFN |  | 15000 | 1650000
c | Analysis of the data | 3 | 20 | reseachesr | SCFN |  | 30000 | 600000
d | Production of survey reports |  | 10000 |  | SCFN |  | 500 | 500000
e | Dessemination meeting |  | 150 |  |  |  | 12240 | 1836000
7 | Develop Food and Nutrition Reaseach Agenda(rioirty areas for further Reseach in Gombe State) | 4 | 20 | reseachesr | SCFN |  | 86050 | 1721000
8 | Provide annual grant for state institutions to carry out research on Food and Nutrition | 1 | 5 | GSU,COE,CON,CHT,State Poly | SCFN |  | 700000 | 3500000
17833875

## Enhance Care Giving Capacity
TEMPLATE FOR THE 2019/2020 GOMBE STATE NUTRITION OPERATIONAL PLAN
THEMATIC AREAS: |  | Enhance Care Giving Capacity
OBJECTIVES |  | 1. To build the capacity of Traditional, Religious Leaders and key service provideders in Gombe State by the end of 2016. | To provide core nutrition services and counselling to Nutrition offcers in the State and LGAs.
SN | ACTITIVITIES | FREQUENCY | # OF PERSONS | TARGET | PERSONS RESPONSIBLE | TIME FRAME |  |  |  | UNIT COST | TOTAL COST | INDICATORS | MOVS | NOTES
[6 empty] | Q1 | Q2 | Q3 | Q4
1 | A week long Advocacy visit to Gatekeepers( Traditional,Religious and Primary health care providers in the 11 LGA) | 2 | 20 | Key Gate keepers in the community and service providers | GSPHCDA/ SMOH | Q1 |  | Q3 |  | 5000 | 1400000 | Number of gate keeper / service providers reach | Attendace Sheets, Singned Payments Sheets, Pictures and Activity report. | Transport allowance to 20 people @ 3000 and 2000 Naira for feeding
2 | Facility Sensitization on food and Nutrition for Women at the PHC | 4 | 1322 | 50 Pregnant Women and Lactating Mothers in 661 PHCs | GSPHCDA/ SMOH | Q1 | Q2 | Q3 | Q4 | 2000 | 10576000 | Number of women reached in all the selected facilities | Registers,pictures,Signed payment sheet,Reports | 1000 for stipend and 1000 for stationaries
3 | Advocacy visit to MDAs( MOE,MOH,MLG,MOWA and MOEP)for the formation creches in public and private Inst and Baby friendly hospital initiative | 4 | 15 | Comissioners, Permanent Secretaries and Directors and Deputy Directors. | SCI, MNCH Coalition, CSO | Q1 | Q2 | Q3 | Q4 | 2000 | 120000 | Number of Advocacy visits conducted | Attendace Sheets, Singned Payments Sheets, Pictures and Activity report. | 1000 for transportation allowance.
4
5 | Formation of peer Education program for girls in 20 selected communities in 11 LGAs | 1 | 5 | Community Girls | MOWA, MOE and CSOs | Q1 |  |  |  | 5000 | 5500000 | Number of peer groups formed | Reports, Payment sheets,Attendance, Pictures | Transport allowance for personel to conduct the activity in 3 weeks

## Coordination&Multi Sectoral Par
TEMPLATE FOR THE 2019/2020 GOMBE STATE NUTRITION OPERATIONAL PLAN
THEMATIC AREAS: |  | Coordination and Multi-Sectoral Partnerships.
OBJECTIVES |  | 1.To achieve effective collaboration among various stakeholder and MDAs on issues of holistic nutrition in Gombe State |  |  |  | 2. To engage partners both local and international for a sustainable development on nutritional issues in Gombe State.
SN | ACTITIVITIES | FREQUENCY | # OF PERSONS | TARGET | PERSONS RESPONSIBLE | TIME FRAME |  |  |  | UNIT COST | TOTAL COST | INDICATORS | MOVS | NOTES
[6 empty] | Q1 | Q2 | Q3 | Q4
1 | A week long Mapping of partners working on Nutrition in Gombe State | 1 | 8 | Governmet and private partners working on Nutrition in the State | MOH, MOE, MOI,GSPHCDA,CSOs | Q1 |  |  |  | 2000 | 112000 | Number of private sectors visted. 2. Number of days activity was conducted | Retirements, pictures and Reports | 8 People will be paid transport allowance of 2000 flat per day for 7 days
2 | 2 days Round Table meeting with Private sectors working on Nutrition | 2 | 25 | Private sectors working on nutrition in the State | MOH, MOE, MOI,GSPHCDA,CSOs | Q1 |  | Q3 |  | 5000 | 500000 | Number of participant in attendance | Reports,Attendance sheets, Payments sheets Pictures. | 2 tea breaks @ 1500, 1 lunch @ 1500 and transport 2000 for each participant for 2 days
3 | 3 days meeting for development and adaptation of guidelines and standards for stakeholders | 1 | 25 | Private sectors working on nutrition in the State | SCI/ MDAs | Q1 |  |  |  | 5000 | 375000 | Number of participant in attendance. | Draft of document, Pictures, Repoerts, Attendance sheets, Payments sheets. | 2 tea breaks @ 1500, 1 lunch @ 1500 and transport 2000 for each participant for 3 days
4 | Quarterly meeting to review the activities of SCFN in the State | 4 | 40 | SCFN and relevant stake holders | SCI/ MDAs | Q1 | Q2 | Q3 | Q4 | 2000 | 320000 | Number of Participants | Reports,Attendance sheets, Payments sheets Pictures. | Transport allowance @ 2000 for each participant.
5

## Safe water&Improved Sani
TEMPLATE FOR THE 2019/2020 GOMBE STATE NUTRITION OPERATIONAL PLAN
THEMATIC AREAS:
OBJECTIVES: TO EXPAND THE PROVISION OF SAFE WATER AND IMPROVED SANITATION FACILITIES AT ALL LEVELS.
SN | ACTITIVITIES | FREQUENCY | # OF PERSONS | TARGET | PERSONS RESPONSIBLE | TIME FRAME |  |  |  | UNIT COST | TOTAL COST | INDICATORS | MOVS
[6 empty] | Q1 | Q2 | Q3 | Q4
OBJECTIVE ON WATER SANITATION: EXPAND THE PROVITION OF SAVE WATER AND IMPROVED SANITATION FACILITIES AT ALL LEVELS
1 | Conduct Health Education and Community Mobilization on improved hygiene and sanitation. | Quarterly in all LGAs | 15 | Community Leaders/Members, women, Children, Youth, CBOs. | WATSAN, Min. of Environment, SPHCDA, Min. of Water Resources. | X | X | X | X | 412500 | 1650000 | 1500 persons reached per LGA. | Sensitization /Activity Report, Pictures.
2 | Conduct Mapping of existing toilet facilities in the state. | once | 4 | 11 LGAs | WATSAN, Min. of Environment, SPHCDA, Min. of Water Resources. |  |  |  | X | 20000 | 220000 | List of toilet facilities mapped. | Detailed report of survey.
3 | Construction of 22 blocks of 3 component of VIP latrines (per year) in Schools, Health facilities and communities 50 per latrine. | Once | 22 Contractors | 11 LGAs | Min. of Works, Min. of Environment, WATSAN. |  |  |  | X | 850000 | 18700000 | Project Completion | Pictures, Project Completion Report.
4 | Construction of Gombe South Regional Water to ensure full coverage of water supply in the state.
5 | Construction of non - borehole water sources in 33 communities of 3 LGAs (Dukku, Nafada & Akko)
6 | Develop IEC materials on handwashing | Once | 1 Consultant | 11 LGAs | Min. of Works, Min. of Environment, WATSAN, Consultant. |  |  | X |  | 500 (Per Pack X 10,000) | 5000000 | No of IEC Materials produced. | Invoice for IEC materials produced.
7 | Establishment of WASHCOM in 110 communities across 11 LGAs | Once | 110 Communities | 11 LGAs | WATSAN, Min. of Environment, SPHCDA, Min. of Water Resources. |  |  |  | X | 82456.14 | 9070175.4
8 | Operation and Maintenance of Gombe Regional Water/Water purification and treatment solution.
9 | Re-activate community wide sanitation program (Duba gari) driven by environmental health workers (including safe handling and disposal of infant feaces and solid waste management). | Monthly | 5 per ward | 114 Wards | WATSAN, Min. of Environment, SPHCDA, |  |  | X | X | 339,318.18 (per LGA) | 4392500 | No of functional committees | Pictures, Report
10 | Repairs and rehabilitation of hand - fitted boreholes across the state. | Twice per year | WATSAN Staff | 114 Wards | WATSAN. |  |  |  | X | 20,000 (Per Ward) | 2280000 | No of boreholes repaired. | Reports, Pictures.
OBJECTIVE ON HEALTH: ENHANCE PROVISION OF QUALITY HEALTH SERVICES
1 | Conduct orientation on integration of nutrition services into PHC for all health workers and LGA program managers | 1 | 4560 | 114 Wards | SPHCDA |  |  |  | X | 25,268 (Per PHC In a Ward) | 2880638 | No of Health Personnel oriented | Activity report, attendance, pictures.
2 | Conduct managerial trainings for Nutrition desk officers at LGA level | 1 | 14 | 11 Nutrition Desk Officers | SPHCDA |  |  |  | X | 4358 (Per Person) | 47938 | No of Nutrition Desk Officers trained. | Report, Attendance, Pictures
3 | Provision of essential maternal and child nutrition supplies - commodities and equipment, to all health centres in the state.
4 | Review PHC Treatment guidelines to include Nutrition Counselling and information across all disease areas. | 1 | 25 | 25 Nutrition Stakeholders | SPHCDA |  |  | X |  | 5335.2 | 133380 | The reviewed PHC Treatment guidelines. | Report, Attendance, Pictures
5 | Scale up CMAM sites to the remaining 3 LGAs and strengthen referrals to stabilization centres | 1 | 7 | 3 LGAs | SPHCDA |  |  |  | X | 5317500 | 15952500 | No of CMAM LGAs scaled up | Report, Attendance, Pictures
6 | Strengthen data management for nutrition at the PHC level to improve identification and tracking of cases. | 1 | 15 | 15 PHCs | SPHCDA |  |  |  | X | Computer & Accessories X 3 - 450,000. Cabinets X 15 - 750,000. Printing of M&E Tools - 100,000. 3 Nutrition Focal Officers Data management Training/15 Facilities In-Charge/ LGA M&E Officers - 115,000. Training of Comm. Volunteers on identification and tracking of cases X 30 - 165,000 | 1580000 | No of PHCs with Strengthened Data management | Invoices, Training attendances, reports and pictures.
7 | Strengthen supportive supervision for nutrition services at all levels - State & LGA. | Quarterly | 5 Personnels | 15 PHCs (3 LGAs) | SPHCDA |  |  | X | X | 10000 | 1500000 | No of PHCs visited. | Supervision Report, Pictures.
| Train and mentor health workers and Community Volunteers on essential nutrition services across the state. | Once | 570 Health Workers and Community Volunteers | 11 LGAs | SPHCDA |  |  |  | X | 10000 | 5700000 | No of trained and mentored Health Workers and CVs trained on essential nutrition services. | Training Report, Attendance list, Pictures.

## Behavious Change and demand
TEMPLATE FOR THE 2019/2020 GOMBE STATE NUTRITION OPERATIONAL PLAN
THEMATIC AREAS: Behaviour change and demand generation for Nutrition
OBJECTIVES:4. To increase the knowledge of nutrition among the populace and nutrition education into formal and non/informal trainings;
ACTITIVITIES | SUB-ACTITIVITIES | FREQUENCY | # OF PERSONS /Quantity | TARGET | PERSONS RESPONSIBLE | TIME FRAME |  |  |  | UNIT COST | TOTAL COST | INDICATORS | MOVS
[6 empty] | Q1 | Q2 | Q3 | Q4
Conduct special radio and television campaign on adherence to food safety regulations, and mandatory standards for foods including imports | Production of special radio and television jingles on adherence to food safety regulations, and mandatory standards for foods including imports in Hausa and English Languages | 2 | 4 | 4 | Representative of Min. of information in SCFN | 1 |  | 1 |  | cost of production @50000x8 | 400000 | number of jingles produced | copies of jingles, receipt
| Airing special radio and television campaign on adherence to food safety regulations, and mandatory standards for foods including imports | 4 | 4 times per month | 12 | Representative of Min. of information in SCFN | 1 | 1 | 1 | 1 | rate of jingle @8000 x12x4 | 384000 | number of jingles aired | receipt,
| Sponsor Kainuwa Drama group in radio and TV to conduct drama series on adherence to food safety regulations, and mandatory standards for foods including imports | Once a quarter | 12 | 4 | Representative of Min. of information in SCFN | 1 | 1 | 1 | 1 | cost of drama is 26000 | 104333 | number of drama aired | receipt,
| Advocate for airing of drama by GMC | 1 | 1 | 1 | Director MEP | 1 |  |  |  | 0 | 0
Sub total | [10 empty] | 888333
Conduct stakeholders dialogue at State and LGA levels on importance of eating varieties of food | Conduct stakeholders dialogue at State level on importance of eating varieties of food(provide refreshment | 2 times per year | 2 | 50 | Nutrition Officer |  | 1 |  | 1 | (500 per head, transport for participants (2000) and invitation(5000) | 250000 | number of community dialogue held | report, pictures and attendance
| Conduct town hold meeting with stakeholders dialogue at community level in 5 LGAs on importance of eating varieties of food | once a yearr | 1 | 500 | Nutrition Officers at LGAs |  |  | 1 |  | (support 5 state team member to visit to LGAs to advocate for the activities @ 48500, provide cost of mobilisation (10,000X 5), fueling @15,000 per LGA for 5 per LGA, snacks allowance for members of state team(@ 2000X 5X5) and cost of publicity (5000X5), refreshment for participants @200*500 | 348500 | number of meeting held | report, pictures and attendance
Sub total | [10 empty] | 598500
Develop and distribute IEC materials on Food and Nutrition through appropriate channels in Gombe state. | conduct 2 days meeting to develop and pre test IEC materials on Food and Nutrition through appropriate channels in Gombe state. | 1 | 20 | nutrition officers , media, min. of information e.t.c | min. of information |  | 1 |  |  | hall @30,000x2, lunch@1500x20x2, communication @2000, material @500x20, transport for pretest@5000x3x2, allowance @2000x3x2 | 174000 | number of meeting held | report, pictures and attendance
| Printing of IEC materials on Food and Nutrition through appropriate channels in Gombe state. | 1 | 1000 | 10 different types of IEC amterials | min. of information |  | 1 |  |  | printing @500x 1000 | 500000 | Number of IEC materials produced | copies of IEC, receipt, invoice
| Distribution of IEC materials on Food and Nutrition through appropriate channels in Gombe state. | 1 | 1000 | 11 LGAs | LGA nutrition team |  |  | 1 |  | 10000x11 | 110000 | Number of IEC distributed | distribution list
Sub total | [10 empty] | 784000
Update the state pre-service curricula for all health programs to include Nutrition counseling and information | Conduct advocacy to statekeholders on the need for the Update the state pre-service curricula for all health programs to include Nutrition counseling and information | 1 | 15 | 10 stakeholders (office of head of service, min. of health, civil service commision, schools of nursing and health tech and mini. Health and education LGA services commision | SCFN | 1 |  |  |  | transport @15000, publicity@50000, 2000 x 15 for snack allowance communication @2000 | 97000 | advocacy conducted | report of advocacy, attendance and pictures
| conduct 3 days meeting with the relevant stakeholder to update pre service curriculum | 1 | 30 | 11 stakeholders (office of head of service, min. of health, civil service commision, schools of nursing and health tech and mini. Health and education LGA services commision | SCFN |  |  | 1 |  | hall@50000x3,matrial@500x30,luch and tea break 2000x30x3, transport 2000x3x30 |  | number of meeting held | report, pictures and attendance
| production of state pre-service curricula for all health programs to include Nutrition counseling and information | 1 |  | 500 copies | SCFN |  |  | 1 |  | printing @500x 500 | 250000 | Number of copies of pre-service curricula produced | copies of pre service curriculum, receipt, invoice
| support 2 days oreintation of newly employed health workers on the the updated pre-service curriculum | 1 |  | 100 employees | SCFN |  |  |  | 1 | hall@50000x2x 2,material@500x100,luch and tea break 2000x100x2, transport for facilittors 2000x3x2 days, faciltation allowance 10,000x2x3 | 722000 | number of meeting held | report, pictures and attendance
| distribute the updated ducuments to all PHC facilities | 1 |  | 540 PHC | 12 nutritional officers |  |  | 1 |  | transport @15000x11 | 165000 | Number of updated documents distributed | distribution list
| support 2 days oreintation of PHC staff on the the updated pre-service curriculum | 1 | 400 | 400 PHC | SCFN |  |  | 1 | 1 | lunch@400x1000x2 days, transport for participants @1000x400, facilitors @5000x 3 x11 LGA, allowance 10000x3x11, communication @2000x11 LGAs | 1568500 | number of meeting held | report, pictures and attendance
Sub total | [10 empty] | 2802500
Conduct campaign during World Nutrition week to increase Nutrition awareness | Conduct preparation meeting with relevant stakaholders during World Nutrition week to increase Nutrition awareness | 1 | 20 | 20 | nutrition team |  |  | 1 |  | resfreshment @1000x 20, transport@2000 x20 | 60000 | number of meeting held | report, pictures and attendance
| printing of banners and IEC material | 1 | 1000 | 3 banners, 1000 t-shirts and fez cap, 2000 hands bills | organisation committee |  |  | 1 |  | 3 banners @15,000, 1000 t-shirts and fez cap @ 1500=1,500,000,2000 hands bills @100,000 | 1615000 | Number of IEC materials produced | copies of IEC, receipt, invoice
| conduct rally during to celebrate world nutrition week | 1 | 1000 | Gombe metropolitan | organisation committee |  |  | 1 |  | fueling @50000,water and glucose @20,000, inviation 5000 | 75000 | number rally held | activity report, pictures
| carry out round table discussion with stakeholders to celebrate world nutrition week | 1 | 200 | to create awareness and address nutrition challenges | organisation committee |  |  | 1 |  | refreshment @1500@200, drama troupes @50,000, facilitators 5000x5=25000, hall 30000 | 405000 | number of meeting held | report, pictures and attendance
| conduct media chart with various state media station during world nutrition week | 1 | 10 | GMC, ray power, progress, NTA and 5 news papers | organisation committee |  |  | 1 |  | transport @5000x10 | 50000 | media chart held | activity report, pictures
| Publicity during world nutrition week | 1 | 5 | GMC, ray power, progress, NTA and 5 news papers | organisation committee |  |  | 1 |  | publicity @30,000x5 | 150000 | pubicity ensured | copies of programme held, activity report, pictures
| support various11 communities (1/LGA) activities at all the LGA during the week to mark world nutrion week | 1 | 22 | 100 people /community= 1100 | organisation committee |  |  | 1 |  | refreshment @250@1100, transport @5000x 11, allowance @ 5000x11x 3 | 495000 | number of meeting held | report, pictures and attendance
Sub total | [10 empty] | 2850000
Conduct high level advocacy to the Governor, LGA chairmen, Commissioners, Legislators, Emirs on the multi-sectoral nature of nutrition and need for increased visibility | One day meeting to develop advocacy kits for the conduct high level advocacy to the Governor, LGA chairmen, Commissioners, Legislators, Emirs on the multi-sectoral nature of nutrition and need for increased visibility | 1 | 15 | 5 copies advocacy kits | Director MEP | 1 |  |  |  | resfreshment 500x15, transport @1000*15 | 22500 | number of meeting held | report, pictures and attendance
| Printing of advocacy kits | 1 | 1 | 6 copies advocacy kits | Director MEP | 1 |  |  |  | 1000 | 5000 | Number of advocacy kits produced | copies of advocacy kits, receipt, invoice
| Sending and follow up letters for advocacy visits to the Governor, LGA chairmen, Commissioners, Legislators, Emirs on the multi-sectoral nature of nutrition and need for increased visibility | 1 | 15 | 15 | Director MEP |  | 1 |  |  | 3000 for distribution of letters | 3000 | Number of invitation sent | copies of of letters and evidence of recieved
| Conduct high level advocacy to the Governor | 1 | 30 | 2 buses | Director MEP |  | 1 |  |  | 5000 for fuel of vehicle x 2 vehicle | 10000 | advocacy held | report, pictures and attendance
| Conduct high level advocacy to the 11 LGA chairmen and 5 Commissioners, | 1 | 15 | 2 buses | Director MEP |  | 1 |  |  | 5001 for fuel of vehicle x 2 vehicle | 10000 | advocacy held | report, pictures and attendance
| Conduct high level advocacy to the Legislators at house of assembly on the multi-sectoral nature of nutrition and need for increased visibility | 1 | 15 | 2 buses | Director MEP |  | 1 |  |  | 5000 for fuel of vehicle x 2 vehicle | 10000 | advocacy held | report, pictures and attendance
| Conduct high level advocacy to the 4 Emirs on the multi-sectoral nature of nutrition and need for increased visibility | 1 | 30 | 2 buses | Director MEP |  |  | 1 |  | 1500 for fuel of vehicle x 2 vehicle | 30000 | advocacy held | report, pictures and attendance
Sub total | [10 empty] | 90500 | advocacy held | report, pictures and attendance
Conduct knowledge, attitude and practice survey on food and nutrition in the three senatorial district | Identify and engage a consultant and research team to Conduct knowledge, attitude and practice survey on food and nutrition in the three senatorial district | 1 | 16 | Consultant | M0EP |  | 1 |  |  | 30,000 for cosultancy fee x30 days, DSA @30,000 for 30days | 1800000 | consultant engaged | copy of engagement report
| Conduct training of research team knowledge, attitude and practice survey on food and nutrition in the three senatorial district | 1 | 16 | Research team | consultant |  | 1 |  |  | hall 50,000x3=150,000Workshop Mats 500x15=7500, lunch 1500x16x3=72,000 transport Allowance 2000x15x3=90,000 | 319500 | number of participants trained | report, pictures and attendance
| print research tool | 1 | 450 |  | research team |  | 1 |  |  | 450x100 | 450000 | Number of reserch tools | copies of research tools, receipt, invoice
| carry out field work | 10 | 15 |  |  |  | 1 |  |  | 10000 allowance for field officers x10 days x15 participants | 1500000
| prepare report | 1 | 1 |  | consultant |  |  |  |  | 0 | 0 | report produced | copies of research report
| conduct dissemination meeting | 1 | 150 | stakeholders | MOEP |  |  |  |  | Transport allowance 2000x150=3000 Lunch 1000x15000=150000 Community moblisation =10000 | 460000 | number of meeting held | report, pictures and attendance
| produce and distribute report | 1 | 500 | MDAs,INGOs,Community leaders etc | MOEP |  |  | 1 |  | 400 | 200000 | Number of report distributed | distribution list
Sub total | [10 empty] | 4729500
Conduct trainings and support for community health workers and volunteers to continuously mentor women and community members on | Conduct 3 days trainings of 110 (10/LGA) community health workers and volunteers to continuously mentor women and community members on | 1 | 110 | community health workers and volunteers | Nutritional officers |  | 1 |  | 1 | hall @30,000x2, lunch@1500x110x2, communication @2000, material @00x110, transport for @2000x110, faciltators allowance @10000x3 | 653000 | number of participants trained | report, pictures and attendance
| support for 110 community health workers and volunteers to continuously mentor women and community members on | 1 | 110 | community health workers and volunteers | Nutritional officers |  | 1 | 1 | 1 | transport@1000x110x6, | 990000 | number of communities engaged | report, pictures and attendance
| Support M&E officers of LGA to collate data and report SCN | [5 empty] | 1 | 1 | 1 | transport and snacks allowance data collection @ 30000x3 quarters | 90000 | Data colleted | report
Sub total | [10 empty] | 1733000
Conduct sensitization meetings with Community and opinion leaders on cultural practices affecting food and nutrition | identify 20 communities for meetings with Community and opinion leaders on cultural practices affecting food and nutrition (5000 communication) | 1 | 1 | 15 | State nutritional officer |  | 1 |  |  | 0 | 5000 | Number of communities identified | List of selected communities
| conduct advocay to the communities for conduct sensitization meetings with Community and opinion leaders on cultural practices affecting food and nutrition (transport @2000*20) | 1 | 1 | 30 | LGA nutrition Officer |  | 1 |  |  | 2666.6667 | 40000 | number advocacy conducted | report and pictures
| One day sensitization meetings with 20 Community and opinion leaders on cultural practices affecting food and nutrition (transport @5000 *20, allowance for the team 2000*15 , refreshment @500X 20X20 participants | 1 | 1 | 15 | [6 empty] | 330000 | number of meeting held | report, pictures and attendance
375000
Sub total
Support the 114 WDCs to integrate Nutrition messaging into their activities at the ward level | Identify 3 LGAs (1/senetorial district) and 5 WDCs per LGA to support WDC into activities at ward Level | 1 | 1 | 1 | State nutritional officer | 1 |  |  |  | 0 | 0 | Number of wards selected | list of WDCs
| Conduct 2 days trainiing of members of 15 WDCs on intergration of Nutrition messaging and refferal cases of severe cases of malnutrion to CMAN (transport for facilitators @15,000 per LGA X3, transport for participants@2000*45, Lunch and tea break @1500X50X2, training material @500*45, communication @2000) | 1 | 45 | 15 WDCs | State nutritional team | 1 |  |  |  | 6878.3333 | 309525 | Number of WDCs trained | reports, pictures and attendance
| Production of registers and refferal tools and distribute them during ( @30,000) | 1 | 1 | 150 registers and 150 refferal booklet | State nutritional team | 1 |  |  |  | 500 | 150000 | Number of WDC trained | copies of registers and invoice
| support nutritional officers to join quarterly meetings of 15 WDCs to collate data and review their activities and share report (transport @7,000X3X*4) | 4 | 3 | 60 meetings | LGA nutional officers | 1 | 1 | 1 | 1 | 21000 | 84000 | number of conducted | reports, pictures and attendance
| provide incentives to member of WDC to ensure effective refferal (@1500*45*4) | 4 | 48 | 48 persons | State nutritional team | 1 | 1 | 1 | 1 | 1000 | 192000 | Number of WDC supported | reports and attendance
| conduct one day annual review meeting with stakeholder to performance for scaling (transport @3000*55, lunch and tea break @1500 *55, hall @50000,communication @2000) | 1 | 55 | 1 meeting | State nutritional team |  |  |  | 1 | 4537.2727 | 249550 | number of meeting held | report, pictures and attendance
Sub total | [10 empty] | 985075
Grand total | [10 empty] | 15745908

## Resource Mobilization
TEMPLATE FOR THE 2019/ 2020 GOMBE STATE NUTRITION OPERATIONAL PLAN
THEMATIC AREAS: Improve resource mobilization, utilization and accountability at all levels
OBJECTIVES:4. cross cutting
SN | ACTITIVITIES | SUB-ACTITIVITIES | FREQUENCY | # OF PERSONS /Quantity | TARGET | PERSONS RESPONSIBLE | TIME FRAME |  |  |  | UNIT COST | TOTAL COST | INDICATORS | MOVS
[7 empty] | Q1 | Q2 | Q3 | Q4
1 | Develop a resource mobilization strategy for the state | Identify and engage a consultant to develop resource mobisation stragey | 1 | 1 | Consultant | M0EP |  | 1 |  |  | 75000 | 750000 | Development a resource mobilization strategy for the state | copy of a resource mobilization strategy for the state
| Sub total | [10 empty] | 750000
6 | Conduct Advocacy to executive and legislative arms of Government on the need for sufficient budgetary allocation and timely release of fund for food and nutrition. | Conduct high level advocacy to the Governor | 1 | 30 | 2 buses | Director MEP |  | 1 |  |  | 2000 for fuel of vehicle x 3 vehicle, snack @5000x30, communication @5000 | 80000 | advocacy conducted | report of advocacy, attendance and pictures
|  | Conduct high level advocacy to the Legislators at house of assembly | 1 | 15 | 2 buses | Director MEP |  | 1 |  |  | 2000 for fuel of vehicle x 3 vehicle, snack @5000x30, communication @5000 | 80000 | advocacy conducted | report of advocacy, attendance and pictures
| Sub total | [10 empty] | 160000
3 | Build the capacity of staff of MDAs to mobilize resources | Identify and engage a consultant to provide on the job capacity buiding on resource mobilisation to 5 MDAs | 1 | 1 | 6 (Minof agric, MOEP, MOH, SPHDA, MOWA, RUWASA) | M0EP |  | 1 |  |  | 55000 | 550000 | number of MDAs whose capacity built | training report, pictures and attendance
| Sub total | [10 empty] | 550000
4 | Introduce public hearing on annual state budget | Conduct high level advocacy to the Legislators at house of assembly | 1 | 15 | 2 buses | Director MEP |  | 1 |  |  | 2000 for fuel of vehicle x 3 vehicle, snack @5000x30, communication @5000 | 80000 | advocacy conducted | report of advocacy, attendance and pictures
|  | Carry out one day interative session with Legislators at house of assembly on the of public hearing on annual state budget | 1 | 30 |  | SCFN |  |  | 1 |  | hall@50000x1,matrial@500x30,lunch and tea break 2500x30x1, facilitation20000x2, 10000 communication | 190000 | meeting conducted | activity report, attendance and pictures
| Sub total | [10 empty] | 270000
| Establish mechanisms to leverage corporate social responsibility opportunities from the private sector for Nutrition promotion | write letters to private sector to leverage corporate social responsibility opportunities for Nutrition promotion | 1 |  | 10 private sectors | SCFN |  |  | 1 |  | 0 | 0 | Number coporate organisation engaged | copy of letters and acceptance by private sectors
|  | Invite some to attend quarterly meeting of food and nutrition | 1 | 5 | 11 private sectors | SCFN |  |  | 1 |  | 0 | 0 | Number coporate organisation that attended quarterly meeting | activity report, attendance and pictures
| Sub total | [10 empty] | 0
5 | Creation of nutrition units with budget lines, plans and M&E in all relevant MDAs and ensure components of the costed plan is included in their annual budget | conduct advocacy visits to the Commissioners of all relevant MDAs for the Creation of nutrition units with budget lines, plans and M&E in all relevant MDAs and ensure components of the costed plan is included in their annual budget | 1 | 10 | 15 (8 Mins and 2 agencies | Director MEP |  | 1 |  |  | transport @10000*3*10 | 300000 | number of advocacy conducted | report of advocacy, attendance and pictures
|  | conduct 3 days annual workplan meeting with relevant MDAs | 1 | 1 | 10 | M0EP |  |  | 1 |  | hall@ 3x50000, lunch and tea @25x3, | 1152000 | number of meeting s held | activity report, attendance and pictures
| Sub total | [10 empty] | 1452000
| Conduct annual nutrition budget tracking and budget review meeting at the MDA level & LGAs | Identify and engage a consultant to Conduct annual nutrition budget tracking and budget review meeting at the 10 MDA level & 11 LGAs | 1 | 2 | 10 MDA level & 11 LGAs | M0EP |  |  |  | 1 | consultancy fees @60,000 x25 days for 2 consultant | 3000000 | number of MDAs and LGAs whose annual nutrition budget was tracked | activity report, attendance and pictures
| Sub total | [10 empty] | 3000000
7 | Conduct annual dissemination of state nutritional status and indicators to lawmaker, executive and key stakeholders | 1 | 35 | 10 law makers, excutive 10, 10 members SCN | M0EP |  |  | 1 |  |  | hall@10000x1,matrial@500x30,lunch and tea break 2500x35x1,per dem @ 10000x3 days, accomodation x13500*2, 2000 communication, transport @5000x35x2 | 2632500 | number of disemmination meeting s held | activity report, attendance and pictures
| Sub total | [10 empty] | 2632500
| Grand total | [10 empty] | 8464500