## Sheet1
ABIA STATE COMMITTEE ON FOOD AND NUTRITION (ABSCFN) WORKPLAN FOR 2021
S/N | IDENTIFIED PROBLEMS | CAUSES | SOLUTION PROPOSED | OBJECTIVE OF PROPOSED SOLUTION | ACTIVITIES FOR ACHIEVING OBJ. | STRATEGIES ADOPTED | TIME LINE | COLLABORATING ORGANIZATION | INDICATORS | EXPECTED OUTCOME | TARGET | REQUIRED RESOURCES | BUDGET
a. | Poor breastfeeding practices | (1) Late initiation of Breastfeeding. 2. Low level of compliance to exclusive breastfeeding for first 6 months. 3. Low level of sustained breastfeeding for 2 years among care givers | HEALTH SECTOR:- (1) Build capacity of the health workers and care givers for effective promotion and adoption of adequate breastfeeding practices. 2. Expand the number and activities of the IYCF Support groups in the 291 wards by 5. | 1. To build the capacity of the health workers to effectively promote adequate BF practices. 2. To build capacity of Care givers to adopt , practice and sustain adequate BF practices 3. To promote child growth monitoring at household and health facility | 1).Training of 266 health workers from 133 health facilities in 3 LGAs (Obingwa, Bende and Ikwuano) on Optimal Breast Feeding practices. | Routine PHC service outlets e.g. ANC, Postnatal/RI Clinics. 2). Community meetings (Men & Women) 3). FBO meetings. | January - August, 2021 | SMOH/ABPHCDA, FMC, ABSUTH, FBOs, etc. | Percentage of Care givers adopting appropriate BF practices | 5% increase in the current EBF rate in Abia. | Health workers and Care givers | Personel, Posters/Fliers; Counseling Cards; Take Home Brochures | #3,827,600
[5 empty] | 2). Sensitization of the 53 WDCs in the 53 Wards OF Obingwa, Bende and Ikwuano LGAs, for support to strengthen/create IYCF Support Groups in each wards. | Community meetings | FEBRUARY - SEPT. 2021 | SMOH/ABPHCDA, FMC, ABSUTH, FBOs, etc. | Number of functional WDCs; Percentage of Care givers adopting appropriate BF practices | 5% increase in the current EBF rate in Abia. | Community Men and Women groups; Community Gate Keepers; | Personel, Posters/Fliers; Counseling Cards; Take Home Brochures; Note books. | #1,085,200.00
[5 empty] | 3). Training of 133 Health workers from 133 Primary Health Facilities in 3 LGAs on the use and interpretation of growth charts and traditional beads for growth monitoring. | Routine PHC service outlets e.g. ANC, Postnatal/RI Clinics. 2). Community meetings (Men & Women) 3). FBO meetings. | October - Dec. 2021 | SMOH/ABPHCDA, FMC, ABSUTH, FBOs, etc. | Percentage of Care givers that routinely monitor the growth of their children every month. | 5% increase in the current EBF rate in Abia. | Health workers and Care givers | Personel, Posters/Fliers; Counseling Cards; Take Home Brochures; Weighing scales; Child Growth Charts | #1,177,200.00
b. | Poor complementary feeding practices | Early introduction of Complementary Foods. 2). Use of inadequate CF (quality and quantity). 3). Poor adherence to Food Safety and Hygiene practices | Build capacity of HWs and Care givers on adequate complementary feeding practices | 1). To build capacity of HWs on adequate CF. 2). To build capacity of Care givers to prepare and use adequate CF from locally available food items. 3). To promote and improve the skill of Care givers on hand washing, Safe food handling and preservation | 3 day Training of 133 Primary health workers on CF. / Food demonstration for Care givers. | Routine PHC service outlets e.g. ANC, Postnatal/RI Clinics. 2). Community meetings (Men & Women) 3). FBO meetings. | APRIL - SEPT. 2021 | SMOH/ABPHCDA, FMC, ABSUTH, FBOs, etc. | (1) Prevalence of stunting, Wasting, Under and Over weight among U - 5 children. 2). Prevalence of diarrhoea among U - 5 children | 5% increase in the base (2018 SMART Survey | Health workers and Care givers | Personel, Posters/Fliers; Counseling Cards; Take Home Brochures, Food demonstration materials | #1,300,000.00
| Poor breastfeeding practices | (1) Late initiation of Breastfeeding. 2. Low level of compliance to exclusive breastfeeding for first 6 months. 3. Low level of sustained breastfeeding for 2 years among care givers | EDUCATION SECTOR:- (1) Promote behavioural change towards adoption of appropriate breastfeeding practices early in life among adolescent and women of reproductive age (WRA). | (1) To increase the knowledge of adolescents and young women on the benefits of exclusive breastfeeding and the effects of complementary feeding on growth and development of young children. (2) To build a positive attutude among adolescents and young women towards adopting appropriate Breastfeeding practices (early initiation of breastfeeding; exclusive breastfeeding for 6 months and sustained breastfeeding for 2 years) and adequate CF practices, food safety and hygiene. 3).To build skills and confidence of adolescent girls and young women on appropriate breastfeeding techniques and overcoming challenges and to prepare adequate CF using locally available food items. | (1) Baseline Evaluation of knowledge and attitude of the students on Food and Nutrition subject content. | Integrate teaching of appropriate breastfeeding and complementary feeding practices into Food and nutrition subject in Senior Secondary schools | Jan - Dec 2021 | MOE, ASUBEB, MOI, ABSPHCDA, MOUAU,NSN | (1) Percentage increase in the knowledge of EXB and CBF (2) Percentage increase in the attitude and perception scales (3) Percentage increase in demonstrated skill and confidence | 5% increase in the current EBF rate in Abia. | Adolescents; (Male and female secondary school students) & Young women | Resource persons posters/fliers demonstration kits | 1M
| Poor complementary feeding practices | Early introduction of Complementary Foods. 2). Use of inadequate CF (quality and quantity). 3). Poor adherence to Food Safety and Hygiene practices | Promote behavioural change towards adoption of appropriate complementary feeding practices early in life among adolescent and women of reproductive age (WRA). |  | 2). One day stakeholders meeting to review proposed strategies. | Integrate the activities into: (1) Home Economics/ Food and Nutrition class in secondary schools. (2). Vocational classes in Skill acquisition centres. (3). Radio programmes | Jan - Dec 2021 | MOE, ASUBEB, MOI, ABSPHCDA, MOUAU,NSN | (1) Percentage increase in the knowledge of CF, food safety and hygiene. 2).Percentage increase in the attitude and perception scales. 3). Percentage increase in demonstrated skills on preparation of CF, food safety and hygiene. | 5% decrease in the prevalence of stunting, wasting and underweight and diarrhoea among U5 children. | Adolescents; Young women | Resource persons posters/fliers demonstration kits | 1M
|  | Early introduction of Complementary Foods. 2). Use of inadequate CF (quality and quantity). 3). Poor adherence to Food Safety and Hygiene practices |  |  | 3). Development of content and teaching materials for infant and young child feeding practices
4). One day stakeholders meeting to review proposed content and teaching materials.
5). One day (one day / senetorial zone) zonal training of teachers on the approved content and teaching materials.
6). Conduct Visits to ….. Secondary Schools (by 20 Monitors) for Monitoring and Evaluation.
|  | (1) Late initiation of Breastfeeding. 2. Low level of compliance to exclusive breastfeeding for first 6 months. 3. Low level of sustained breastfeeding for 2 years among care givers. 4). Consumption of nutritionally inadequate meals. 5). Poverty | AGRIC SECTOR:- 1. Capacity building for the Extention workers and Women of child bearing age 2. Encourage women to get involved in income generating ventures (e. g. processing / marketing of Agric products); 3. Formation of cooperatives to access credit facilities | 1. To build the capacity of Extension workers to effectively promote ebf and appropriate CF among their clients. 2. To promote healthy eating habit among women | 1. Conduct a 5 day Training of 30 Agric Extension workers (10/zone) on appropriate Infant and Young Child Feeding practices. | Forthnightly meetings with women of child bearing age. 2. Monthly meetings with communities (men and women) | Jan - Dec 2021 | MOA and ADP | Percentage of women adopting BF practices | 5% increase in the current EBF rate in Abia | Extension workers and women of child bearing age. | Personel, posters/training materials | 350000
| Poor complementary feeding practices | Early introduction of Complementary Foods. 2). Use of inadequate CF (quality and quantity). 3). Poor adherence to Food Safety and Hygiene practices | Build capacity of HWs/Mother of child bearing age on processing/preparation of adequate complementary food from local foods (Afican Yam bean; plantain, soy-bean, maize, groundnuts, etc. | To promote the processing/preparation of CF with local foods with HWs/women of child bearing age | 2).3 day Training of 60 women from 3 Agric zones of Abia on income generating ventures and processing / preparation of adequate CF with local foods. | Forthnightly training with HWs | Jan - Dec 2021 | MOA and ADP | 1. Prevelence of stunting, wasting, under and over weight among U - 5 children. 2. Prevalence of diarrhorea among U-5 children | 5% increase in the base (2018 SMART survey | Extension workers and HWs | Personel, flow chart chart of processing of plantain, soy-bean, maize, groundnut (materials for processing of plantain, soy-bean etc | 500000
| 1. Poor breastfeeding practices 2. Poor complementary feeding practices | (1) Late initiation of Breastfeeding. 2. Low level of compliance to exclusive breastfeeding for first 6 months. 3. Low level of sustained breastfeeding for 2 years among care givers 4. Early introduction of Complementary Foods. 5). Use of inadequate CF (quality and quantity). 6). Poor adherence to Food Safety and Hygiene practices | ADVOCACY & COORDINATION:- Organize sensitization meetings on Breastfeeding and CF for various women groups in the communities. 2). Enact laws that promote Ebf and CF e.g. 6 months maternity leave for nursing mothers; Paternity leave for fathers; Establishment of Creche in MDAs, etc. by Abia State House of Assembly. | To sensitize the community women groups on appropriate Breastfeeding and Complemntary feeding practices. 2). To promote adoption of appropriate Infant and Young Child Feeding practices among the community women | 1). Production of Advocacy tools and IEC materials on Ebf and CF. 2). Advocacy Visits to the Community Gate keepers to sensitize them on appropriate Breastfeeding and CF practices. 3).Conduct sensitization meetings with various community men and women groups onappropriate feeding practices for infants and young children in the communities. 4). Production and airing of Jingles and Talkshows on Ebf and CF. 5). Advocacy visits to relevant Stakeholders at the State and LGAs. 6). Advocacy visits to Abia House of Assembly. | Advocacy visits; Town Hall meetings; Community Dialogue; Radio Programs | Jan - Dec 2021 | ABSCFN & all corncerned MDAs | 1). Increased support for Ebf and appropriate CF practices from relevant Stake holders at the State, LGAs and Communities. 2). Increase in number of women adopting exclusive breasfeeding and appropriate CF practices. | 5% increase in the current EBF rate in Abia | Community Men and Women groups; Community Gate Keepers; Policy Makers at both state and LGAs | Personnel; Funds | 2.260 million
| Poor breastfeeding practices | (1) Late initiation of Breastfeeding. 2. Low level of compliance to exclusive breastfeeding for first 6 months. 3. Low level of sustained breastfeeding for 2 years among care givers | MINISTRY OF INFORMATION & STRATEGY: 1). Organize sensitization meetings on breastfeeding and Complementary Feeding for various women groups in the communities. 2). Organize advocacy visits toMedia Organisations to acquaint them on the need for exclusive breastfeeding and adequate complementary feeding practices. 3). Enact laws that promote exclusive breastfeeding and complementary feeding e.g. 6 months maternity leave for nursing mothers, paternity leave for fathers; establishment of creches in MDAs, etc by Abia state House of Assembly | 1). To sensitize the community women groups on appropriate breastfeeding and Complementary feeding practices. 2). To promote adoption of appropriate infant and young child feeding practices among the Community women. 3). To increase level of awareness among the women on the benefits exclusive breastfeeding and appropriate complementary foods through the mass media. | 1. Advocacy and Sensitization visits to 7 Media Houses - BCA, Radio Nigeria, Vision Africa Radio, Love FM,Umuahia,Magic FM Aba, MCL TV Aba and selected 2 communities in each of the 3 selected LGAs. | Radio programmes and dramas; Press conference; Community Dialogue; Town hall meetings and Advocacy visits. | June - November, 2021 | ABSCFN, NUJ, AND ALL CORNCERNED MDAs | Increased support for Exclusive breastfeedin g and appropriate CF practices from relevant stakeholders in the state, LGAs and communities. 2. Increase in number of women adopting exclusive breastfeeding and appropriate CF practices. 3. Increase in media reports on Ebf and CF practices. | 5% increase in the current EBF rate in Abia. | Community Men and Women groups; Community Gate Keepers; Policy Makers at both state and LGAs, Media Managers. | Personnel; Funds | #220,000.00
|  |  |  | To create awareness on the importance of EBF, cf practices for infants and young children and the implication of non compliance | 2). Production and airing of jingles in Igbo and English on Exclusive breastfeeding and Complementary feeding. | [7 empty] | #1,553,600.00
|  |  |  | To sensitize the women and care givers and give them opportunity to ask questions where necessary. | 3). Discussion program on TV & Radio | [7 empty] | Participation cost in the different Radio stattions for 30 minutes is #183, 460.00
|  |  |  | To create awareness on Exclusive Breastfeeding and Complementary feeding | 4). Production of Advocacy tools and IEC materials on Ebf & CF | [7 empty] | Production cost = #700,000
| Poor breastfeeding practices | (1) Late initiation of Breastfeeding. 2. Low level of compliance to exclusive breastfeeding for first 6 months. 3. Low level of sustained breastfeeding for 2 years among care givers | CHILD PROTECTION - MINISTRY OF WOMEN AFFAIRS: Awareness creation/ Sensitization. 1. This is to ensure comprehensive and curative formula to facilitate and promote knowledge on nutritional values. 2. Building and expanding capacity of students, in particular the girls through sensitizing them in programmes organized by Ministry of Women Affairs and Social Development. |  |  |  | June - November, 2021 |  |  | Education through sensitization and awarenes creation among family tiers, community leaders and FBOs | Students families and communities. | Personnel, posters, fliers and invitation letters. Care-givers women leader and secondary school students (girls). | 3961500
| GENERAL |  | GENERAL | GENERAL
|  |  | Quarterly meeting of Abia State Committee on Food and Nutrition (ABSCFN) | To organize Quarterly meetings of Abia State Committee on Food and Nutrition (ABSCFN) | ABSCFN Quarterly meetings | In House meeting for the nABSCFN committee members every quarter | 2nd Tuesday of the last month in a quarter | ABSCFN | Number of meetings held | 4 meetings held | ABSCFN members | Papers, Pens, Flip Chart stand and Flip Chart papers | N616,000,00
|  |  | Quarterly technical review of Nutrition activities across the 17 LGAs of Abia. (Participants = 17 LGA Nutrition Officers, 15 Officers in the State Nutrition Unit,and 25 ABSCFN Members) | To conduct Quarterly technical review of Nutrition activities across the 17 LGAs of Abia. | Quarterly technical review nof Nutrition activities in all the 17 LGAs | Work Review and Capacity building | 3rd Thursday of the last month in a quarter | ABSCFN | Number of quarterly technical review meetings held / year | 4 meetings held | LGA Nutrition officers | Projector, Papers, Pens, Flip Chart stand and Flip Chart papers | N748.000.00
|  |  | Domestication of the National Policy on Food and Nutrition as Abia state Policy on Food and Nutrition | 1. To review the National Policy on Food and Nutrition and adapt it to Abia state . 2. To produce A Food and Nutrition Policy for Abia state. 3. To develop a strategic Plan of Action for Nutrition n Abia | 1. Engagement of a consultant to review the National Policy on Food and Nutrition | In dept book review on the NPFN by the Consultant | January - July, 2020 | ABSCFN | Number of Consultants engaged | NPFN Reviewed |  | Copies (Electronic and Hard copies) of the NPFN | N700,000.00
[5 empty] | 2. Meeting of a sub committee of ABSCFN (Sector Heads)to review the NationPolicy and domesticate the policy | A 4 day residential meeeting for a 12 man subcommittee of ABSCFN to work on the Policy and Strategic Plan of Action. | January - July, 2020 | ABSCFN | Participants attendance register; Report of the activity; Pictures | NPFN adopted in Abia | ABSCFN Sub committee | Projector, Papers, Pens, Flip Chart stand and Flip Chart papers | N2,005,560.00
[5 empty] | 3. State wide presentation of the Abia state Policy on Food and Nutrition | State wide Book Launch / presentation of the Abia State Policy on Food and Nutrition and The Abia Strategic Plan of Action for Nutrition | January - July, 2020 | ABSCFN | Number of copies of Abia state Policy on Food and Nutrition produced abd disseminated | Availability of Abia State policy on Food and Nutrition | Abians | Projector, Papers, Pens, Flip Chart stand and Flip Chart papers | N810, 000.00
|  |  | Inauguration of LGA Committee on Food and Nutrition (LGCFN) in Abia State. | To establish and Inaugurate LGA Committee on Food and Nutrition (LGCFN) in the 17 LGAs of Abia State. | Conduct One day sensitzation meeting of ABSCFN with selected members of LGA Heads of different sectors (5/LGA) | Sensitization of selected LGA Heads of different sectors (5/LGA) on the need for LGCFN by ABSCFN |  | ABSCFN | Number of LGCFN inaugurated | All 17 LGCFN | LGA Stakeholders | Copies of the Abia FNProjector, Papers, Pens, Flip Chart stand and Flip Chart papers | N1,135,000.00
Note on F3: Ms. Ofoegbu: The 3 LGAs are Obingwa, Bende and Ikwuano with 51, 47 & 35 HFs respectively. Participants are the OICs & Assts.
Note on N3: Ms Ofoegbu: Training materials & photocopy for 266 @ #600 each = #159600; Snacks for 266 @ #400 each x 5 days = #532000; Lunch for 266 @ #1000 each x 5 days = #1330000; 2 Bottled water for each @ #100 x 5 days = #266,000;Transport for 266 participants @ #5000 each = #1330000. There will be 5 Facilitators each for 6 batches. Transport for 30 Facilitators @ #7000 each = #210000. TOTAL = #3,827,600.00
Note on F4: Mrs Oforegbu: Obingwa has 14 wards, Bende has 20 while Ikwuano has 19 wards (Total = 53 wards) and each ward has a Ward Devept. Committee with at least 10 members. Total number to be sensitized is 10x53 = 530
Note on N4: Ms. Ofoegbu: Snacks for 63 participants @ #400 each = #25,200; transport for 530 @ # 1000 each = = #530,000. Bus Hire for Facilitators @ #10000 x 53 wards = #2530,000. Total Budget = #1,085,200.00
Note on N5: Ms. Ofoegbu: Training materials and Photocopy for 133 @ #600 each = n#79800; Snacks and Drinks for 133 @ #400 each X 3 days = #159,600;; Lunch for 133 @ #1000 each x 3 days = #399,000.00 ; 2 Bottles of Water for 133 for 3 days =#79,800.; Transport for 133 @ #3000 each = #399,000; 4 Facilitators for each zone - Transport for 12 Facilitators @ #5000 each. = #60,000. Total = 1,177.200.00
Note on N6: Ms. Ofoegbu: Training materials and Photocopy for 133 @ #600 each = n#79800; Snacks and Drinks for 133 @ #400 each X 3 days = #159,600;; Lunch for 133 @ #1000 each x 3 days = #399,000.00 ; 2 Bottles of Water for 133 for 3 days =#79,800.; Transport for 133 @ #3000 each = #399,000; 4 Facilitators for each zone - Transport for 12 Facilitators @ #5000 each. = #60,000.; Purchase of Food demonstration materials, etc =#122,800. Total = #1,300, 000.00
Note on F11: Ms. Ofoegbu: One day / senetorial zone. 25 participants in each zone Total = 75 participants, and 7 Facilitators/zone
Note on N16: Mrs Oforegbu: Hiring of 14 seater bus to convey committee members to the media houses in 3 senetorial zones - Umuahia @ #50,000 x 2 = #100,000; Aba @ #60,000 x 2 = 120,000. Total = #220,000.00
Note on N17: Mrs Oforegbu: Production of Jingle in Igbo and English @ #20,000 each (b) Airing BCA for 3x in a month for 6 months @ #4000 x 12 x 6 = #288, 000; ii). Airing at Luv FM for 3x in a week for 6 months @ #3000 x 12 x 6 = #216,000; iii). Vision Africa for 3x in a week for 6 months @ #3500 x 12 x 6 = #252,000; iv). Pace Setter FM for 3x in a week for 6 months @ #3800 x 12 x 6 = #273,600; v). Magic FM for 3x in a week for 6 months @ #7000 x 12 x 6 = #504,000. Total = #1,553,600.00
Note on N20: Nmerechi: Training materials for 100 women at N300 each for 3 days i.e Bag envelop, pen and book. = 90,000. Tea break each day for 100 women at N500 =150000 Lunch for 100 women at N1,500 each = 390000. Training materials is for 150 students (girls) at N300 each. = 135000 Tea break at N500 each for 150 students for 3 days = 225000. Lunch for 150 students at N1,500 for 3 days = 675000. Transportation for 150 students at N5,000 at the final day. - 750000 Gift items for the girls such as sanitary pad at N1000 each X 150 = 150000. Transportation fare for the women at N8,000 each for 100 women = 800000. Resource persons, 3 persons per each day at N10,000 only for three days (9 persons). = 90000. Posters, fliers and flex at 156500. MISCELLANEOUS 1. Typing and dispatch of letters including transportation to the 3 Senatorial zones. = 200000 2. Transportation to the three Senatorial zones Abia North, Abia South and Abia Central = 150000.