**EDO STATE LOCAL GOVERNMENT COMMITTEE ON FOOD & NUTRITION 2021 WORK PLAN OF ACTION.**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **S/N.** | **ACTIVITIES.** | **OBJECTIVES.** | **STRATEGY.** | **TARGET POPULATION.** | **EXPECTED OUTCOME.** | **TIMELINE.** | **TOTAL BUDGET.** | **RESPONSIBLE.** | **PARTNERS.** |
| 1. | **Sensitization of adolescents Girls and young women of reproductive age (10-49years).** | Awareness creation on the importance of good nutrition as a panacea for malnutrition. | PHC FACILITIES,PHC workers, markets and schools. | Women of 10 years and above. | Increased knowledge of proper nutrition.  Malnutrition reduced amongst the populace. | January to December 2021. | To be determined by each LGCFN in the LGAs. | LGCFN, PHC workers, Agric officers, school teachers, SBMC/SUBEB/ LGEA. | EDSPHCDA, SMOH |
| 2. | **Infants and Young Children Feeding(IYCF). i.e Sensitization.** | To promote and support awareness on breastfeeding in the communities. | Collaborate with FBOs, PHC workers, Traditional rulers and women leaders in the community. | Nursing mothers and caregivers. | Increased practice of exclusive breastfeeding amongst nursing mothers and caregivers. | -do- | To be determined by each LGCFN in the LGAs. | LGCFN, PHC workers. | UNICEF. WHO, FBOs, EDSPHCDA |
| 3. | **Nutrition Education.** | To increase knowledge on importance of food and nutrition. | Visitation to public and private schools. | Pupils/ students in primary and secondary schools. | Adoption of positive nutritional practices by Pupils and students | -do- | To be determined by each LGCFN in the LGAs. | LGCFN, LGEA, AND SUBEB | SUBEB, ADP |
| 4 | **Distribution Of Vitamin A, Iron Supplements and Albendazole( Provision of logistic support and mobilization)** | To provide vitamin A supplements and Albendazole to. infants and young children between 6-59 months twice every year.  Iron supplements will reduce anaemia amongst adolescent | PHC facilities, PHC workers, markets and schools. | **VITAMIN A & ALBENDAZOLE**-infants and young children between 6-59 months.  **IRON SUPPLEMENTS**- 15-19 years women | To boost the immunity of infants and children against childhood diseases to prevent blindness. | -do- | To be determined by each LGCFN in the LGAs. | LGCFN, LGEA, AND SUBEB | UNICEF. WHO, EDSPHCDA, PHCs and SUBEB. |
| 5. | **Implementation of Maternal, New born and Child Health Week (MNCHW)- Logistics and Mobilization supports** | To provide Vitamin A and Iron supplements, albendazole and other Nutrition supplements to infants and young children between 6-59 months twice every year. . | 1.Visit to Public & Private secondary schools, homes, churches, mosques, community halls etc.  2.Awareness campaigns in communities.  . | Same as above | Same as above | May & November | To be determined by each LGCFN in the LGAs. | LGCFN, PHC Workers and Ministry of Education. | UNICEF, WHO, EDSPHCDA, WHO, UNICEF, PHCs |
| 6 | **World food day celebration**. | 1. Create awareness on food and nutrition, its production and challenges globally.  2.To achieve goal one of the SDGs. | 1. Awareness walk/Rally to sensitize the public on food, nutrition and other Agricultural issues.  2.Distribution of fliers and handbills.  3. Symposium | Farmers’ Association/ cooperative and food & Nutrition based companies. | 1. General public is sensitized on the role of agriculture in eradicating hunger, poverty and malnutrition.  2. The fact that agriculture is a profit oriented business is made known to the public. | October 16th, 2021. | To be determined by each LGCFN in the LGAs. | LGCFN, SCFN & MANR. | FAO, USAID & IFAD. |
| 7. | **Pre-season capacity building for farmers.** | To promote local food production and enhance its affordability. | Sensitization of the general public of the need for farming either at subsistence or commercial levels. | Farmers’ Association/ cooperatives. Men and women of 18 years and above. | Mass production of food that is available to all at affordable price. | February – April | To be determined by each LGCFN in the LGAs. | LGCFN. NOA, LGAs’ Dept. of In formation. | GIZ, IFAD, World Bank, ADP, MANR, |
| 8. | **Capacity building for Agric. officers and LGCFN members in the LGAs.** | To improve capacity to address food and nutrition security. | Organize a 2-day capacity building workshop for members of LGCFN. | LGCFN Members. | Local Government Committees on Food & Nutrition strengthened at the grass root level. | January – December, 2021 | To be determined by each LGCFN in the LGAs. | SCFN, MBEP, MLG&CA. | GIZ, IFAD, NDDC, World Bank, ADP, MANR. |
| 9. | **Sensitization campaigns on fish farming and vegetable gardens for all,** | Dietary diversification and nutrient fortification through consumption of fresh vegetables and fruits. | 1. Awareness walk/Rally to sensitize the public on the need fish farming and vegetable gardens by all.  2.Distribution of fliers & handbills.  3. Symposium | FBOs, Traditional rulers and women leaders in the community. | 1 Quick access to vegetables.  2. Access to delicious and balanced diet. | -do- | To be determined by each LGCFN in the LGAs. | LGCFN, ADP & FADAMA | LGAs, NDDC,ADP, MANR |
| 10. | **Quarterly coordination meetings** | To improve coordination of LGCFN activities in the LGAs | Quarterly meeting of LGCFN members | LGCFN members | Increased coordination of food and nutrition activities. | March, June, September & December. | To be determined by each LGCFN in the LGAs. | LGCFN | LGCs. |