## Sheet1
KATSINA STATE NUTRITION WORK PLAN 2021
|  |  | Sub Activity | Responsible Organization |  | 2020 | [10 empty] | Risk/Assumption
S/N | Intervention | Description of Core Activity |  |  |  | Indicator | Baseline Data | End of Year Target | Time Frame |  |  |  | Target | Unit | Total | Delivery
|  |  |  | Government | Partners/Donors |  |  |  | Q1 | Q2 | Q3 | Q4 | Population | Cost | Cost | Platform
1. Interventions focusing on Adolescent & Maternal Nutrition
1.1 | Iron folic supplementation for women | 1.1.1 Iron-folic acid supplementation | 1.1.1.1 Estimate and provide Iron-folate suplementation to pragnant mothers during ANC & MNCHW | SPHCDA | UNICEF | Number of women of reproductive age suplemented with iron folate during ANC & MNCHW | TBD | 10% increase of the 2020 coverage | 2.5% increase coverage | 2.5% increase coverage | 2.5% increase coverage | 2.5% increase coverage | 425330 |  |  | Health Facilities
1.2 | Promote women's nutritional status | 1.2.1 Food demostration to pregnant / lactating mothers | 1.2.1.1 Procurement of food items and ketchen utensils 1.2.1.2 Capacity building training on food demosration to nutritionist/dietitian | SPHCDA | NHED | 1) Number of sessions conducted per facility 2)Number of pregnant women and lactating mothers reached 3) Number of Nutritionist and dietitians trained
|  | 1.2.2 Dietry counselling during pregnancy and lactation | 1.2.2.2 1 Nutrition Counselling for pregnant and lactating mothers during ANC & PNC at facility | SPHCDA | UNICEF | Number of pregnant and lactating mothers councelled during ANC & PNC at facility
|  |  | 1.2.2.2 2 Nutrition Counselling for pregnant and lactating mothers during MNCHW at community | SPHCDA | UNICEF | Number of pregnant and lactating mothers councelled during MNCHW at community
|  |  | 1.2.2.2 Food demonstration for pregnant and lactating mothers | SPHCDA | UNICEF | Number of pregnant and lactating mothers trained on food demonstration.
|  | 1.2.3 Supplementary Maternal Nutrition Support Services | To be provided
1.3 | Promote Adolescent's Nutrition | 1.3.1 suplementation of iron and folic acid to adolescents | 1.3.1.1 Iron-folate suplementation to teenagers | SPHCDA | UNICEF | Number of adolescents given Iron folate after menses
1.4 | Capacity Building | 1.4.1 Develop the capacity of Health care providers for effective services delivery | 1.4.1 Train LGAs and facility nutrition officers on CMAM, IYCF, Zinc-lo ORS, iron folate | SPHCDA | UNICEF | Number of staff trained on CMAM,IYCF,Zinc lo- ORS, Iron folate
| Monitoring & Evaluation | 1.5.1 Develop M&E framework for effective data collection | 1.5.1.1 Develop and produce adequate checklist and data tools for ISS and data collection | SPHCDA | UNICEF | No. of data tools produced and shared
|  |  | 1.5.1.2 Undertake regular ISS visits to facilities | SPHCDA | UNICEF | No of ISS visits conducted
1.5 |  |  | 1.5.1.3 Conduct HMIS quarterly review for data officers | SPHCDA | UNICEF | No. of meetings conducted
Total: Interventions focusing on Maternal Nutrition
2. Interventions focusing on Infant and Young Child Feeding
| 2.1 Breastfeeding promotion, Protection and support, taking into account policies and recommendations of HIV and infant feeding | 2.1.1 Early initiation of breastfeeding within 30 minutes of delivery | 2.1.1.1 Encourage SBA to support lactating women to start breastfeeding within 30 minutes after delivery at the facility level | SPHCDA | UNICEF | Number of Lactating mothers that practice breastfeeding within 30 minutes of delivery | [9 empty] | Health Facilities
|  |  | 2.1.1.2 Health education to create awareness on early initiation of breastfeeding during ANC | SPHCDA | UNICEF | Number of Lactating mothers enlighten on early initiation of breastfeeding during ANC
|  | 2.1.2 EBF for six months and continue breastfeeding until two years of age and 12 months for HIV-exposed infants | 2.1.2.1 Conduct regular Health talk to create awareness on the importance of EBF for 6 moths until 2 years of age and 12 months for HIV-exposed infants | SPHCDA | UNICEF | Number of mothers enlighten of the relevance of EBF for 6 monthe untill 2 years of age and 12 months for HIV exposed infants
| 2.2 Complementary feeding promotion | 2.2.1 Behaviour change promotion to follow international best practices | 2.2.1 .1 Unddetake continues BCC to promote international best practices among SBAs | SPHCDA | UNICEF | No. of SBA that provides BCC to pregnant mothers
|  | 2.2.2 Provision of CIYCF Counselling | 2.2.2.1 Conduct FIYCF counselling in 72 OTP centers in 14 LGAs | SPHCDA | UNICEF | No. of mothers councelled at facility level on IYCF
|  |  | 2.2.2.2 Conduct CIYCF counselling in the targetted communities | SPHCDA | UNICEF | No. of mothers councelled at community level on IYCF
|  | 2.2.3 Demonstration of nutrient-dense complementary foods for children | 2.2.3.1 Demonstration to mothers on preparation of 'Garin Lafiya', 'Kunun Gyada' and other nutrient-dense foods to enhance nutritional diet among children under 2 | SPHCDA | UNICEF | No. of mothers trained on preparation of Garin Lafiya and Kunun Gyada | [9 empty] | Health Facilities
|  | 2.2.4 Counselling on Feeding of Sick Child | 2.2.4.1 Provide conseling to mothers on persistent method of feeding a sick child | SPHCDA | UNICEF | No. of Mothers councelled on persistent method of feeding a sick child
2.3 Capacity Building
| 2.4 Monitoring & Evaluation | Provision of data tools | 1.5.1.1 Develop and produce adequate checklist and data tools for ISS and data collection | SPHCDA | UNICEF | No. of checklist and data tools produced
|  |  | 1.5.1.2 Undertake regular ISS visits to facilities | SPHCDA | UNICEF | No. of Visits
|  |  | 1.5.1.3 Conduct HMIS quarterly review for data officers | SPHCDA | UNICEF | No. of quarterly review of data
Total: Interventions focusing on Infant and Young Child Feeding
3. Interventions focusing on Management of SAM
| 3.1 Prevention of SAM | 3.1.1 Screening of children 6-59 month | 3.1.1.1 Conduct sceening of 6-59 month children for SAM at community level | SPHCDA | UNICEF | Number of childrens screened 6-59 month.
| 3.2 Treatment of severe acute malnutrition | 3.2.1.identification of SAM and subsequent treatment (CMAM) | 3.2.1.1 Admit children with SAM cases in the OTP centers 3.2.1.2 Procurement of RUTF and routine drugs for the treatment of SAM | SPHCDA | UNICEF | 1. Number of childrens with SAM cases Admitted 2. Number of children cured 3. Quntity of RUTF and routine Drugs procured
|  | 3.2.2.Treatment of SAM with complications | 3.2.2.1 Admit children in stabilization centers. 3.2.2.2 Procurement of F100,F75 and Resomol. | SPHCDA | UNICEF | 1.Number of children Admitted 2. Qauntity of F75,F100 & Resomol procured 3. Number of children stabilized | [9 empty] | Health Facilities
| 3.3 Capacity Building | 3.3.1 Built the capacity of Health personnel for the management of SAM | 3.3.1.1 Train health workers and In-charges of the OTP sites on how to manage Sam cases 3.3.1.2 Train community volunteers on tracking SAM cases at community level | SPHCDA | UNICEF | 1.Number of health worker Trained 2. Number of CV trained
| 3.4 Monitoring & Evaluation | 3.4.1.Develop M&E framework for effective data collection of SAM cases | 3.4.1.1.Develop and produce adequate checklist and data tools for SAM data collection | SPHCDA | UNICEF | 1. Number of Data Tools developed 2. number of Data Tools Produced
Total: Interventions focusing on Management of SAM
4. Interventions focusing on Micronutrient Deficiency Control
| 4.1 Vitamin A supplementation | 4.1.1 Bi-annual doses of VAS for children U-5 | 4.1.1.1 Provide children with vitamine A 6-59 months during measles campaign and MNCHW | SPHCDA | UNICEF | 1. Number of Childrens supplimented 2. Number of measles campaign & MNCHW conducted | [9 empty] | Health Facilities
| 4.3 De-worming | 4.3.1 Two rounds of treatment per year | 4.3.1.1 Procure and distribute albendazole to facility for treatment of worm infestation | SPHCDA | UNICEF | 1. Number of Doses of Albendazole procured 2. Number of doses of Albedazole distributed 3. Number of childrens Dewormed 4. Number of Rounds conducted. | [9 empty] | Health Facilities
| 4.4.Zinc /Low ORS Supplementation | 4.4.1 Diarrhoea management | 4.3.1.1 Procure and distribute Zink Lo- ORS to facility level for treatment of diarrhoea 4.3.1.2 Capacity Building of Health Care Givers on Diarrhoea treatment with Zimc | SPHCDA | UNICEF NHED | 1. Number of Zinc and Lo-ORS Procured 2. Number of Zinc and Lo-ORS Distributed 3. Number of childrens with Diarrhoea treated with Zinc 1. Number of Health Care Givers trained | [9 empty] | Health Facilities
| 4.6 Monitoring & Evaluation | 4.6.1 Develop M&E framework for effective data collection | 4.6.1.1 Develop and produce adequate checklist and data tools for ISS and data collection | SPHCDA | UNICEF | 1. Number of Data Tools developed 2. number of Data Tools Produced
Total: Interventions focusing on Micronutrient Deficiency Control
5. Interventions focusing on DRNCD
| 5.1 Awareness of DRNCD | 5.1.1Identifying risk factors, providing education, and increasing services for DRNCD |  | SPHCDA | UNICEF | [10 empty] | Health Facilities/Community
5.2 Capacity Building
5.3 Monitoring & Evaluation
Total: Interventions focusing on DRNCD
6. Interventions focusing on Nutrition Information System and Programme Management
| 6.1 Nutrition Information System | 6.1.1 Monitoring & Supervision | 6.1.1.1 Conduct monitoring and supportive supervision for effective nutrition programme in the State 6.1.1.2 Conduct regular quarterly nutrition review meetings with all partners and stakeholders | SPHCDA | UNICEF | 1.Number of MSS conducted 2. Number of quarterly review meeting conducted | [9 empty] | Health Facilities
|  | 6.1.2 Data Managemnt | 6.1.2.1 Establish State nutrition data base | SPHCDA | NHED | 1. Number of Data base established
|  | 6.1.3 Advocacy/Resource/Release | 6.1.3.1 Conduct Advocacy to the State Policy makers on resources allocation and timely release for nutritional activities in the State. | SPHCDA | UNICEF | 1. Number of Advocacy visits conducted
|  | 6.1.4 Partnershiop & Coordination | 6.1.4.1 Established synergy between various stakeholders to enhance partnership and coordination through quarterly meetings | SPHCDA | UNICEF | 1. Number of Collaburation with stakeholders achived
| 6.2 Knowlegemnt Management | 6.2.1 Research
6.3 Capacity Building
6.4 Monitoring & Evaluation
Total: Interventions focusing on Nutrition Information System and Programme Management
7. Interventions focusing on Logistic Management and Supplies
| 7.1 Procurement of Nutrition Commodities, Supplies & Equipment |  | 7.1.1 Procure nutritional commodities to all CMAM and OTP sites in LGAs | SPHCDA | UNICEF | 1. Number of Nutritional commodity procured | [9 empty] | Health Facilities
| 7.2 Storage |  | Store all commodities at the state store | SPHCDA | UNICEF | 1. Number of commodities stored
| 7.3 Transportation |  | Transport commodities to LGAs | SPHCDA | UNICEF | 1. Number of commodities transported to LGAs
| 7.4Distribution |  | Distribute nutrition commodities to LGAs | SPHCDA | UNICEF | 1. Number of Nutrition commodities distributed to LGAs
7.5 Monitoring & Evaluation
Total: Interventions focusing on Logistic Management and Supplies
Grand Total
Note on J7: USER: