|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **S/NO** | **Activity** | **Expected output/outcome** | **Means of verification** | **Responsible Party** | **Time line** | **Estimated cost**  |
| 1 | Quarterly meetings of TSCFN | Enhanced institutional capacity and demonstrate strengthened commitment to scale-up quality nutrition services and interventions | Minutes of meetings and attendance sheets | Committee | March, June, September & December 2021 | **700,000.00** |
| 2 | Develop a Multi –Sectoral Nutrition plan | Produced a plan that guide the implementation of Nutrition in the State | Copies of State Multi-Sectoral Nutrition plan | Committee/MDAs | September 2021 | **2,000,000.00** |
| 3 | Support to media for airing TSCFN programme | Parents and care giver have improved knowledge and skills to adopt essential nutrition practices | Number of activities air | Committee/TSPHCDA | January – December 2021 | **500,000.00** |
| 4 | Emergency Response Fund for incidence of malnutrition outbreak | Emergency response provided to malnourished children  | Number of malnourished children supported | Committee | January- December 2021 | **1,000,000.00** |
| 5 | Domestication of the National Food and Nutrition Policy | Developed and implement food and nutrition policy in the State. | Copies of State Policy on Food and Nutrition | Committee | June 2021 | **1,500,000.00** |
| **TOTAL** | **5,700,000.00** |

**TARABA STATE COMMITTEE ON FOOD AND NUTRITION 2021 WORK PLAN**