## Slide 1
NG CARES
Brief – Need for Accelerated Implementation .

## Slide 2: NG-CARES: AN OVERVIEW
PROGRAM SUMMARY
An emergency program to support state-level efforts to respond to and recover from the COVID-induced socioeconomic crisis
Disbursements are RESULTS-based linked to DLIs in three RESULTS AREAS:
  Increased Social Transfers, Basic Services, and Livelihood Support to Poor and Vulnerable Households
  Increasing Food Security and Safe Functioning of Food Supply Chains
  Facilitating the Recovery and Enhancing Capabilities of Micro and small enterprises
PROGRAM COVERAGE AND VOLUME
All 36 states and FCT
USD 750 million CREDIT of which, USD 715 million ON-LENT to states under Program for Results and USD 15 million for federal TA, coordination and project implementation

## Slide 3: NG-CARES: PROCESS AND CURRENT STATUS
IMPLEMENTATION READINESS PROCESS and STATUS
Execution of SLAs and LEGAL OPINIONS by all states: DONE by DECEMBER 2021
Completion of all other REQUIRED steps for ELIGIBILITY
  ALL 36 states and FCT have completed the necessary steps and documents for eligibility and Disbursement clearance – Feb 2022
Completion of all other required steps for READINESS and receipt of DLI ADVANCES – First week of March 2022
  DLI advances ranging between NGN 500 million and NGN 1.3 billion, depending on the readiness SCORE\
  Total of N35.3 Billion disbursed to all States and FCT
  $122 million disbursed todate.
APPROVALS PROCESS & TIMELINE
IDA BOARD APPROVAL: December 14, 2020
FEC APPROVAL: April 14, 2021
NASS APPROVAL: April 21, 2021
SIGNING OF FINANCING AGREEMENT: June 3, 2021
DECLARATION OF EFFECTIVENESS: September 28, 2021

## Slide 4: Outstanding Actions Related to Effectiveness Condition
Engagement of Independent Verification Agent – Process ***
  TOR CLEARED and published
  EOI received and processed after long delay submitted to Bank
  Returned to IERD for Revision,
  Resubmitted on Tuesday March 5 2022.
  Ongoing Review By WB Procurement Team.
  IVA projected Engagement – June 15th 2022 ???
Legal Covenants (major)
    No later than ninety (90) days after the Effective Date, the Recipient shall recruit a professional firm to act as an Independent Verification Agency IVA, under terms of reference satisfactory to the Association ??????

## Slide 5: NG CARES – Emerging Issues
Federal and State Level
Federal Agencies are very active and providing advisory support to States and FCT in ensuring eligibility and disbursement of DLI advances.
States need to treat NG CARES Operation as “ Budget Support for Non-Discretionary Expenditure for Pro-Poor Services”
Clear delineation of roles and responsibilities among collaborating institutions at State and with Federal level is still needed in many States.
Funds flow arrangement, in many State is promising. There are a few States where the arrangement is more restrictive - Funds Flow Policy Document which is a PAP action, would be monitored.
State and FCT Budget funds release in 2021 was virtually nil in most State and limited prior results

## Slide 6: Major CONCERN and ASK – NG CARES
Less than 18 months to end of emergency Operation - Need for Accelerated Implementation.
  Increased Budget provisions in addition to the DLI advance to (a)ensure achievement of targets and even more and (b) earning all allocated $20 million dollar.
  Take advantage of the NG CARES provision to respond to the additional economic and social shocks in the system. – e.g the food security, food supply chain as well as support to informal sector.
  Strengthen capacity and motivate staff and delivery units in each state for achievement of set targets and more.
  Rapid procurement process for engagement of IVA.
  Finally - Please use NG CARES to create immediate and sustainable Shock Responsive mechanism at State level

## Slide 7: THANK YOU