## Slide 1
Enhancing Top Team Effectiveness of Health Leaders across Nigeria’s 36 States and the FCT
Presentation to State Health Commissioners
November 03, 2023

## Slide 2
Source: Team Analysis
Background
The Nigeria Governors Forum (NGF) Health Secretariat collaborated in late 2022 with the Nigeria Health Commissioners' Forum (NHCF) to enhance the effectiveness of state health leadership teams
This collaboration was deemed necessary to optimize the synergy among the state health MDAs towards achieving desired outcomes driven by their respective leaderships
The NGF engaged Solina Health to implement this project which aimed to understand challenges of the state health leadership teams, develop solutions, and kickstart these solutions to improve their effectiveness
This document describes the implementation progress thus far and the next steps to be taken

## Slide 3
  Diagnostics report
  Project Overview
Content
  Plan for follow up support
  Prayers

## Slide 4: The Top Team Effectiveness project set out to achieve 2 main objectives
Understand the barriers
Use known team effectiveness models to understand the current structural, political, interpersonal and contextual challenges affecting the effectiveness of the state health leadership teams
Co-create a framework for establishing and maintaining top team effectiveness
Develop potential solutions and kickstart the implementation of these solutions towards improving the effectiveness of the state health management teams
Co-create solutions
Objectives of the project
1
2
INTRODUCTION
We adapted the GRPI1 and Lencioni2 models for team development to assess the components of the effectiveness of the top leadership team
SOURCE: 1. The GRPI model – an approach for team development S Raue, SH Tang, C Welland 2013; 2. The Five Dysfunctions of a Team Patrick M. Lencioni 2007; Team analysis

## Slide 5: The project was designed to be implemented in four phases
Key Activities
Phases
Rapid Diagnostic
1
Solutions Co-Creation
2
Documentation and tracking
APPROACH
SOURCE: Solina team analysis
Outputs
Reviewed available academic literature
Developed interview guides and workshop tools
    Interviewed 3 - 4 health team managers per state and analyzed findings
Interview guides and workshop tools
Draft diagnostic report including key barriers to top team effectiveness
Conducted a solution co-creation workshop to:
Review the findings from the interviews
Identify potential root causes and solutions to the identified gaps
Align on the plan for the general retreat
A draft team effectiveness improvement toolkit
Finalized diagnostic report
Develop a simple tracker for the NHCF and continuously track the commitments from the retreat
    Conduct execution support to a few states for six months
    Update tool kit to include lessons learned from execution support
Final team effectiveness improvement toolkit
Commitment tracker
Project close out report
Conducted retreat with three representatives per state:
Introduced the participants to TTE
Developed plans for improving the TTE based on the diagnostic findings
State baseline assessment
State top team improvement plans
National communique
4
TTE Retreat
3
Key Activities
Details on next slide
xxx
The first three phases of the project have been concluded, while the documentation and tracking phase was put on hold due to the general elections and attendant changes in government across many states earlier in the year

## Slide 6: A three step methodology was used to obtain relevant output for the TTE implementation
APPROACH
SOURCE: Solina team analysis
Final diagnostic report
State-specific recommendations
TTE solutions toolkit
Commitment Tracker
Overall output
Rapid diagnostics
Solutions co-creation
TTE retreat
Who
How
4 HCHs
4 ES SPHCDA
3 ES SHIA
26 HCHs
33 ES SPHCDA
32 ES SHIA
12 other leaders
25 HCHs,
31 ES SPHCDA
31 ES SHIA
Held a day session with a select sample of state leaders to review the diagnostic findings, improve the insights, identify the probable root causes of all gaps and recommend potential solutions
Interviewed at least one health leader from all 36 states + FCT to understand their state’s current realities on the GRPI team effectiveness focus areas and determine their gaps
Conducted a 2-day retreat with leaders from 35 states1 to socialize the assessment findings and support each state to develop state-specific plans for improving team effectiveness
1. Rivers state had no representative at the retreat

## Slide 7
  Diagnostics report
  Project Overview
Content
  Plan for follow up meetings
  Prayers

## Slide 8: We summarized the findings from the diagnostics along 4 focus areas of the GRPI model
The majority of states reported clearly documented goals but there appeared to be a gap in having a shared understanding and application across states
Goals
Source: Team analysis
Roles
Roles are documented in most states but they were instances of varying interpretation which in some instances affected interactions. In some cases, suboptimal coordination and collaboration was attributed to this.
Overlapping roles existed in some states but could be helpful or harmful, depending mostly on interpersonal relationships of agency leaders.
Interpersonal relationship
Conflict resolution is mostly through informal processes and channels. Those states where top teams have cordial working and interpersonal relationships record minimal conflict and resolve them easily
Most states have not been able to conduct leadership retreats mostly due to unavailability of funds for the retreats
Respondents from some states provided discordant answers to processes in their states; suggesting gaps in communication and alignment between them.
Processes

## Slide 9: The state teams developed solutions around three domains to address their respective gaps during the co-creation workshop and retreat
SOURCE: KII with MDAs, Solina team analysis, Co-Creation workshop
Strengthen coordination and communication between the MDAs
1
Build capacity of top team to understand their roles and on relevant soft skills
2
Institute a mutual accountability system for monitoring, analyzing, and improving the performance among the health MDAs
3
There were specific solutions proffered for each state across the 3 domains
All the state teams at the retreat received a tailored intervention plan that contained their specific gaps, proffered solutions and state-specific intervention plans
These documents will be reshared with the commissioners
The NGF has developed a dashboard to track state’s progress with implementing the retreat output and intervention plans

## Slide 10: The team developed and shared tailored reports with each state team
SOURCE: KII with MDAs, Solina team analysis, Co-Creation workshop
To provide detailed findings from the diagnostic assessment of the state top health leadership team and the proposed solutions developed by some members of this team.
Objective
Expectations from the HCHs
Assessment methodology
State-specific findings
State improvement plan
State team MBTI learning
Expected use of the state report
Content
Cover page of a state’s report
Discuss the findings from the assessment and align on the immediate next steps.
Implement and track the interventions
Discuss other interventions not covered in this report and plan accordingly

## Slide 11
  Diagnostics report
  Project Overview
Content
  Plan for follow up support
  Prayers

## Slide 12: We developed a dashboard to guide the NGF and States’ commissioners in tracking the plans from the retreat workshop and visualize implementation progress
SOURCE: TTE dashboard
The NGF Health Secretariat will provide assistance to states experiencing difficulty in accessing and utilizing the dashboard
How to access the TTE Dashboard
The TTE dashboard can be accessed using the Microsoft Power Bi application at the following link
https://app.powerbi.com/view?r=eyJrIjoiY2UwZjNkNzYtYzg2OC00OTA5LWE4ZTQtN2FkMzVmYzlhNjQ5IiwidCI6ImNkMWMxYTAyLWUxNWUtNGE2NS1iNWJiLTllMjFhNWFmN2NlOSIsImMiOjl9
How to update the TTE Dashboard
The dashboard is updated using a Google sheet accessible to each state
https://docs.google.com/spreadsheets/d/1AeKASZ4-tgiqhK99RjwNdkJdo96x3Y4Vl8Ds9BbRXns/edit#gid=46133342
How frequently should the dashboard be updated
Monthly, to enable state’s track their implementation progress and course correct where applicable

## Slide 13: Anambra, Edo, Ekiti, Gombe, Kogi, and Zamfara state were selected for the implementation support
SOURCE: Solina team analysis, https://en.wikipedia.org/wiki/List_of_state_governors_of_Nigeria
6
States will be supported to implement their team effectiveness improvement plans
STATES’ SELECTION
States were selected using a 3-step analysis approach
RIVERS
FCT
ANAMBRA
ENUGU
AKWA IBOM
ADAMAWA
ABIA
BAUCHI
BAYELSA
BENUE
BORNO
CROSS RIVER
DELTA
EBONYI
EDO
EKITI
GOMBE
IMO
JIGAWA
KADUNA
KANO
KEBBI
KOGI
KWARA
LAGOS
NASARAWA
NIGER
OGUN
ONDO
OSUN
OYO
PLATEAU
SOKOTO
TARABA
YOBE
ZAMFARA
KATSINA
Geopolitical zoning
All 32 States were grouped into their geopolitical zones
Assessment
Scores were assigned to each state based on the level of their participation in the project and the probability of a continuity of government
Selection
The state with the highest score in each geopolitical zone was selected for the implementation support
1
2
3
The NGF will follow up with these states to schedule the implementation support visits

## Slide 14
  Diagnostics report
  Project Overview
Content
  Plan for follow up support
  Prayers

## Slide 15: Our prayers to the Commissioners
All states
SOURCE: Solina team analysis
Assign a focal person to routinely update the dashboard for your state
Identify an appropriate forum to leverage for routinely reviewing the progress and output of your state health team routinely
Provide dates for the visit to your state to commence implementation support
Call a meeting to review the state’s plan and discuss the approach to implementing the interventions
All states
Implementation support states
Review the dashboard during the NHCF meetings
Provide dates for the visit to your state to commence implementation support

## Slide 16: Backup

## Slide 17: We found that a majority of the states reported gaps in overlap of roles, clarity of reporting lines and existence of team engagement fora
SOURCE: KII with MDAs, Solina team analysis
No perceived gaps
Perceived gaps
Inadequate sample size
Trend in perceived status of the 36 states and the FCT
Goal
Role
Process
Inter-personal commun-ication
Focus
Metrics
Bauchi
Benue
Gombe
Kano
Rivers
Zamfara
Akwa-Ibom
Niger
Ogun
Delta
Kaduna
Lagos
Ebonyi
Yobe
Enugu
Imo
Katsina
Oyo
Jigawa
Nasarawa
Osun
Abia
Adamawa
Anambra
Bayelsa
Borno
Crossriver
Edo
Ekiti
Kebbi
Kogi
Kwara
Ondo
Plateau
FCT
Sokoto
Taraba
Documented vision & mission
Understanding of vision & mission
Aligned priorities
Clearly documented roles
Roles overlap
Documented processes
Clear reporting line
interagency coord. platform
Health leadership meetings/fora
Gaps were assessed as areas where there was no harmony in the response from all the respondents in a state
Many states reported roles overlap due to incursion in the duties of MDAs by other MDAs. While these incursions are sometimes minor and informally resolved, it could be a cause of major friction if there is no clear coordination by the HCH of activities performed by all MDAs
The gaps in existence of health leadership engagement forums were a result of undefined platforms for meeting, interaction and information sharing

## Slide 18: As many as ten states had respondents who could not describe the SMoH’s vision and mission
ASSESSMENT FINDINGS: GOALS
Some respondents from 8 states that previously mentioned that they have documented vision/mission statements could not provide an explanation of the vision
There were disparities in the responses from interviewees from 10 states. This disparity in the understanding of the vision and mission across the categories of respondents further suggests a possible communication gap between the SMoH and health agencies
Understanding of the SMoH’s vision and mission statement
Understanding of vision and mission statement by geopolitical zones (N = states)
Understanding of vision and mission statement by respondent role/agency (N = Respondents)
Chart: 
 | 14.1416 | 4 | 5 | 4 | 6 | 4 | 4
 | 10 | 3 | 2 | 2 | 2 | 1
5
2
NE
2
SS
NC
6
NW
1
SE
27
2
SW
Total
7
7
6
37
All can provide an explanation
Not all can provide an explanation
Chart: 
 | 25 | 27 | 26 | 9
 | 1 | 6 | 6 | 1
33
1
26
HCH
1
SPHCDA
4th person
10
SHIA
32
Can provide some explanation
Can provide no explanation
SOURCE: KII with MDAs, Solina team analysis, Analysis is based on perceived responses from state respondents

## Slide 19: Fourteen states had at least one respondent reporting the presence of overlap
ASSESSMENT FINDINGS: ROLES
The interviewees noted that a deficient understanding of agencies’ roles and responsibilities is the major reason for overlaps despite the operational guidelines and policies being appropriately documented
However, in some cases, respondents saw the overlap as complementary because they facilitated synergy and cross-learning within the health workforce. This is an opportunity that can be identified and utilized in all states
Overlaps in the delineation of roles across MDAs
Presence of overlap in roles by geopolitical zones (N = States)
Presence of overlap in roles by respondent’s roles (N = Respondents)
Chart: 
 | 9.5383 | 6 | 2 | 2 | 5 | 6 | 2
 | 14 | 1 | 5 | 4 | 1 | 0 | 3
7
NW
6
0
Total
NC
NE
7
SS
SW
SE
37
6
5
6
23
1
1
There is no role overlap
There is role overlap
Chart: 
 | 10 | 14 | 13 | 2
 | 8 | 3 | 7 | 3
 | 8 | 16 | 10 | 5
4th person
HCH
26
SPHCDA
SHIA
2
33
30
10
No role overlap
There is role overlap
Complementary role overlap
SOURCE: KII with MDAs, Solina team analysis, Analysis is based on perceived responses from state respondents
Complementary role overlap was recorded as no role overlap

## Slide 20: Only sixteen states confirmed that they report to/through the SMoH
ASSESSMENT FINDINGS: PROCESSES
The laws setting up the agencies in some states does not require them to report to/through the SMoH
It is recommended that a structured reporting line to/through the SMoH be considered across all agencies to improve collaboration in attaining the state’s health goals
Clear documented reporting structures between the MDAs and SMoH in the state
Reporting structures between MDAs and SMoH by geopolitical zones (N = States)
Reporting structures between MDAs and SMoH as reported by respondents (N = Respondents)
Chart: 
 | 10.55 | 4 | 2 | 4 | 2 | 2 | 2
 | 21 | 3 | 4 | 3 | 3 | 4 | 4
NE
6
37
SW
Total
NC
NW
SE
SS
7
7
5
6
6
16
2
2
2
2
All agencies report to/through the SMoH
Not all agencies report to/through the SMoH
Chart: 
 | 16 | 23.7303 | 18.7303 | 5
 | 7.7303 | 1 | 3 | 5
 | 7 | 7
 | 1 | 1
25
9
SPHCDA
HCH
1
1
25
1
3
20
SHIA
4th person
34
31
10
Through/To the HCH
Independent of the HCH
Unclear reporting structure
Not applicable
SOURCE: KII with MDAs, Solina team analysis, Analysis is based on perceived responses from state respondents

## Slide 21: Only fourteen states confirmed the conduct of leadership meetings or retreats to build the interpersonal relationships within the team
ASSESSMENT FINDINGS: INTER-PERSONAL RELATIONSHIP
Some interviewees mentioned the use of group features on social messaging platforms (e.g WhatsApp) and leveraging other partner-funded events to hold semiformal meetings
All states need to make deliberate efforts to hold semi-formal gathering to foster interpersonal relationship within the team . For instance, states can include retreats as part of their annual operation plan or leverage other state activities such as AOP development or other donor funded activities for their retreats
SOURCE: KII with MDAs, Solina team analysis, Analysis is based on perceived responses from state respondents
Existence of any semi-formal gathering to foster stronger interpersonal relationships within the team e.g. retreats
Existence of an informal engagement platform by geopolitical zones (N = States)
Existence of an informal engagement platform by respondents’ roles (N = Respondents)
Chart: 
 | 10.6142 | 3 | 1 | 3 | 1 | 3 | 3
 | 23 | 4 | 5 | 4 | 4 | 3 | 3
NE
1
1
NC
NW
SE
SS
SW
7
6
7
14
5
6
6
Total
37
All agree that the state has
Not all agree that the state has
Chart: 
 | 15 | 17 | 19 | 5
 | 11 | 15 | 9 | 3
 | 1 | 2 | 2
4th person
SHIA
HCH
1
SPHCDA
2
2
26
33
30
10
Yes
No
I don’t know

## Slide 22
Source: Team analysis
Each state will be supported to achieve four key objectives
Objectives
Proposed date
2
1
Details
Establish a shared understanding of the TTE support plan among the state’s top health team
Review the progress of the state’s improvement plan
Review the progress of the state’s improvement plan
Conclude the state support initiative
January 2024
Requirements
3
Communicate a convenient date for the meeting with the state’s top health team
Designate a state liaison preferably the Permanent Secretary or the MDA Head to facilitate communication with the support team
Focus
FOLLOW UP SUPPORT
The activities to be carried out in each state are not limited to the above and are subject to change depending on the specific need of each state
Support visits will be structured around the communicated timelines based on the State’s top health team availability

## Slide 23: Proposed 6-month support plan to selected states
SOURCE: Solina team analysis
Jan
Feb
Mar
Apr
May
Jun
Jul
Inform selected states for support and
secure their commitment for the planned activities
NGF
22/01/2024 - 26/01/2024
Learn of progress made by states in
implementing next steps from the retreat
Solina
Solina
Support the state to schedule and plan the second
and third visits (where necessary)
Solina
Continue virtual support for specific agreed activities
across the state
Key activities
Support the state to schedule and plan the first visit
Responsible
Support state to implement any pending retreat next step
Solina
Solina
19/02/2024 - 21/02/2024
26/02/2024 - 28/06/2024
29/01/2024 - 16/02/2024
07/07/2024 - 19/07/2024
15/01/2024 - 18/01/2024
1
2
4
3
5
6

## Slide 24: Solution Domain 1: Strengthen coordination and communication between the MDAs (1/2)
SOURCE: KII with MDAs, Solina team analysis, Co-Creation workshop, TTE retreat
Suboptimal coordination and communication between the SMoH and other health MDAs to ensure collective buy-in on the SMoH’s vision and mission
Set-up a system/platform comprising the HCH and all MDA heads to coordinate and ensure the alignment and buy-in of the health MDAs on the SMoH’s vision and mission
Set-up a system to develop/routinely review the vision and mission of the health system, and communicate state’s health priorities to all the MDAs
Challenges
Root Causes
Proposed Solutions
Difference in understanding of the vision and mission of the SMoH
a
Derailment of MDAs’ priorities from the state’s health priorities
Conflicting guidance from the national level and interference from development partners
  National and development partners sometimes bypass the SMoH and/or agency heads in their communication with agencies and/or program officers
Establish/leverage existing platforms to routinely discuss and align the SMoH’s and agencies’ priorities, including latest development from National and proposals from development partners
NHCF and NGF to help flag state concerns to the national bodies and emphasize the need to channel all communications to the MDAs, through the SMoH
b

## Slide 25: Solution Domain 1: Strengthen coordination and communication between the MDAs (2/2)
SOURCE: KII with MDAs, Solina team analysis, Co-Creation workshop, TTE retreat
Ambiguous statements in some MDA policies which indicate broad responsibility scope hereby leading to unclear roles between MDAs and potential misinterpretation
  In some instances, an MDA intentionally exploits these ambiguous policies to perform the roles due to delays in service delivery by the originally assigned MDA
Review existing laws/policies to clearly define roles for each MDAs and also correct any possible role overlaps between the MDAs and encourage systems strengthening
  NGF and NHCF to consider engaging FMoH to provide a framework/guide for the review of the MDAs’ policies
  Institute a system for joint problem solving led by the HCH to address challenges on encroachment of roles and create opportunities for synergy
Challenges
Root Causes
Proposed Solutions
Role overlaps across MDAs
c
Non-existence of routine retreats to foster interpersonal relationships within the team
No budget for retreat in state’s annual plan
Include retreats/similar semi-formal events in the ministry’s annual plan or budget
Leverage existing funded meetings/fora (e.g. AOP development/review workshops) for team retreats to foster stronger interpersonal relationships
d

## Slide 26: Solution Domain 2: Build capacity of top team to understand their roles and on relevant soft skills
SOURCE: KII with MDAs, Solina team analysis, Co-Creation workshop, TTE retreat
No clear system in place for the onboarding/orientation of new CEOs and other key personnel in health MDAs and no clear provision for continuous professional development of health leaders
Establish a system to adequately onboard all new CEOs and other key personnel in health MDAs on the State’s health vision and mission and priorities
NGF and NHCF to develop a standard onboarding pack for all MDAs
Onboarding process is to span across a feasible period of time
Develop and disseminate a well laid out job description to guide the operations of all MDAs across all levels (directors, etc.)
Develop a framework and curriculum for continuous training of old and new health CEOs situated at the office of the DPRS SMoH
Challenges
Root Causes
Proposed Solutions
Non alignment of the state’s health priorities with political leaders’ health manifesto
Suboptimal communication/advocacy of the health sector priorities by the health team to political leadership
Build the capacity of the health leaders to adequately engage the political leadership on the priorities of the state’s health sector
b
Insufficient understanding of the existing structures/
systems guiding the operations of the MDAs
a

## Slide 27: Solution Domain 3: Institute a mutual accountability system for improving the performance among the health MDAs
SOURCE: KII with MDAs, Solina team analysis, Co-Creation workshop, TTE retreat
Challenges
Root Causes
Proposed Solutions
Variable structures for reporting or engagement between health sector MDAs and the SMoH across states. For example;
  Use of parallel oversight and steering committees as accountability platforms for individual projects/programs
  Political affiliations which encourage direct informal engagement of health CEOs with political leadership
Set up a system to jointly develop annual state plans and review the priorities of the MDAs periodically
Ensure the SMoH is adequately represented in all project monitoring and supervisory teams/activities
Top health leaders are not aware of activities in other health MDAs and are thus unable to hold each other accountable

## Slide 28: Participants engaged in 5 key sessions to achieve the expected output
SOURCE: KII with MDAs, Solina team analysis, Co-Creation workshop
Session
Session Description
Output
Presentation of findings
1
An overview of the TTE assessment scope, methodology and the major findings across the country was presented to the participants
All participants had a shared understanding of the TTE diagnostic findings
Gallery walk and discussion
2
Proposed recommendations from the Solutions Co-Creation Workshop were displayed at different locations at the venue
Participants took turns in groups to visit the gallery stands which displayed the gaps, root causes, and solutions to the identified challenges across the GRPI team effectiveness model
They shared their thoughts on the identified gaps and provided suggestions on the proposed solutions
An updated list of gaps, root causes and solutions to the identified challenges across the GRPI team effectiveness model
Panel Session
3
Top leaders in the health space shared their experiences, challenges faced, and mitigation strategies adopted to resolve these challenges
Participants gained more knowledge on steps to take in addressing some of the challenges they face in their various fields
Personality assessment
4
Participants were introduced to the concept of personality types and how it can impact the functionality of a team
Each participant also took the Myers-Briggs Type Indicator (MBTI) personality test
Participants had a better understanding of how the personality of individuals can affect their team
Participants got their MBTI personality type
State findings review and intervention plan
5
Participants converge in their state groups to review and validate their states’ findings from the diagnostic
They also developed high-level implementation plans for each of the interventions they identified for resolving their challenges
Participants gained more knowledge on steps to take in addressing some of the challenges they face in their various fields

## Slide 29: 35 (95% of 37) states confirmed the existence of a documented vision and mission for the SMoH
ASSESSMENT FINDINGS: GOALS
In 2 states, the responses of the HCH differed from the agency head. This suggests a communication gap among the stakeholders or possibly, no shared understanding of the state’s vision of mission for health across the MDAs
Some states have gone further to disseminate their vision and mission on their websites and displaying them in their offices. Other states will benefit from this practice to increase team members’ consciousness of the state’s vision and mission
Existence of vision and mission statement
Existence of vision and mission statement by geopolitical zones (N = states)
Existence of vision and mission statement by respondent role/agency ( N = respondents)
Chart: 
 | 10.7806 | 6 | 7 | 5 | 6 | 6 | 5
 | 2 | 1 | 1
NE
1
NC
NW
SW
1
SE
SS
35
Total
7
6
37
All agree that they have
Not all agree that they have
Chart: 
 | 4.1274 | 9.1274 | 9.1274 | 1.5637
 | 1 | 1 | 1
 | 1
4th person
HCH
26
31
SPHCDA
31
9
SHIA
33
10
32
I don’t know
We have
We don’t have
SOURCE: KII with MDAs, Solina team analysis, Analysis is based on perceived responses from state respondents

## Slide 30: 32 (86% of 37) states agreed that the priorities of their SMoH and agencies were aligned
ASSESSMENT FINDINGS: GOALS
Non-alignment of priorities are largely due to poor coordination between the SMoH and the agencies
Respective states’ top health teams will benefit from holding routine joint coordination meetings to review their health goals. This will also ensure shared understanding of the goals, while improving respective MDA-level responsibility & alignment with these goals
Aligned priorities between the SMoH and the agencies
Alignment between priorities of SMoH and agencies by geopolitical zone (N = States)
Alignment between priorities of SMoH and agencies by respondent’s role (N = Respondents)
Chart: 
 | 12.0373 | 6 | 7 | 4 | 5 | 6 | 4
 | 5 | 1 | 2 | 1 | 1
1
1
NW
NC
Total
32
6
NE
1
SS
SW
SE
37
7
6
5
All agree that priorities align
Not all agree that priorities align
Chart: 
 | 26 | 32 | 28 | 9
 | 0 | 1 | 4 | 1
HCH
0
SPHCDA
4th person
SHIA
26
33
32
10
1
1
Priorities align
Priorities do not align/unclear
SOURCE: KII with MDAs, Solina team analysis, Analysis is based on perceived responses from state respondents

## Slide 31: 33 (89% of 37) states confirmed that the roles and organisational structure of the health MDAs are clearly documented
ASSESSMENT FINDINGS: ROLES
Most health MDAs have their roles and organisational structure clearly documented in their establishing laws and operational guidelines
All states will benefit from ensuring current and new team leaders are well briefed on the documented roles and organisational structure of their respective MDAs
Clearly documented roles and organisational structure
Clear documentation of roles and organisational structure of MDAs by geopolitical zone (N = States)
Clear documentation of roles and organisational structure of MDAs by role (N = Respondents)
Chart: 
 | 11.6143 | 7 | 6 | 6 | 5 | 5 | 4
 | 4 | 1 | 1 | 1 | 1
1
NE
1
NC
NW
SE
1
SS
1
SW
33
Total
7
37
5
6
6
All have
Not all have
Chart: 
 | 18.3896 | 27.3896 | 25.3896 | 9
 | 2 | 1 | 2 | 1
 | 1
4th person
SHIA
1
1
1
23
HCH
32
SPHCDA
30
26
33
32
10
No
Yes
Unclear
SOURCE: KII with MDAs, Solina team analysis, Analysis is based on perceived responses from state respondents

## Slide 32: 30 (81% of 37) states reported the existence of clear processes for all routine activities
ASSESSMENT FINDINGS: PROCESSES
States were assessed for all routine planning, budgeting, implementing and monitoring activities. These processes are documented in the operational guidelines in some states; and laws/policies setting up the MDAs in other states
There were disparities in the responses from the interviewees in 3 states on the availability of defined processes for all their state’s activities. This may indicate some capacity gap with the onboarding process of some CEOs who did not have previous context of the MDA laws
Clear processes for all routine activities
Existence of clear processes for all activities by geopolitical zones (N = States)
Existence of clear processes for all activities by respondents (N = Respondents
Chart: 
 | 12.8726 | 6 | 7 | 4 | 6 | 5 | 2
 | 7 | 1 | 2 | 1 | 3
NW
NC
Total
5
37
30
1
NE
SS
1
SW
SE
6
7
6
Clear processes for all routine activities
No clear processes for all routine activities
Chart: 
 | 17.97 | 23.97 | 24.97 | 9
 | 2 | 1 | 1 | 1
 | 2
2
HCH
26
2
24
1
1
30
33
SPHCDA
31
SHIA
1
4th person
32
10
Defined processes for all activities
Defined processes for some activities
No defined processes / unclear
SOURCE: KII with MDAs, Solina team analysis, Analysis is based on perceived responses from state respondents
Having defined processes for only some activities was recorded as a gap in the existence of clear processes for all activities

## Slide 33: 6 (16% of 37) states do not have a formal platform for convening top health teams
ASSESSMENT FINDINGS: INTER-PERSONAL RELATIONSHIP
Most inter-agency meetings are conducted monthly or quarterly with a clearly documented terms of reference for the participant, meeting agenda and action points
However, some respondents shared that the meetings have not been frequent due to conflicting priorities. In light of this, some states leverage informal platforms such as WhatsApp groups for ongoing conversations
SOURCE: KII with MDAs, Solina team analysis, Analysis is based on perceived responses from state respondents
Existence of a formal platform that brings together the heads of the health MDAs
Existence of a formal engagement platform by geopolitical zones (N = States)
Existence of a formal engagement platform by respondents’ roles (N = Respondents
Chart: 
 | 12.4568 | 7 | 6 | 3 | 5 | 6 | 4
 | 6 | 1 | 3 | 1 | 1
31
6
1
Total
NW
NC
NE
6
1
SS
7
SW
1
SE
37
5
All agree that they have
Not all agree that they have
Chart: 
 | 17.1415 | 21.1415 | 20.1415 | 10
 | 2 | 2
 | 1 | 1
HCH
1
30
1
SPHCDA
29
SHIA
4th person
26
33
32
Yes
No
I don’t know

## Slide 34: Incursion of roles was the most reported cause of conflicts, and most states have no defined process for resolving conflicts
ASSESMENT FINDINGS: MANAGING CONFLICTS
SOURCE: KII with MDAs, Solina team analysis, Analysis is based on perceived responses from state respondents
The state should institute an accountability framework that will facilitate responsibilities and synergy among health MDAs; heads
While leveraging existing inter-agency coordination and other funded platforms to bring the MDAs’ heads together, conflicting issues should be addressed with reference to established laws and policies
Based on the responses from the respondents, some of the causes of conflicts within and across health MDAs are
Chart: 
 | 52.17 | 19.57 | 19.57 | 8.7
Incursion of roles
External interference
Poor communication/misunderstanding
Funding issues
Approach or system for conflict resolution within and across health MDAs
Chart: 
 | 33.33 | 5.05 | 26.26 | 7.07 | 28.28
Unclear from responses
By HCH or MDA leads
Adhoc/informal arrangement
By conflict resolution committee
By top management committee