## Slide 1: SFTAS PROGRAMME UPDATE
Date: 25th August 2021
NIGERIA GOVERNORS’ FORUM (NGF)
STATES FISCAL TRANSPARENCY, ACCOUNTABILITY AND SUSTAINABILITY(SFTAS) TECHNICAL ASSISTANCE PROJECT
Presented by:
Olanrewaju Ajogbasile
Senior Programme Manager,
NGF HelpDesk & SFTAS TA
oajogbasile@ngf.org.ng
+2349083411461

## Slide 2: Good
STATES PERFORMANCE SUMMARY
States PERFORMANCE PRIOR ASSESSMENT
36 States published AFS FY 20 by 31st July 2021
36 States published BPR by 28th July 2021
32 States enacted improved audit laws by 31st July 2021
S/N | STATE | Eligibility Criteria 2021 APA (Part 1): Publication of Audited Financial Statement for FY2020 | DLI 10.3a: Audit Law Enactment | DLI 1.1: Publication of 2021 Q2 Budget Performance Report
1 | Abia |  |  | 
2 | Adamawa |  |  | 
3 | Akwa Ibom |  |  | 
4 | Anambra |  |  | 
5 | Bauchi |  |  | 
6 | Bayelsa |  |  | 
7 | Benue |  |  | 
8 | Borno |  |  | 
9 | Cross River |  |  | 
10 | Delta |  |  | 
11 | Ebonyi |  |  | 
12 | Edo |  |  | 
13 | Ekiti |  |  | 
14 | Enugu |  |  | 
15 | Gombe |  |  | 
16 | Imo |  |  | 
17 | Jigawa |  |  | 
18 | Kaduna |  |  | 
19 | Kano |  |  | 
20 | Katsina |  |  | 
21 | Kebbi |  |  | 
22 | Kogi |  |  | 
23 | Kwara |  |  | 
24 | Lagos |  |  | 
25 | Nasarawa |  |  | 
26 | Niger |  |  | 
27 | Ogun |  |  | 
28 | Ondo |  |  | 
29 | Osun |  |  | 
30 | Oyo |  |  | 
31 | Plateau |  |  | 
32 | Rivers |  |  | 
33 | Sokoto |  |  | 
34 | Taraba |  |  | 
35 | Yobe |  |  | 
36 | Zamfara |  |  | 
N.B: Disbursement Linked Results (DLRS) are subject to verification by the Independent Verification Agent (IVA) Office of the Auditor General of the Federation (OAuGF)

## Slide 3: SFTAS PROGRAMME UPDATE Upcoming Disbursement Linked indicators’ deadlines
EC/DLI | Eligibility Criteria/ Disbursement-linked results (DLRs) | DEADLINES | AUG | SEPT
DLI 7.2 | Quarterly State debt reports accepted by the DMO on average two months or less after the end of the quarter in 2021 | 31-Aug-21 | Part DLI | 
DLI 10.1 (2021) | Published online on an official State website by September 30, 2021, the Audited Financial Statements* of all local government authorities** within the State for fiscal year 2020***, which includes showing all allocations and actual receipts of state-local government joint account allocation committee (SLJAAC) transfers for each local government authority in the State | 30-Sep-21 |  | Part DLI
DLI 12.2 | INTERIM MILESTONE: No later than September 30, 2021, the Participating State must have awarded at least 20 more contracts to SMEs in the period after September 30, 2020, as compared to the period January 1, 2020 to September 30, 2020. Information on the contract award is to be published on the PPA or state official website or the eProcurement system of the state (if it exists). For each contract award publication, the minimum information on the contractor/supplier/service provider include the full name, the number of employees and the total assets in Naira | 30-Sep-21 |  | Part DLI
DLI 2.2 | Publish online Citizens’ accountability report based on audited financial statements/reports for FY2020, no later than September 2021. Citizen’s accountability reports are summarized and comprehensible versions of the audited financial statements and details of State government public consultations with citizens presenting the annual financial statements that are made available on the state official website(s) | 30-Sep-21 |  | Full DLI

## Slide 4: DLI 10.1 – FY 2020 Local Governments Audited Financial STATEMENTS
S/N | STATES | NGF TA
1 | Abia State | YES
2 | Adamawa State | YES
3 | Akwa Ibom | YES
4 | Anambra | YES
5 | Bauchi State | NO
6 | Bayelsa State | YES
7 | Benue State | NO
8 | Borno State | YES
9 | Cross River State | NO
10 | Delta State | NO
11 | Ebonyi State | NO
12 | Edo State | YES
13 | Ekiti State | YES
14 | Enugu State | YES
15 | Gombe State | YES
16 | Imo State | YES
17 | Jigawa State | YES
18 | Kaduna State | YES
19 | Kano State | NO
20 | Katsina State | NO
21 | Kebbi State | YES
22 | Kogi State | NO
23 | Kwara State | YES
24 | Lagos State | YES
25 | Nasarawa State | NO
26 | Niger State | YES
27 | Ogun State | YES
28 | Ondo | NO
29 | Osun | NO
30 | Oyo State | NO
31 | Plateau State | NO
32 | Rivers State | NO
33 | Sokoto State | NO
34 | Taraba State | NO
35 | Yobe State | NO
36 | Zamfara State | NO
DLI Deadline: 30th September 2021
TA Deadline: 31st August 2021
STATES’ ENGAGEMENT OF NGF TA SUPPORT (DLI 10.1)
ONLINE PUBLICATION
Edo, Ekiti and Kogi State have published and provided publication links.

## Slide 5
KEY UPDATES
FOR THE UPCOMING 2020 APA: NGF in collaboration with the FMFBNP, CBN, DMO and the World Bank has concluded the reconciliation exercise for State debt as at end of FY2020. This reconciled data was sent to all States on 9th August 2021 for feedback. It is important States send in their feedback by Friday 3rd September 2021 for consideration prior to final adoption. The reconciled data will be used to verify the debt-related DLIs for the 2020 APA.
  Only 13 States have responded - Abia, Adamawa, Bauchi, Benue, Cross River, Gombe, Kano, Kogi, Nasarawa, Niger, Ogun, Plateau and Zamfara State.
The Verification of NEW DLIs 10-13: the data request was sent to States via email on 12th July 2021 from the IVA. This will be a purely desk-based assessment i.e. no physical/on-site visits are required to the States. All States are advised to respond to the data request by email to the IVA Team Leader assigned to them, copying sftas@oaugf.ng & oadedokun@sftas.org.ng
  Benue, Taraba, Kwara, Kogi, Sokoto, Kebbi, Enugu, Ebonyi, Anambra, Gombe, Bauchi, Zamfara and Katsina State should please reach their assigned IVA team lead and the FMFBNP-PCU (oyindak@yahoo.com, +2348095360073) to address some verification queries and data request requiring immediate feedback.
THE VERIFICATION OF 5 New COVID-19 DLI Results with deadlines Dec 2020 to July 2021 has commenced
DLRs: 10.1 (2020), 10.2, 10.3, 11.2, and 13.2
A desk-based review FOR 36 States BY the IVA WITH enhanced review by the World Bank and PCU given the external firm is not yet on board
Program DLIs | UPDATED Verification and Disbursement Timeline | # Eligible States Receiving Grants | Grants per State USD Million
New COVID-19 DLIs Results Dec 2020 to July 2021 5 X DLRs 10.1 (2020), 10.2, 10.3, 11.2, 13.2 | To be verified and disbursed by Q4 2021. | 36 | Up to $7 million per State
Original DLIs 1-9 2020 Results (2020 APA) | To be verified and disbursed by end Q1 2022 | 36 | Up to $9-15 million per State

## Slide 6
THANK YOU

## Slide 7: CONTACTS
Programme Coordination Unit
Mr. Stephen Okon,
The SFTAS-National Program Coordinator,
Director Home Finance Department,
Federal Ministry of Finance, Budget and Planning
Central Business District, Abuja.
stephenokon117@yahoo.com
08065643949
Mr. Ali Mohammed,
The Deputy National Program Coordinator
ali4m1968@gmail.com
07033337112
Please copy enquires to:
Oyinda Adedokun,
Programme Manager
oadedokun@sftas.org.ng
08095360073
Office of the Auditor-General for the Federation as the IVA
Busayo Fawale
Programme Manager
fawale2002@gmail.com
08146505040
Please copy enquires to:
sftas@oaugf.ng
Nigeria Governors’ Forum
Olanrewaju Ajogbasile
Senior Programme Manager, NGF HelpDesk & SFTAS TA
oajogbasile@ngf.org.ng
+2349083411461
Please copy enquires to:
saffun@ngf.org.ng
Zabiola@ngf.org.ng
Debt Management Office
Oluwatosin Akomolafe,
SFTAS DMO
Akomolafe.tosin@yahoo.co.uk
08095918519
OGP
Mr. Andrew Onyeanakwe
Program Manager SFTAS OGP
Andrew.Onyeanakwe@ogpnigeria.gov.ng
08033138503