## Sheet1
Bauchi State Committee on Food and Nutrition (SCFN)
Detailed Implementation Workplan
Strategies | Activities | Results/Outputs | Duration | Responsible Departments/ Stakeholders
FY'21
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | NOV | DEC
Objective 1: Strengthen Nutrition Governance and Coordination at the State and LGA levels in Bauchi State
1.1 Provide statutory mechanisms for establishing(Nutrition Data Base in the State) the Secretariat of State Committee on Food and Nutrition in theMinistry of Budget and Economic Planning. | 1.1.1 Advocate for the provision of policy and frame work for establishing Secretariat of State Committee on Food and Nutrition in the Ministry of Budget and Economic Planning | Policy and frame work for SCFN secretariat established |  | SCFN
| 1.1.2 Purchase of 3 Unit of HP Laptop Computers,Photocopier Machine, Color Printer, Scaner, LG Projector/Screen, Flip Chart Board, Extention Wires, Internet Modem, Flash Drive, External Harddrive, GIS Machine, 2in one Steel Camera. | Adequate working equipment and materials provided
1.1.3 Purchase of A4 Papers, Color Printer Catrage, Giant Staples and Pins, Small Staples and Pins, Spiral Binding, Lamination Materials, Photocopier Toners, Hard Cover Exercise Books and File Trays.
1.2 Advocate for establishment of Local Government Committee on Food and Nutrition | 1.2.1 Advocacy kits, transportation,refreshment, inauguartion of committee and ToR draft
1.3 Strengthen multi-sectoral coordination mechanism for nutrition programmes, Monitoring and Evaluation. | 1.3.1 Quarterly State Food and Nutrition Committee (SFNC) meetings | Activities reviewed and recommendations for sectoral implementation improvement
1.4 Capacity building for Food and Nutrition Committee members at State, local government, and community levels on nutrition issues. | 1.4.1 Trainning of Food and Nutrition Committee members at State, local government, and community levels on nutrition issues.
1.5 Integrated Monitoring and Evaluation tools | 1.5.1 Develop M&E tools and conduct quarterly M&E of all CMAM and OTP sites in the State. | Effective implementation of activities ensured
Objective 2: Social protection
2.1 Promotion of male involvement in family health sevices and in food security and nutrition programs | 2.1.1 Community mobilization and education to promote male involvement in maternal and child health including nutrition programs | Number of Meetings conducted (link to health) |  | SPHCDA/ Min. for LG Affairs/ SCFN
2.2 Supporting and scaling up of community-based nutrition initiatives | 2.2.1 Initiate mother support groups for breastfeeding and complementary feeding | Number of mother support groups established(link to Nutrition-Agric) |  | SPHCDA
Objective 3: Health
3.1 Interventions focusing on Infant and Young Child Feeding | 3.1.1 Complementary feeding promotion |  |  | SPHCDA
3.1.2 Capacity Building
3.1.3 Monotiring and evaluation
3.2 . Interventions focusing on Management of SAM | 3.2.1 Prevention and management of moderate undernutrtion in children 0-23 months of age | Reduced rate of malnutrition
| 3.2.2 Treatment of severe acute malnutrition | Child morbidity and mortality rate reduced
3.2.3 Capacity Building
3.2.4 Monitoring and evaluation
3.3 . Interventions focusing on Micronutrient Deficiency Control | 3.3.1 Vitamin A supplementation | Child morbidity and mortality rate reduced
3.3.2 Multiple Micronutrient Powders
3.3.3 De-worming
3.3.4 Zinc /Low ORS Supplementation
3.3.5 Capacity building
3.3.6 Monitoring and evaluation
3.4 Interventions focusing on DRNCD | 3.4.2 Capacity building
3.4.3 Monitoring and evaluation
Objective 4: Education
4.1 Strengthen Nutrition Education in Schools | 4.1.1 Produce and distribute nutrition education teaching and learning materials in schools | # schools receiving nutrition education and learning materials |  | Ministry of Education/SUBEB
Objective 5:WASH
5.1 Hygiene Promotion in communities | 5.1.1 Production and distribution of IEC materials (bulk develoment) |  |  | SPHCDA/RUWASSA/SCFN
5.2 WASHCOM | 5.2.1 WASHCOM formatioin and training |  |  | RUWASSA

## Sheet2
No of Health facilities
S/NO | LGA | PHCs and General Hospitals | Visited and entered into ODK | Have security issues | Are hard to reach | Pending visits (next week)
1 | Alkaleri | 20 | 9 | 6 | 5
2 | Toro | 18 | 13 | 2 | 3
3 | Kirfi | 14 | 11 | 0 | 3
4 | Tafawa Balewa | 17 | 12 | 0 | 2 | 3
|  | 69 | 45 | 8 | 13 | 3