## Sheet3
CROSS RIVER STATE COMMITTEE ON FOOD AND NUTRTION ACTION PLAN FOR 2021
| STRATEGIC OBJECTIVE | ACTIVITY | PERFORMANCE MEASURES | EXPECTED RESULT | RESPONSIBLE PERSON | START DATE | END DATE | FREQUENCY | RESOURCES | COST (=N=)
1 | Strenthened political commitment and capacity at State and LGA level to mobilize resources for scaling up health and nutrition interventions | Advocacy and sensitization visits to CRSHOA, Commissioner for health, Comm. Aggriculture, and Comm. Budget and planning to support and fund nutrition programme | No of advocacies and sensitization visits conducted | Nutrition budget approved with funds released | SNO | March | April | 1 | Advocacy kit, transport, Projector, PAS | 800000
2 |  | 1 day orientation of new members on the roles and responsibilites of SCFN | Report and attendence sheet of training | SCFN functioning Effectively | SNO | May | May | 1 | Training materials, Tea/break and lunch, transport, PAS,Hall hire, Projector | 1500000
3 |  | Conduct 3 days meeting to review State action plan | State action plan available | Effective implementation of nutrition programme | SNO | June | june | 1 | DSA,Transport, PAS,Projector, stationery, hall hire lunch and snacks | 3500000
4 |  | Quarterly meeting of SCFN to review nutrition programme in the State | Meeting reports and attendence | Effective implementation of nutrition activities in the State | SNO | FEB | Dec | 3 | Stationary, Tea/break Lunch, projector, Transport, DSA | 2000000
5 |  | Conduct a 2 day Promotion, Sensitization and creation of awareness workshop to atleast 300 cassava farmers each across the three senatorial district in cross river to adopt provitamin A cassava stem in their farming system | Increase cultivation provitamin A Cassava | Improve nutritional status of Cross Riverians | Nutrition Officer, MOA | July | july | 1 | Stationary, Lunch,Projector, Transport, DSA | 10000000
6 |  | Conduct a 2 days training for 300 farmers on the cultivation of orange fleshed potato and its value chain | Increased cultivation of orange flash potato in the State | Improve health and nutrition of the populace | Nutrition Officer, MOA |  |  |  |  | 5000000
7 |  | Celebration of annual World Breatfeeding Week | Report, pictures, | Increase awareness on EBF and appropriate complimentary feeding nutrition | SNO | August | August | 1 | Media,flyers, T-shirts, transport refund, Vehicle hire for rally | 10000000
8 |  | In collaboration with Home Grown School Feeding programme conduct regular monitoring of 20 selected schools to ensure proper feeding of school childen | Report of schools monitored | Increased number of Healthy and well nourished children | SNO | JULY | Nov | 3 | Transport, DSA, snacks and lunch | 6000000
9 |  | Conduct nutrition education in 10 selected schools and setting nutrition clubs | Report of number of schools with nutrition clubs | Increase knowldge of nutrition among adolescent boys and girls | SNO | Mach | Nov | 1 | Transport, DSA, snacks and lunch | 3000000
10 |  | Establishment and equiping SIX centers for Community management of Acute malnutrition | Number of centers established and functional | % of children with SAM efficiently managed | SNO | Sept | Nov | 1 | Weighing scales, Heightometer, Therapeutic foods, drugs cups and spoons Transport DSA, | 12000000
11 |  | 1.Capacity building of subject matters specialist in the state committee of food and nutrition on any agricultural value chain (from production to finished goods) 2. Step down Training of the above for 300 Women and youth in the 3 senatorial district on any Agro Value Chain Development and processing | More involvement of women and youth involve in Agro Value Chain | 1. Increase in knowledge on value chain development 2. Increase in income generating activities leading to stability of Household in terms of food security | Nutrition Officer, MOA | Oct. | Dec. | 1 | DSA,Transport, Projector, stationery, hall hire lunch and snacks | 3000000
12 |  | world food day celebration | Report, pictures, | Increase awareness on Food security, Nutrition and Food safety | Nutrition Officer, MOA | Oct. | Oct. | 1 | Media,flyers, T-shirts, transport, Vehicle hire for rally, snacks, Inaugural Lecture fee | 2000000
|  | TOTAL | [7 empty] | 58800000