## SUMMARY
sa
KADUNA STATE 2021 MULTI-SECTOR NUTRITION ANNUAL OPERATIONAL PLAN (AOP) BUDGET
S/N | MDA | Total Budget (in NGN) | % of Total Budget | Main Sector | Remarks
1 | Ministry of Agriculture | 11906000 | 0.59637 | Agriculture | A total of 7 activities are planned with 5 expected to be implemented using Government funds while 2 are targeted for partner support. One of these activities will be implemented in Qrt.1; 2 in Qrt.2; 3 in Qrt.3 and 1 in Qrt.4. One of the activities will be jointly funded and executed in collaboration with KADA.
2 | Ministry of Education | 26395800 | 1.3222 | Education | A total of four key activities are planned to be implemented in FY2021 with government and partners expected to provide funding support for two each
3 | Ministry of Health | 20758700 | 1.0398 | Health | • A total of 11 activities are planned and all expected to be jointly funded through government and partner support. The partners whose support is anticipated include; Save the children, ANRiN, Lafiya project, and BMGF. • Two activities are planned to be conducted in the 1st Qrt of 2021 , 4 activities in 2nd quarter, 3 in 3rd quarter and the remaining 2 in the 4th Qrt.
4 | Ministry of Human Services and Social Develeopment (HSSD) | 21139700 | 1.0589 | Women Affairs and Social Development | No funding support identified for its planned activities for FY2021.
5 | Kaduna Agricultural Development Agency (KADA) | 10233530 | 0.51259 | Agriculture | • A total of 13 activities are planned with all expected to be implemented using Government funds with no partner support. • Five of these activities are earmarked to be conducted in Qrt.1; 6 in Qrt.2; and 1 each in Qrt.3 and Qrt.4. • One of the activities will be jointly carried out with the Ministry of Agric.
6 | Planning and Budget Commission | 31681528 | 1.5869 | Governance | • 21 activities were planned for 2021 • 8 of the activities will be supported by partners while 5 activities will be counterpart funded • Out of a total of N31,681,528 earmarked to fund its planned FY2021 activities, N11,821,690 will be funded by partners, N8,340,188 as counterpart while N11,519,650 will be funded solely by the state government.
7 | Kaduna State Primary Health Care Board (SPHCB) | 1291317999 | 64.6814 | Health | • SPHCB alone constitute 64.7% of the total FY2021 Multi-sector Nutrition Budget. • A total of 27 activities are planned out of which three were rolled over from 2020. These activities, especially provision of ready to use therapeutic food (RUTF) will be funded mainly using Government funds while some will be supported through the ANRiN project.
8 | Rural Water Supply and Sanitation Agency (RUWASSA) | 575555366 | 28.8293 | Public Infrastructure & Works | Of the 11 activities planned, one was newly introduced, three will be solely funded by the MDA's government funds while 8 are to be funded through joint partner and government counterpart funds.
9 | SEMA | 7439200 | 0.37263 | Governance (Emergency/Humanitarian) | • SEMA's work cuts across key MDAs of Health, education, infrastructure, agric, RUWASSA etc. • All of its 3 planned activities are targeted for partners funding.
|  | 1996427823 | 100 |  | One Billion, Nine Hundred and Ninety-Six Million, Four Hundred and Twenty-Seven Thousand, Eight Hundred and Twenty-Three Naira only is required to programme for Nutrition Interventions in Kaduna State for FY2021
____________________ THOMAS GYANG COMMISSIONER

## AGRIC
2021 AGRICULTURE ANNUAL OPERATIONAL PLAN FOR NUTRITION
AGRICULTURE ANNUAL OPERATIONAL PLAN FOR NUTRITION
TIME FRAME
CODE | ACTIVITIES | OUTPUT INDICATORS | RESPONSIBLE PERSON | Q1 | Q2 | Q3 | Q4 | COSTING ELEMENT | BUDGET | SOURCE OF FUNDS | REMARKS
1.1.6 1.1.9 | I. Purchase .Small ruminant animals for 40 women group (Rabbits male&female) ii. purchase 40 No.Starter packs | No. of Ruminants Purchased and distributed to beneficiaries | DD Live Stock/MOA | X |  |  |  | Male and Female Rabbits at 6,000 x40x2=480,000 40 No.feeding tray at 2500x40=100,000 N0.Water tray at 1500x40=60,000 supplementary feeds concentrates and multi vitamins at 15000 x40=600,000 Dewoming drugs and other essential drugs at 25,000 supplementary feeds concentrates and multi vitamins at 15000 x40=60,000 Logistics at 5000x20=100,000 | 1365000 | KADENAP
1.1.8 | iii. Conduct bi-annual Monitoring of home gardens | No.of monitoring visit conducted | DPM&E/MOA |  | X |  |  | Monitoring DTA @6000x4x2x20 CDx3 Fueling @ 20,000 x3days | 60000 | AGRA
1.1.11 | Purchase of 10,000 No.Jumbo fish for 20 women groups | No. of Jumbo fish purchased. | DD Fisheries/MOA |  |  | X |  | 10000 N0. of jumbo at 60/0ne=600,000.00 5 bags of 2mm at 13,000/one=65,000 5bags of 3mm at 13000=65,000 5bags of 4mm at 13,000/one=65,000 5 bags of 6-9mm at 13,000/bag=65,000 260,000x20=5,200,000 MEDICATION 4 N0 Aqua sterilizer at 2000/one=8,000x20=160,000 4 N0 Aqua syringe at 2000/one=8,000x20=160,000 4 N0.Aqua plus at 2000/one=8,000x20=160,000 CONTAINERS 20 Containesr at 30,000/one=600,000 DRYING EQUIPMENT 20 N0.fish smoking equipment at 100,000/one=20x100,00=2,000,000 | 7800000 | KADENAP | Women of child bearing age, to empower and improve their nutritional status (New activity)
1.1.11 | 1. Procure smoking kilns for x number clusters | No. smoking klins procured | DD Fisheries/MOA |  |  | X |  | 1. Smokimg Kilns Kilns@350000x6 | 2100000 | KADENAP
1.1.11 | 2. Distribute x number kiln to x number clusters | No. klins distributed to x number clusters | DD Fisheries/MOA |  |  | X |  | 2. Distribution of Kilns Fuel @15000x5 | 75000 | KADENAP
1.1.11 | 3.Training on Smoking Kilns | No. Treained on smoking kilns | DD Fisheries/MOA |  |  | X |  | 3. Training on smoking Kilns Refreshment @2000x90 Facilitator Transport 3000x2x10 Fuel@15000x10 Demonstration Materials Fish@5000x10 Species@1000x10 Briquette@2400x10 | 474000 | KADENAP | Women of child bearing age, to empower and improve their nutritional status
1.2.8 | 1. Conduct advocacy visit | Advocacy visit conduted | DD Produce |  | X |  |  | 1. Advocacy visit to agro base manufacturing companies Within the State Fueling @15000 DSA@3000x5 Driver@2000 | 32000 | AGRA
| TOTAL | [7 empty] | 11906000
| New Activities | 1
| Total number of finalised activities | 7
| Activities to be removed | 2
| Joint activities with KADA | 1
| Total no. of first quarter activities | 1
| Total no. of second quarter activities | 2
| Total no. of third quarter activities | 3
| Total no. of fourth quarter activities | 1
| How many are funded by partners | 2
| How many are solely funded by MDAs | 5
| Total Cost | 13767000

## MOE
KADUNA STATE COMMITTEE ON FOOD NUTRITION 2021 ANNUAL OPERATIONAL PLAN FOR EDUCATION
ACTIVITY CODE | ACTIVITIES | OUTPUT INDICATORS | TIME FRAME |  |  |  | COSTING | BUDGET | FUND SOURCE | RESPONSIBLE PERSONs | REMARKS
|  |  | Q1 | Q2 | Q3 | Q4
RESULT AREA 4: Improving Capacity to address Food and Nutrition Insecurity
STRATEGIC OBJECTIVE 4.1: Assessing, Analyzing and Monitoring Nutrition Situations
4.1.1. | Conduct on the job training for Teachers and Students on the Establishment/activation of School Gardens. a. Generate database of Agric and Home Economic Teachers across selected Public Schools of the State. b. Conduct a Planning meeting with relevant stakeholders on establishing / resuscitating of school gardens programme in 280 primary and secondary schools of the State | 1. Number of Agric & Home Economic Teachers in the State generated 2. Number of planning meetings held |  | X |  |  | Refreshment (Breakfast and Lunch) @ N2,000 x 10 | 20000 | MoE budget | MoE (D/EPPD) | i. The target number is 1,400 Schools in 5 years. For the first year 280 Schools are targetted. (96 Secondary and 184 Primary Schools) ie. 8 Secondary schools per zone and 8 Primary Schools per LGA ii. Activity would be conducted with SUBEB, KADENAP, KADA, MoA and RUWASSA
| c. Conduct a feasibility study of the schools where the gardens would be established or activated | 1. Feasibillity studies conducted 2. Number of schools identified | X |  |  |  | i. DTA for 9 officers @ N8,000 x 5 days ii. Fuelling @ N10,000 x 5 x 3 | 510000
| d. Conduct a 2-days training for Teachers on establishing/ activation of School Gardens - 560 Agric/Home Economic Teachers to be drawn from some selected Schools in the State. | 1. Number of Teachers trained 2. Number of schools covered for the training |  | X |  |  | i. Pay Resource persons @ 20,000 x 23 x 2 days ii. Lunch for 583 participants + facilitators @ N1,500 x 2 days iii. Tea break for 583 @ N800 x 2 days iv. Local transport for 560 participants @ N3,000 x 2 days v. Training and writting materials for 560 participants @ N500 vi. Public address system & projectors @ N10,000 x 12 clusters x 2 days vii. DTA @ N8,000 x 12 officers to monitor viii. Fuelling @ N10,000 x 12 | 7717800 |  |  | The plan aim to target 2 Teachers per School One training to be conducted every two years Funding of school garden captured in MoE budget
| e. Establishment/activation of 280 School gardens (Procure farming tools and seedlings) | 1. Number of School gardens established and activated |  | X | X |  | i. 2 Watering cans @ N2,000 x 280 ii. 10 Cutlasses @ N200 x 280 iii. 5 Hoes @ N500 x 280 iv. 2 Rakes @ N1000 x 280 v. 2kg Protein Maize @ N2,000 x 280 vi. 10g Water melon @ N1000 x 280 vii. 2kg Spinach @ N1,500 x 280 viii. 5 Fruit Trees @ N2500 x 280 ix. Logistics for Distribution, Manure, Labour assistance @ N20,000 x 280 | 13680000 |  |  | i. 280 school gardens to be established for this year
| f. Monitoring & evaluating of establishment/activation of school garden - 20 persons drawn from the relevant MDAs | 1. Number of M&E staff drawn from relevant MDAs (SUBEB, KADA, MoA, KADENAP) 2. Number of Schools awarded |  |  |  | X | i. DTA @ N8,000 for 23 Officers for M&E activities x 5 days ii. Fuelling for 23 Officers @ N5,000 x 5 days iii. Award best performing Schools @ N300,000 | 1795000
| Sub-total | [6 empty] | 23722800
RESULT AREA 2: Enhancing Caregiving capacity
STRATEGIC OBJECTIVE 2.1: Child survival, growth and development improved
2.1.1 | Build capacity on Food handling and Hygiene practices for Mother and Care-givers in Early Child Care Development Centres (ECCD) 1. Conduct ToT to 46 LGA Master trainers on ECCD at State level. 2. Print Nutrition promotion & key messages and disseminate to the Schools. | 1. Number of LGA Master trainers trained on food handling and hygiene practices 2. Number of Nutrition key messages printed and distributed |  |  | X |  | i. Tea break @ N800 x 50 ii. Lunch @ N1,500 x 50 iii.Transport @ N3,000 x 8 iv. DTA @ 4,000 x 38 x 2 v. Stationaries @ N500 x 46 vi. Facilitators fees @ N20,000 x 4 vii. DTA @ N8,000 x 2 officers to monitor vii. Print 800 copies of Nutrition key messages posters and disseminate @ N500 ix. Training materials @ N1,000 x 50 x. Hall @ N150,000 | 1162000 | ANRiN | MoE (D/EPPD) | i. A 2-day training to 46 master trainers (Teachers) of ECCD (2 master trainers per LGA x 23 LGAs) ii. Step down training to take place in 4th Quarter iii. Activity would be conducted with SUBEB and SPHCB, MoH (to facilitate the training)
| 3. Step Down the Training to Mothers and Caregivers on Health and Nutrition at each LGA | 1. Number of Mothers and Caregivers counselled/sensitized |  |  |  | X | Snacks, Training materials for demonstration, Transportation and facilitation fee | 1511000 | ANRiN
| Sub-total | [6 empty] | 2673000
| TOTAL | [6 empty] | 26395800

## SMOH
KDMSPAN CODE | ACTIVITY | OUTPUT INDICATORS | TIME FRAME |  |  |  | COSTING | BUDGET | FUND SOURCE | RESPONSIBLE PERSON | REMARKS
|  |  | Q1 | Q2 | Q3 | Q4
2.1.8 | Conduct 4 days meeting with 25 stakeholders to adapt the national policy on BFI in the state | Kaduna state BFI policy adapted and approved |  | * |  |  | Tea break=1500*27=40,500 Lunch =2500*27=140,400 Hall=10000*4 days=400,000 Accommodation=9000*27=243,000 Stationery=500*25=12,500 Transport Allowance=3000*25=75,000 DSA for resource persons=30,000*2=60,000 DSA for HW =3900*25=97,500 | 1,068,500 | SMOH and ANRIN Project/ Save the children,Lafiya project,BMGF | Nutrition Desk Officer MOH
2.1.8 | Assess BFI status across public PHC and secondary health facilities in the state | Number of health facilities assessment/status on BFI conducted |  | * | * | * | Transport Allowance=3000*15=45000 Printing of tools= 100,000 DSA for resource persons=30,000*15=450,000 | 595,000 | SMOH and ANRIN Project/ Save the children,Lafiya project,BMGF SMOH and ANRIN Project/ Save the children,Lafiya project,BMGF | Nutrition Desk Officer MOH
2.1.8 | Organize 2 days orientation workshop for medical directors /facility in charges on baby friendly initiative implementation | Number of health workers sensitized on baby friendly initiative |  |  | * |  | Tea break=1500*287*2 days=861,000 Lunch=2500*287*2days=1,435,000 Hall hire=100,000*2 days=200,000 Accommodation=9000*287*2days=5,166,000 Stationeries=500*287=143,000 DSA for participants=3900*287=1,119,000 DSA for MTs and resource person=30,000*2 persons *2 days=120,000 Facilitation fee=20,000*2 persons *2 days=80,000 | 9,124,300 | SMOH and ANRIN Project/ Save the children,Lafiya project,BMGF | Nutrition Desk officer SMOH
2.1.8 KDMSPAN | a) Mobilize stakeholders to conduct community sensitization on the importance of exclusive breastfeeding(EBF) during 2021 world breastfeeding week | Number of community sensitizations conducted on EBF |  |  | * |  | Transport Allowance= 3000*6=18,000 Refreshment= 1000*3* 150=450,000 DSA for Facilitators=30,000*6=180,000 | 648,000 | SMOH and ANRIN Project/ Save the children,Lafiya project,BMGF | SMOH nutrition desk officer
2.1.11 | b) Collaborate with RUWASA and Min. of Edu to conduct quarterly hand washing promotion at primary schools and community level | Number of schools and communities hand washing promotion conducted | * | * | * | * | Refreshment= 300*150=45,000 beneficiaries*4 quarters*6 schools /communities=1,080,000 DSA for Facilitators=30,000*24 persons=720,000 | 1800000 | SMOH, RUWASA,ANRIN project, save the children BMGF,Lafiya Project and UNICEF | SMOH & RUWASA nutrition desk officers
2.1.8 | c) Conduct 4 days meeting with 28 stakeholders to adapt the national strategy for the implementation of the national regulations on the marketing of infant and young children, food and other designated products / international code of marketing of breast milk substitutes | Kaduna state 5 years strategy for the regulations on the marketing of infant and young children, food and other designated products / international code of marketing of breast milk substitutes |  |  | * |  | Tea break=1500*30=45,000 Lunch =2500*30=156,000 Hall=10000*4=400,000 Accommodation=9000*30=270,000 Stationery=500*28=14,000 Transport Allowance=3000*28=84,000 DSA for resource persons=30,000*2 persons*4 days=240,000 DSA for HW =3900*28=109,200 | 1318200 | SMOH, ANRIN project, save the children, BMGF,Lafiya project and UNICEF | SMOH nutrition desk officer
4.6.3.a health sector 2021 AOP | Conduct behavioral change communication activities on continuous breastfeeding and appropriate complementary feeding practices from 6 months | Sensitize Caregivers, community, and general populace through media and communication |  |  |  |  | 10,000 per slot * 50{ radio}=500,000 15,000 per slot *20{TV} =300,000 | 800000 | SMOH, ANRIN project, save the children, Lafiya Project, BMGF and UNICEF | SMOH Nutrition desk officer
2.13 | Provide incentives to pregnant women,mothers and other caregivers in 30 SHFs to motivate utilization of health activities | No. of pregnant women, caregivers and mothers that received incentives in 30 SHFs | * |  |  |  | Incentives ( Sanitary pad,Hypo and diapers= 30*1500*200= 9,000,000 Transport for 30 nutrition officer= 3000*30=90,000 | 9090000 | SMOH,ANRiN, Save the children,BMGF, lafiya project
| Revitalization of baby friendly hospital initiative in all SHC facilities | Conduct 5 days training on youth friendly services for 30 SHFs service providers by 2 facilitators |  | * |  |  | Facilitators Transport =3000*2*2=12,000 Facilitators DSA= 30,000*2*5=300,000 Refeshments(tea break and lunch= 3500*32*5= 560,000 participants transport= 3000*30= 90,000 Hall hire=70,000*5=500,000 stationaries=500*30=15000 Facemasks=5500*6=33,000 sanitizer=1500*32=48,000 | 1258000 | SMOH,ANRiN, BMGF,Lafiya Project and Save the children
2.18 | Conduct activities to support brestfeeding from 0 month to 12months for HIV exposed infants | No. of HIV exposed infants EBF from 0 month |  |  |  | * | Facilitators Transport =3000*2*9= 54000 Facilitators DSA= 30,000*9*2=540,000 Refeshments(tea break and lunch= 1500*239= 358,500 participants transport= 2000*230=460,000 | 1412500 | SMOH, ANRiN project, save the children
2.1.11 | Establish 30 Nutrition corners at SHCs in the state | Procure and distribute food demonstration equipment(cooking utensils and foodstuff), ingredients and fuels to 29 SHCs and 1 tertiary health facility in the state |  | * |  |  | Equipments@50,000*30= Ingredients@5000*48*12 transportation of equipments= 20,000*30= 600,000 | 5080000 | SMOH, ANRiN Lafiya project,BMGF, save the children and UNICEF | SMOH Nutrition desk officer
| TOTAL | [6 empty] | 20758700

## HumanServ & SD
HUMAN SERVICES AND SOCIAL DEVELOPMENT 2021 ANNUAL OPERATIONAL PLAN FOR NUTRITION
TIME FRAME
S/N | OBJECTIVE | ACTIVITIES | OUTPUT INDICATORS | Q1 | Q2 | Q3 | Q4 | COSTING ELEMENT | BUDGET | SOURCE OF FUNDS | RESPONSIBLE PERSON | REMARKS
1.1 | Ensuring Food and Nutrition Security at the State, Community and Household
1.1.12 |  | Liaise with Banks (UBA, Access, Stanbic and Sterling ) to promote increased access to Micro- Credit facilities for Women to expand farm operations. (interest rates and collat erals) | * No. of cooperative groups selected for farming & small scale business operation * No. of women accessing micro credit | x |  |  |  | 1.Mapping /Planning Meeting Refreshment @1000x9 2. Training of women cooperative group Lunch @1000x510 Facilitator @20000x2x10zones DSA@3000x4x10 Workshop materials 500×510 PAS 5000 Hall hire 70000x10 | 1963000 | MHSSD, UNICEF, Alive and Thrive, Save the Children, CS-SUNN | Dir. Gender
1.1.14 |  | Promote the formation of women into sustainable cooperative groups for the provision of grants and revolving loans | * No. of women cooperative groups formed in 23 LGAs * No. of cooperative groups/individuals that received grants and/or revolving loan |  | x |  |  | Administrative cost |  | MHSSD | Dir. Gender
| Sub-total | [7 empty] | 1963000
2.1 | Child survival, growth and development improved
2.1.16 |  | Birth Registration. Promote awareness on Girl Child Education, end Child Marriage, adolescent nutrition and health related practices | % improvement in Girl Child Education and reduction in Child marriage. | X | X | X | X | PAS 5000. Posters 150x2300. Tshrts and face caps 2000x2300. Banner 5000x3. Fuel 5000x23. DSA 7x3000x23LG. Lunch 1000x7x23LG | 1930000 | UNICEF, Alive and Thrive, Save the Children | Dir. Gender | SPHCDA/ MHSSD. NPOPC, MO HEALTH
| Sub-total | [7 empty] | 1930000
2.2 | Caring for the Socioeconomically Disadvantaged and Nutritionally Vulnerable through Improved Poverty Alleviation Schemes
2.2.2 |  | Develop and institutionalize poverty alleviating schemes/projects to empower Vulnerable households. Provision of loans through KADSWEF | No. of household empowered. No. Of women that benefited from KADSWEF | x | x | x | x | N20,000 per household for 1000 houeholds.Fuel 5000x23. DSA 7x3000x23LG. Lunch 1000x7x23LG | 11745000 | CS-SUNN, Alive and Thrive, MHSSD, Kaduna State Government. | Dir. Gender | MHS&SD, Planning and Budget Commission
| Sub-total | [7 empty] | 11745000
4.3 | Social Protection Programs for the Vulnerable Groups
4.3.2 |  | Incorporate Nutrition considerations (e.gM others with SAM children, CCT) into social protection programs to address poverty, malnutrition and health of the vulnerable groups. Traning Nannies of Magajin Gari Orphanage home, 23 LG Head of Women Units and their assistants, 40 Social Welfare Officers of the Ministry on preparing nutritious food supplement and Backyard gardening. | * No. of Social Protection programmes with nutrition intervention * % improvement in nutritional status of social protection beneficiaries. | x | x | x | x | 1. Training of Nannies, Head of Women units and Social Welfare Officers. Lunch @1000x80 Facilitator @20000x2 DSA@3000x80 Workshop materials 500×80 PAS 5000 Hall hire 70000x2. Food materials for training. 1000x80. Materials utensils 1000x80 | 5501700 | MHSSD, UNICEF, Alive and Thrive, Save the Children, CS-SUNN | Dir. Gender | MHSSD/MOA
| Sub-total | [7 empty] | 5501700
| TOTAL | [7 empty] | 21139700

## KADA
KADUNA STATE COMMITTEE ON FOOD AND NUTRITION 2021 ANNUAL OPERATIONAL PLAN (KADA)
S/N | ACTIVITY | OUTPUT INDICATORS | TIME FRAME |  |  |  | COSTING | BUDGET | RESPONSIBLE PERSON | FUND SOURCE | REMARKS
|  |  | Q1 | Q2 | Q3 | Q4
1.1.1 | 1. Generate data base of farmers cooperatives/ clustering | Number of farmers cooperative | X |  |  |  | Staff Time | 0 | DD M&E | KADA
1.1.1 | 2. Conduct one day Planning meeting | Number of participants | X |  |  |  | Planning meeting refreshment@2000x6 | 12000 | DAS | KADA
1.1.1 | 3. Conduct annual Stakeholder meeting (6 cluster) | Number of participants |  |  | X |  | Annual stakeholder meeting Lunch @ #2500 x100 persons Tea break @1200x100 Training Materials @700x 100, Transport @3000x100, Honorarium @20000x3zones Fueling@ 10,000 | 810000 | DAS | KADA
1.1.4 | Conduct one day TOT on production ,promotion, consumption of vitamin A and micro nutrients rich foods for 200 extension agent | Number of extension agents trained | X |  |  |  | ToT for extension agent DTA @3,000x200 x 4 = 2,400,000.00 DTA driver @ 2,000x4X4 = 32,000.00 Fuelling @8000 X 4 =32,000.00 Facilitator fee @20,000x2 X 4 = 160,000.00 Workshop materials @450x200 = 90,000.00 | 2704000 | DAS | KADA | Target beneficiaries include farmers, women groups.
1.1.4 | Procure 200 bundles of vines | Bundles of vines procured | X |  |  |  | Procure and distribute OFSP @600x200 | 120000 | DAS | KADA
1.1.6 | Conduct ToT to 55 farmers on the production and diversification of fruits and vegetables | Number of farmers trained on the production and diversification of fruits and vegetables. |  | X |  |  | Tea break @1200x55 Lunch@2500x55 Facilitator fee@20000 Training materials@450x160 | 472500 | DAS | MOA/KADA | The famers selected are women groups to retain some of the vegetable and fruits for home use.
1.1.8 | Procure/provision of seedlings (procure 1000 starter packs) for small holders farmers including women for house hold gardening. | No. of seedlings procured |  | X |  |  | Lump sum of N1,500,000.00 | 1500000 | DAS | MOA/KADA
1.1.8 | Orientate and distribute starter packs to 250 farmers | No. of starter packs procured and distributed to farmers |  | X |  |  | Starter packs Citrus @250x1000 Pawpaw@150x1000 Mangoes@250x1000 Oil palm@350x1000 Ugu@100x1000 Moringer@100x1000 Furadan@700x 1000 refreshment@2000x1000 Facilitator fee@20000x4 DTA@9000x4(SMS) Transportation(15000x4 zones DTA driver@2000x4 Media 2000x2 Handout@550x160 EAs during step-down. Breakfast@1500x170 Lunch@2500x170 Media/coverage@30000 Facilitator fee@20000x2 Construction of a modern dryer @ 25000x5 | 1161030 | DAS | KADENAP
1.4.1 | Conduct Tot training for 4 SMS and extension agents on GAP, modern drying and storage | No. of extension agent trained on GAP |  |  |  | X | Assorted leafy vegetables for demonstration Eg spinach, pumpkin leaf, moringa,tomatoes,pepper,spring onions, bitter leaf,water leaf,ugu leaf,etc. container/ nylon for packaging( assorted leaf) | 146000 | DAS | KADA | At the end of the harvesting period, nursing mothers and young children will have their 5 star meals at home.
1.5.4 | 1. Planning meeting | No. participants |  | X |  |  | 1. Planning meeting Refreshment@2000x9 | 18000 | DAS | KADA
1.5.4 | 2. Procure inputs | No. of Inputs procured |  | X |  |  | 2. Inputs Fertilizer@5500x2x4 zones Herbicite@1500x4 polythene bags@ Weighing scale@5500x4 Knapsack sprayer@15000x4 Watering can2500x4 Hoe@250x10x4 wheel barow@15,000x12x4 | 872000 | DAS | KADA
1.5.4 | 3. Procure motorcycles | No. of motorcycles procured |  | X |  |  | 3. purchese of motor cycle for 20 SMS @350,000x4 | 1400000 | DAS | KADA
1.5.4 | 4. Purchase of protective cloth | No. of protective cloth purchased |  | X |  |  | 4. protective clothing Rian boot 220 set for 200 EA &20 SMS@ 3000x220 Rain coat 220 set for 200 EA &20 SMS @2500 Protective mask 220 set for EA &SMS @1,500 | 1840000 | DAS | KADA
| TOTAL | [6 empty] | 10233530
New Activities | 0
Total number of activities for A.O.P 2021 | 13
Activities to be removed | 0
Joint activity with MoA | 1
Total number of first quarter activity | 5
Total number of second quarter activity | 6
Total number of third quarter activity | 1
Total number of fourth quarter activity | 1
How many are funded by partners | 0
How many are solely MDA funded | 13
Total cost | 10233530

## PBC
TIME FRAME
KDMSPAN Code | Strategic Objectives | Activities | Output Indicators | Q1 | Q2 | Q3 | Q4 | Cost Element | Budget | Sources of Fund | Responsible Person | Remarks
5.1: | Promote Advocacy, Communication and Social Mobili zation
5.1.5 |  | 2-day Annual review meeting of SCFN with Local Government Committee on Food and Nutrition | No. of review meetings organised No. of SCFN members that participated in review meetings |  |  | X |  | Two Tea Break @N 1,500 x 45ppl x 2days x 2ce = N270,000 Lunch@ N3,500 x 45ppl x 2days = N315,000 Diner on arrival@ N3,000 x 40ppl x = N120,000 Breakfast on departure @ N2,500 x 40ppl = N100,000 Hall hire @ N100,000 x 2days = N200,000.00, Bottle Water @ N200 x 45ppl x 2days x 3ce = N54,000 Projector & Screen @ N10,000 x 2days =N20,000.00 PA Sys @ N10,000 x 2days = N20,000.00 Accomodation @N12000 x 40ppl x 3 nights = N1,440,000 10% service charge = N253,900 W/Shop Materials @ N700 x 41ppl=N28,700 Photo copy W/Shop Material @ N250 x 41ppl =N10,250 Report Writing @ 10,000 x 3pple =N30,000 DSA @ N7,600 x 3nights x 36ppl =N820,800 Resource Facilitator @N10,000 x 2pple x 2days = N40,000 Transportation Birnin Gwari @ N20 x 200km x 2ce = N8,000 Chikun @ N20 x 115km x 2ce = N4,600 Giwa @ N20 x 50km x 2ce = N2,000 Igabi @ N20 x 70km x 2ce = N2,800 Ikara @ N20 x 175km x 2ce = N7,000 Jaba @ N20 x 230km x 2ce = N9,200 Jema'a @ N20 x 310km x 2ce = N12,400 Kachia @ N20 x 200km x 2ce = N8,000 Kaduna North @ N20 x 85km x 2ce = N3,400 Kaduna South @ N20 x 90km x 2ce = N3,600 Kajuru @ N20 x 130km x 2ce = N5,200 Kaura @ N20 x 300km x 2ce = N12,000 Kauru @ N20 x 100km x 2ce = N4,000 Kubau @ N20 x 80km x 2ce = N3,200 Kudan @ N20 x 30km x 2ce = N1,200 Lere @ N20 x 120km x 2ce = N4,800 Makarfi @ N20 x 70km x 2ce = N2,800 Sabon Gari @ N20 x 10km x 2ce = N400 Sanga @ N20 x 380km x 2ce = N15,200 Soba @ N20 x 30km x 2ce = N1,200 Zango Kataf @ N20 x 240km x 2ce = N9,600 Zaria @ N20 x 5km x 2ce = N200 Other Participants @ N20 x 85km x 14pple x 2ce = N47,600 | 3901050 | PBC 2021 approved budget | DD(DAC) | PBC is funding this activities
5.1.7 |  | Conduct and Sustain advocacy to policy makers (Governor, Hon Commissioners for education, information, Budget, Health, Agriculture, Legislators, SSG, Wife of Governor and LGA Chairmen, Telecom network providers) at all levels for resource mobilization for food and nutrition activities including establishment of school farms & gardens NB: This activity is linked to activity 6.1.9 in result area 6 | No. of Policy makers reached at all levels for resource mobilization for food and nutrition activities. No. of advocacy visits conducted with reports produced No. of MDAs with increased nutrition investment | X | X | X | X | Local transport@N3,000 x 16pple = N48,000 x 4 =N192,000 Refreshment lunch @2,500 x 16pple = N40,000 x 4 =N160,000 Total N352,000 | 352000 | PBC 2021 approved budget | DD(DAC) | KDSG
| Sub-total | [7 empty] | 4253050
6.1 | Promote Adequate Budgetary Allocation and Tra cking
6.1.1 |  | Conduct assessment at all levels on determinants of low financial investments in Food & Nutrition programs compared to other life-saving interventions in partnership with private sector | Number of Assessment of Financial gap for nutrition conducted |  |  | X |  | Administrative ii. Planning Meeting - Refreshment @N1,500 x 15ppl =N22,500.00 iii. Assessment tool has been developed and adapted in 1Q 2019 iv. Conduct Two - day training on Assessment tools for financial investment Accomodation @ N9,000 x 3 nights x 45 participants = N792,000 Tea Break @N 1,500 x 2days x 53 ppl x 2ce= N318,000 Lunch@ N3,500 x 53ppl x 2days= N371,000, Hall hire @ N100,000 x 2 days = N200,000 Bottle Water @ N200 x 2 x 53ppl x 2days= N42,400 Projector & Screen @10,000 x 2days = N20,000 PA Sys @ N10,000 x 2days = N20,000 10% service charge = N176,340 W/Shop Materials @N700 x 53ppl=N37,100 Photo copy W/Shop @250x 53ppl = N13,250 Report Writing @ 10,000 x 2pple =N20,000 DSA @ N7,600 x 3nights x 45ppl =N1,026,000 Resource Facilitator @N10,000 x 2pple x 2days = N40,000 Transportation @N20 x 85km x 45pple x 2ce = N153,000 | 3229090 | ANRiN | DD(DAC) | Assement tools have been developed in 2020. the assessment will be conducted in 2021 with funding support from ANRiN
6.1.2 |  | Conduct regular budget tracking and apply lessons learnt to all-levels of F&N budgeting processes. | No. of MDAs with Budget tracking tool completed and applied lessons learnt No. of LGAs with Budget tracking tool completed and applied lessons learnt |  |  |  | X | Administrative ii. Two day training for 53 participants (in Zaria) - Facillilators @ N20,000 x 2 x 2 days = N80,000.00 - Accomodation @ N9,000 x 3 nights x 45 participants = N1,215,000.00 - Tea Break @N 1,200 x 2 x 53 ppl x 2 days= N254,400 - Lunch@ N2,500 x 53 ppl x 2 day= N265,000 - Hall hire @ N200,000, - Bottle Water @ N200 x 2 x 53ppl x 2days= N42,400 - Projector & Screen @10,000 - PA Sys @ N10,000 - W/Shop Materials @N700 x 53ppl= N37,100.00 - Photo copy W/Shop Material @ N250 x 53ppl =N13,250.00 - Report Writing @10,000 - DSA @ 5,700 x 3 x 45 ppl = N769,500.00 - Transportation @ 6,000 x 45 ppl =N270,000 | 1520150 | CS-SUNN | DD(DAC) | Funding from CSSUNN/KDSG
6.1.3 |  | Develop Score Cards of lessons learnt on Budget tracking & applications to KDMSPAN | No. of score card developed with lessons learnt and applied KDMSPAN |  |  |  | X | i. Administrative ii. Produce Annual Scorecard on Food & Nutrition intervention at all level - Printing of scorecard @ N1,000 x 100 x 2 =N200,000 iii. Validation of Scorecard - Refreshment for 10 key Stakeholders @N2,000 x 10 = N20.000 iv. Organize Sensitization for 53 persons (within Kaduna Metropolis) - Tea Break @N 1,500 x 2 x 53 ppl x 1day=N159,000 - Lunch@ N3,000 x 53ppl x 1day= N159,000 - Hall hire @ N100,000, - Bottle Water @N200 x 2 x 53ppl x 1day= N21,200 - Projector & Screen @ 10,000 - PA Sys @ N10,000 - W/Shop Materials @ N700 x 53ppl= N37,100 | 1383550 | CS-SUNN | DD(DAC) | Funding fron CS-SUNN
6.1.4 |  | Participate in biannual National Council on Nutrition meeting | No. of meetings held at State Council on Nutrition and reports produced No. of meetings attended at National level |  | X |  | X | i. Planning Meeting - Refreshment @ N1,500 x 15 = N22,500.00 222,500.00 222,500.00 222,500.00 222,500.00 222,500.00 i. Organise one day 1,112,500.00 planning meeting to map out relevant stakeholders and resources needed for kaduna state council meeting on Nutrition. ii. Establish and inaugurate the kaduna state council and Nutrition in accordance with the state policy on food and nutrition. iii. Articulate key outcomes of the state council meeting for presentation at National Council on Nutrition- Administrative. iv. Participant at National Council on Nutrition ii. Organise inaugurations of State Council on Nutrition - Freshement for 10 members and Secretariat @N2,000x 10 = N20,000 - Lunch for 10 members @N3,000 x10 =N30,000 Sub-Total = N50,000:00 iii. Articulate key outcomes of the State Council Meeting -Administrative iv. Attend Annual National Council Meeting - Fueling @ 10,000 for 3days = N30,000.00 - DSA for 2 representatives (D/Governor & HC PBC) @ 40,000x3days= N120,000 Sub-total = N150,000.00 N222,500.00 | 222500 | ANRiN | DD(DAC)
6.1.5 |  | Organize state level Nutrition Partners quarterly meeting | No. of meetings held and reports produced | X | X | X | X | i. Planning Meeting - Refreshment @ N1,500 x 15 =N22,500.00 ii. Organize state level Nutrition Partners and MDAs quarterly one - day meeting - Tea Break @N 1,500 x 2 x 53 ppl x 1day=N159,000 - Lunch@ N3,000 x 53ppl x 1day= N159,000 - Hall hire (PBC Conference @ zero cost ) - Bottle Water @ N200 x 2 x 53ppl x 1day= N21,200 - Projector & Screen@ zero cost - Photo copy W/Shop Material @ N250 x 53ppl =N13,250 - Report Writing @10,000 - Transportation @6,000 x 44 ppl =N264,000 - Facilitators @20,000 x 1day x 2 ppl = N40,000 Sub Total=N666,450.00 | 2665800 | ANRiN | DD(DAC)
6.1.6 |  | Organize quarterly meetings of State Committee on Food and Nutrition (SCFN) | No. of meetings held and reports produced | X | X | X | X | Tea Break @N 1,500 x 35 ppl = N52,500 Second Tea Break @ N2000 x 35pple = N70, 000 Lunch@ N3,500 x 35ppl = N122,500, Hall hire @ N100,000 =N100,000.00, Bottle Water @ N200 x 35ppl x 2=N14,000 Projector & Screen @ N10,000 =N10,000.00 PA Sys @ N10,000 = N10,000.00 10% service charge = N37,900 W/Shop Materials @ N700 x 35ppl=N24,500 Photo copy W/Shop Material @ N250 x 35ppl =N8,750 Report Writing @ 10,000 x 2pple =N20,000 Transportation @ N5000 x 30pple = N150,000 Resource Facilitator @N10,000 x 3pple = N30, Sub Total = N650,150 x 4qtrs | 2600600 | UNICEF | DD(DAC)
6.1.8 |  | Advocate for the Creation of budget lines on food and nutrition activities in MDAs/LGAs and ensure timely release of funds | No. of advocacy visit conducted No. of MDAs with budget line on food & Nutrition No. of LGAs with budget line on food & Nutrition |  |  | X |  | Administrative ii. Develop Advocacy Plan for MDAs/LGAs for creation Budget Line and ensure release of fund on Food &Nutrition - Accomodation for for 44 persons @ N9,000 x 2 nights = N792,000.00- Tea Break @N 1,500 x 2 x 53 ppl x 1day= N159,000.00 - Lunch@ N3,000 x 53ppl x 1day= N159,000.00 - Hall hire @N100,000 - Bottle Water @N200 x 2 x 53ppl x 1day= N 21,200.00 - Projector & Screen@ 10,000 =10,000.00 - PA Sys @ N10,000 x4 = N10,000.00 - Meeting files @N250 x 53ppl= N13,250.00 - Transportation @6,000 x 44 ppl = N264,000.00 Sub Total=N736,450 (Once off) iii. Advocacy visit to Governor, Legistlature | 382000 | PBC 2021 approved budget | DD(DAC) | MoA, SPHCB, MoE MoLG, MHSSD
6.1.9 |  | Conduct training for Nutrition desk officers in MDAs/LGAs on Memo, Proposal/concept note and report writing | Number of officers trained on resource mobilisationnand allocation Number of MDAs and LGAs with increased resources for nutrition activities | X |  |  |  | i. Planning Meeting - Refreshment @ N1,500 x 15 = N22,500 ii. Two dayTraining Workshop for 53 participants (in Zaria) Accomodation @N9,000 x 3 nights x 45 participants = N1,215,000.00 Tea Break @N 1,200 x 2 x 53 ppl x 2day=N127,200 Lunch@ N2,500 x 53ppl x 2day= N265,000, Hall hire @ N100,000 x 2 =N200,000.00, Bottle Water @ N200 x 2 x 53ppl x 2day=N42,400 Projector & Screen @10,000 x 2 =N20,000.00 PA Sys @ N10,000 x 2 = N20,000.00 W/Shop Materials @ N700 x 53ppl=N37,100 Photo copy W/Shop Material @ N250 x 53ppl =N13,250 Report Writing @ 10,000 =N10,000 DSA @ 5,700 x 3nights x 45 ppl =N769,500 | 2741050 | PBC 2021 Approved Budget | DD(DAC) | The fund for the planning meeting will be drawn from PBC 2021 Approved Budget while partners are expected to support the training
6.1.10 |  | Conduct monitoring & evaluation on food and nutrition activities in collaboration with partners and the private sector | No. of monitoring visits conducted and report produced No. of evaluation studies conducted | X | X | X | X | i. administrative ii. Administrative iii. Monitoring visit across the State by 6 persons per zone for 5 days - DSA @ 10,000 x 6 ppl x 5nights x 3 zone = N900,000.00 - Fueling @ 10,000 per zone x 5days x 3 = N150,000.00 - Driver @ N4,000 per zone x 3 x 5nights = N60,000.00 - Report Writing @ 10,000 x 3 = N30,000.00 - Contingency = N10,000 per zone x 3 = N30,000.00 Sub Total= N1,170,000.00 | 1170000 | PBC 2021 approved budget | DD(DAC) | PBC M&E Officers/ M&E SPHCDA
|  | Produce an annual compedium on State and LGA Committees activities,success stories lessons learnt, etc | Compedium on State and LGA Committees activities,success stories lessons learnt, etc produced. |  |  |  | X | Hosting of annual compedium on food and nutrition interventions on PBC website - Administrative
6.1.8 |  | i. Dissemination of the State Policy on Food and Nutrition document | No. of State Food and Nutrtion Policy produced | X |  |  |  | i. Print & Disseminate 100 copies of State Policy of Food & Nutrition - @2,000 x 100= N200,000.00 | 200000 | ANRiN | DD(DAC) | Additional copies of the document to be printed PBC to fund the dissemination
|  | ii. Printing and dissemination of Kaduna State Multisectoral Strategic Plan of Action for Food and Nutrition (KDMSPAN) | No. of KDMSPAN document produced |  | X |  |  | Printing of 100 copies of Kaduna State Multisectoral Strategic Plan of Action for Food and Nutrition (KDMSPAN) @2,000 x 100= N200,000.00 - Hosting of Kaduna State Multisectoral Strategic Plan of Action for Food and Nutrition (KDMSPAN) at PBC website - Administartive | 200000 | ANRiN | DD(DAC) | Additional copies of the document to be printed PBC to fund the dissemination
|  | iii. Facilitate the Development of 2022 Annual Operation Plan of Kaduna State Multisectoral Strategic Plan of Action for Food and Nutrition (KDMSPAN) by MDAs | No of AOP developed |  |  | X |  | Accomodation @N9,000 x 3 nights x 35 participants = N945,000.00 Tea Break @N 1,500 x 2 x 35 ppl x 2day=N210,000 Lunch@ N3,000 x 35ppl x 2day= N210,000, Hall hire @ N100,000 x 2 =N200,000.00, Bottle Water @ N200 x 3 x 35ppl x 2day=N42,000 Projector & Screen @10,000 x 2days =N20,000.00 PA Sys @ N10,000 x 2days = N20,000.00 10% service charge = N164,700 W/Shop Materials @ N700 x 35ppl=N24,500 Photo copy W/Shop Material @ N250 x 35ppl =N8,750 Report Writing @ 10,000 x 2pple =N20,000 DSA @ N11,400 x 3nights x 30 ppl =N1,026,000 Transportation @ 85km x N20 x 30pple x 2 = N102,000 Resource Facilitator @N10,000 x 2pple x 2days = N40,000 | 2973550 | KDSG | DD(DAC) | Budget to be provided
|  | iii. Facilitate the Development of 2022 Annual Operation Plan of Kaduna State Multisectoral Strategic Plan of Action for Food and Nutrition (KDMSPAN) by 23 LGAs | No of AOP developed |  |  |  |  | Two Tea Break @N 1,500 x 45ppl x 2days x 2ce = N270,000 Lunch@ N3,500 x 45ppl x 2days = N315,000 Diner on arrival@ N3,000 x 40ppl x = N120,000 Breakfast on departure @ N2,500 x 40ppl = N100,000 Hall hire @ N100,000 x 2days = N200,000.00, Bottle Water @ N200 x 45ppl x 2days x 3ce = N54,000 Projector & Screen @ N10,000 x 2days =N20,000.00 PA Sys @ N10,000 x 2days = N20,000.00 Accomodation @N12000 x 40ppl x 3 nights = N1,440,000 10% service charge = N253,900 W/Shop Materials @ N700 x 41ppl=N28,700 Photo copy W/Shop Material @ N250 x 41ppl =N10,250 Report Writing @ 10,000 x 3pple =N30,000 DSA @ N7,600 x 3nights x 36ppl =N820,800 Resource Facilitator @N10,000 x 2pple x 2days = N40,000 Transportation Birnin Gwari @ N20 x 200km x 2ce = N8,000 Chikun @ N20 x 115km x 2ce = N4,600 Giwa @ N20 x 50km x 2ce = N2,000 Igabi @ N20 x 70km x 2ce = N2,800 Ikara @ N20 x 175km x 2ce = N7,000 Jaba @ N20 x 230km x 2ce = N9,200 Jema'a @ N20 x 310km x 2ce = N12,400 Kachia @ N20 x 200km x 2ce = N8,000 Kaduna North @ N20 x 85km x 2ce = N3,400 Kaduna South @ N20 x 90km x 2ce = N3,600 Kajuru @ N20 x 130km x 2ce = N5,200 Kaura @ N20 x 300km x 2ce = N12,000 Kauru @ N20 x 100km x 2ce = N4,000 Kubau @ N20 x 80km x 2ce = N3,200 Kudan @ N20 x 30km x 2ce = N1,200 Lere @ N20 x 120km x 2ce = N4,800 Makarfi @ N20 x 70km x 2ce = N2,800 Sabon Gari @ N20 x 10km x 2ce = N400 Sanga @ N20 x 380km x 2ce = N15,200 Soba @ N20 x 30km x 2ce = N1,200 Zango Kataf @ N20 x 240km x 2ce = N9,600 Zaria @ N20 x 5km x 2ce = N200 Other Participants @ N20 x 85km x 14pple x 2ce = N47,600 | 3901050 | UNICEF
|  | Support the adoption of State policy/plan on anemia reduction in adolescent girls/women and school age children |  |  |  | X | X | Tea Break @N 1,500 x 35 ppl = N52,500 Second Tea Break @ N2000 x 35pple = N70, 000 Lunch@ N3,500 x 35ppl = N122,500, Hall hire @ N100,000 =N100,000.00, Bottle Water @ N200 x 35ppl x 2=N14,000 Projector & Screen @ N10,000 =N10,000.00 PA Sys @ N10,000 = N10,000.00 10% service charge = N37,900 W/Shop Materials @ N700 x 35ppl=N24,500 Photo copy W/Shop Material @ N250 x 35ppl =N8,750 Report Writing @ 10,000 x 2pple =N20,000 Transportation @ N5000 x 30pple = N150,000 Resource Facilitator @N10,000 x 3pple = N30,000 | 650150 | UNICEF |  | Subject to the availability of the policy document from the national for adoption.
|  | Support the development of plan/strategies to eliminate introduction of water and fluids to support exclusive breastfeeding practices and commemoration of world Breastfeeding week (including 6 CFCI communities in Lere and Igabi) |  |  |  | X | X | Two Tea Break @N 1,500 x 27 ppl x 2days x 2ce = N162,000 Lunch@ N3,500 x 27ppl x 2days = N189,000, Hall hire @ N100,000 x 2days = N200,000.00, Bottle Water @ N200 x 27ppl x 2days x 3ce = N32,400 Projector & Screen @ N10,000 x 2days =N20,000.00 PA Sys @ N10,000 x 2days = N20,000.00 Accomodation @N12000 x 23ppl x 3 nights = N828,000 10% service charge = N154,140 W/Shop Materials @ N700 x 27ppl=N18,900 Photo copy W/Shop Material @ N250 x 27ppl =N6,750 Report Writing @ 10,000 x 2pple =N20,000 DSA @ N11,400 x 3nights x 23 ppl =N786,600 Transportation @ N20 x 85km x 23pple x 2ce = N150,000 Resource Facilitator @N10,000 x 3pple x 2days = N60,000 | 2566990 | UNICEF |  | restructure the activity to be smart by separating it into two activities
|  | Support the development and implementation of budgeted plan to improve dietry diversity including in CFCI communities in Lere and Igabi |  |  |  | X | X | Tea Break @N 600 x 220 ppl = N132,000 Lunch@ N1,200 x 220ppl = N264,000, Transportation to Lere @ N7333 x 6pple = N43,998 Transportation to Igabi @ N3000 x 6pple = N18,000 Transportation @ N1000 x 204pple = N204,000 DSA for Facilitator @N30,000 x 12pple = N360,000 | 1021998 | UNICEF |  | Budget to be provided
| Sub-total | [7 empty] | 27428478
| TOTAL | [7 empty] | 31681528

## SPHCB
KADUNA STATE COMMITTEE ON FOOD AND NUTRITION 2021 ANNUAL OPERATIONAL PLAN
CODE | ACTIVITY | OUTPUT INDICATORS | TIME FRAME |  |  |  | COSTING | BUDGET (IN NGN) | FUND SOURCE | RESPONSIBLE PERSON | REMARKS
|  |  | Q1 | Q2 | Q3 | Q4
5.1.14 | Monthly performance-based pay for 16 community mobilizers and 16 OiCs. From poorly performing facilities | % increase in attendance and access to Ante Natal services | x | X | x | X | • Incentives@ 5000x16x12 •Transport@16x2000x12 • Data @ 1000x16x12 | 1,536,000.00 | ANRiN | SNO SPHCB
2.1.4 | Conduct 5 days bi-annual Maternal, Newborn and Child Health MNCH) Week (Microplan devt, Planning Meetings, Orienations, monitoring & supervisions, trainings, procure commodities and publicity) | No. of pregnant women that receive Iron Folate |  | x |  | X | • (Stakeholders) meeting @ #1000 each x30 • Lunch @ N1000/person for 94 persons at State level training •Hall hire @ N70000 •Transport for 94 @ N3000 per person x 94 • Lunch @ State supervisors orientation @ N1000 per person x 46 •Hall hire @ N50000 •lunch for 1467@ N500 per person @ Micro development trainning •refreshment for 1099 persons @N500 per person @ orientation of town announcers meeting •refreshment for 1168 persons @ orientation of demand creators meeting @ N500 per person • allowance for Supervisors @ N10000 daily x 6days •Allowance for 23 STFs @ N5000 daily x 10 days •Allowance for 46 monitors @ N5000 daily x 5 days •refreshement for 20 @ N800 per person x 3 sittings @ eveining review meetings •Transport for 3 zonal coordinators @ N5000 daily per person x 5 days •Transport for 138 LGHA team members (6 per LGA) @ N2,000/day x 5 days • Determine@580*89832 • Statpack@1000x1000 •Transportation@20000x23 • Flag Off@200000 • Town Announcement@6000x1212 • Jingles@4780x60 •Small banners@1200x1212 •Big banners@15000x28 •Press Conference@50000x1 •TV discussions@150000x1 • Cottonwool@1000x1600 •Latex Gloves carton@12000x200 •Handwash@200x1600 •Adhesive plaster@200x1000 •Detergent@100x1000 •Paper Towel@300x1000 •Plaster strips@10x1000 •Pregnancy test kits @20x80000 •Iodine@340x1000 •Fersolate@1x7135812 •Folic Acid@1x7135812 •Albendezole@38.40x342519 •Paracetamol@115x21815 | 218,401,677.00 | Government/Partners | SNO
2.1.5 | Sustain on-going Vitamin A Supplementation during M N C H W for under 5 children | % of eligible children received Vitamin A | x |  | X |  | Linked to activity 2.1.4 above
2.1.8 | Commemorate World Breastfeeding Week, Symposium for 100 students and 20 state team members | Community sensitization |  |  | x |  | • Refreshment @ 1000x320 | 1180000 | Govt/Partners
2.1.9 | Conduct training a 3 days refresher training for 26 HCWs by 3 facilitators on promotion of use of Micronutrient Powders, IYCF and CMAM |  | x |  |  |  | • Transport@3000x29 •Accomodation@10000x19x4 •Teabreak @ 500x29x3x2 •Lunch@1000x26x3 •Stationery@500x26 •Manual@500x26 • DTA@5700x26x4 • Honorarium@ 10000x3x3 | 1720800 | ANRiN | SNO
2.1.10 | Train health facilities 62 Secondary Health Facility In- Charges by 6 facilitators at all levels to promote early initiation of breast feeding. | No. of health facility staff trained on IY CF |  | X |  |  | • teabreak@500X68X2 • hall@70000x2 • Stationery@500x62 • DTA@8000x62 • Lunch@ 1000x68x2 • Transport@3000x62 • Facxilitator Fee@20000x6 | 1165000 | Government | SNO
2.1.11 | Procure and distribute food demonstration equipments, ingredients and fuels to 48 PHCs | No. of functional nutrition corners | x |  |  |  | • Equipments@50000x32 • Ingredients@5000x48x12 | 4,480,000 | ANRiN | SNO
2.1.12 | Conduct 6days training newly developed MIYCN counseling guideline & minimum package of nutrition services at PHCs for 126 HCW by 8 facilitators | No. of pregnant women, caregivers and mothers that received MIYCF counseling |  | x | X |  | • Transportation@3000x126x3 • Hall@70000x6 •lunch@1000x126x6 •Teabreak@1000x126x6x2 •Training materials@500x126 •DTA@8000x126x6 Facilitation Fee@20000x8x6 •Facemask@5500x6 •Sanitizer@1700x6 • Liquid Soap@750x6 | 10,940,700 | Government/Partners | SNO
2.1.15 | Sensitization of caregivers especially grandmothers/ mothers-in-law for optimal nutrition | No. of dialogues conducted |  |  |  |  | Linked to 2.1.1 |  |  |  | Activity by MoE
2.2.1 | Conduct one day annual orientation meeting with 207 traditional, religious and quarterly review meeting with 230 traditional,religious and opinion leaders by 9 facilitators on nutritional care of the vulnerable group. | No. of vulnerable groups receiving community nutritional care | x | X | x | X | • Teabreak @1200x216 • Lunch @2500x216 • Transport@3000x207 • Facilitator Fee@20000x9 | 1600200 | Govt/UNICEF | SNO
3.1.1 | Conduct quarterly supervision to health facilities in the 23 LGA to track progress and emerging challenges on growth monitoring. | No. of Monitoring Visits to sites conducted | x | X | x | x | 3 supervisors in each LGA transportation 3x23x3000x4=828,000 DTA 8000x3x23= 552,000 | 1380000 | Government | SNO
3.1.7 | Conduct training a 3 days refresher training for 26 HCWs by 3 facilitators on promotion of use of Micronutrient Powders, IYCF and CMAM | No. of community health influencers, promoters of services (CHIPS) agents trained |  | X |  |  | • Transport@3000x29 •Accomodation@10000x19x4 •Teabreak @ 500x29x3x2 •Lunch@1000x26x3 •Stationery@500x26 •Manual@500x26 • DTA@5700x26x4 • Honorarium@ 10000x3x3 | 1720800 | Government/ANRiN | SNO
3.1.12 | Scale up CMAM servcices to 4 LGAs | No. of CVs trained No. of SAM cases referred from communities to CMAM sites No. of SAM cases treated/recovered |  | X |  |  | •Facilitators fees@ 20000x3x7x4 • Sensitization of community members: Refreshment@ 500x100x5x4 • DTA@8000x2x5x4 •Transport@3000x10x4 •Health Workers 3 day training: Teabreak@500x38x3x2x4 •Lunch@800x38x3x4 •Stationery@500x35x4 •Transport@3000x35x3x4 •Setting up&Follow-up: Refreshment@500x31x10x4 •DTA8000x2x10x4 •Car hire@10000x10x4 •Supportive Drugs@500x25000x4 •Stopwatch&thermometers@5000x20x4 •Weighing Scales@15000x5x4 •File Jackets@700x5x4 •12 Storekeepers training:Teabreak@500x14x2x2x4 •Lunch@800x12x2x4 •Stationery@500x12x1x4 •Transport@3000x12x2x4 •2 Day CVs Training:Teabreak@500x104x2x2x4 •Lunch@800x104x2x4 •Stationery@500x100x4 •Transport@3000x100x4 | 59816000 | Govt/Partners |  | Included training of HCW and purchase of other materials needed for the full scale up of CMAM
3.1.7 | Conduct training for 60 health care workers for 5 days by 8 facilitators Scale-Up stabilization centers from 17 SHFs to 4 additional SHFs for the treatment of CMAM cases with complications in 2021 |  |  | x |  |  | • Facilitators fee@400000x8x5 •Transport@2000x68 • lunch@800x168x5 •Teabreak@500x68x5 •Stationery@500x10x1x4 •Photocopy of manual@10x390x12x4 | 1985400 | Govt
6.2.2 | Conduct 5 days survey to map out the whole state in identifying local source of nutrition food for pregnant women and children (92 enumirators (4 persons per LGA) and 23 suoervisors) | No.of studies conducted |  | X |  |  | Training for 115 persons Breakfast @ 800x115 Lunch @ 1000 x 115 Hall @ 100,000 DSA @ 12500 (17 far LGAs) DSA @ 6000 (6 metropolis LGAs) Transport @ 5000 (17 Far LGAs) Transport @ 3000 (6 Metropolis) Printing of data tools @ 500,000 | 2964500 | Govt. |  | Liaise with KADENAP
2.1.4 | Print IEC Materials |  | x |  |  |  | • Printing of Counseling Flipcahrt@2500x48 | 120000 | ANRiN
2.1.12 | RollL-out CIYCF to additional 5 LGAs by condcuting training of 185 (37 per LGA) Health Care Providers for 6 days, and 3 days training for 250 CVs and procure seating furniture |  | x | x | x | x | • DTA for MTs@40000x11x5 • DTA for facilitators 8000x15x11 • Transport for Facilitators @ 600x30x10x2 •Transport for HWs@3000x184x6 •Teabreak@500x200x6x2 •Lunch@800x200x6 •Vehicle hire@5000x2 •Stationery@500x185 •Photocopy @ 10x185x393 • Food Items at 2000x5 •Teabreak for Community Volunteers training@500x54x3x2x5 •Lunch@800x54x3x5 •Stationery@500x100x5 •Photocopy@10x35x250x5 •Mats@3500x90x5 •Training materials@3000x5 | 13927050 | Govt/Partners
3.1.3 | Kaduna Emergency Nutrition Action Plan (KADENAP) |  | x |  |  |  |  | 188000000
| Procurement of Ready to use Therapeutic Food (RUTF), F75 , F100, RESOMAL for management of SAM across the110 CMAM OTPs (To be moved to KADSHMA) | [5 empty] | • RUTF @ 21450X45000 | 965250000
1.6.1 | Conduct a 2 days training to 46 master trainers (2 per LGA x 23 LGA, 2 facilitators, 4 resource persons) and 1 day Step down training to 501 caregivers on Early Child Care Development (Total no.of PEI (Caregivers) 501) @ LGA level by 45 MTs |  |  |  | x |  | • Teabreak@1200x52x2 • Lunch@2500x52x2 •Transport@3000x50 •Accomodation@10000x38x3 •DSA@5700x38x3 •Honorarium@10000x2x2 • Refreshment@547x500x2 • Transport@1000x547 • Stationery@700x547 | 3841500 | Govt |  | Activity in MoE
3.1.1 | Conduct quarterly supervision to health facilities in the 23 LGAby 3 supervisors to track progress and emerging challenges on growth monitoring. |  | x | x | x | x | • Transport@1000x23x3x4 | 276000
3.1.8 | Conduct 1 Day refresher training for 26 Health promoters on IYCF CMAM in emergency and special circumstances by 3 facilitators |  |  |  | x |  | • Refreshment @1500x33 • Transport@3000x30 • Honorarium@20000x3 | 199500 |  | Liaise with SEMA
3.1.7 | Conduct 5 days quarterly supervision & monitoring to HFs and Support Groups meetings on IYCF in 6 LGAs by 3 monitors |  | x | x | x | x | • Accomodation@24800x3x12 • Perdiem@15840x3x12 • Transport from hotel to @5000x3x2 •Local Transport@1500x3x10 •Lunch@ 5000x20x2 •Transport to contingous LGAs@5000x10x3 | 1888040 | ANRiN | ANRiN
| Conduct 1 day monthly data validation meeting at LGA level with 23 LGHA and 98 Health Facility staff, with 6 facilitators |  | x | x | x | x | • Transport for participants@1500x122 • Perdiem@8000x3x6 • Transport for Facilitators@5000x3x2 | 357000 | ANRiN
| Procurement of office equipments for Nutrion unit |  | x |  |  |  | • Color Printer@87000x1 • Airconditioner@150000x1 • Laptops@360000x13 •Water Dispenser@70000x1 •Office Table@75000x2 •Chair@45000x4 •Plasma TV@80000x1 •Cabinet@150000x2 •Projector@77409x1 | 5699409 | ANRiN
| Office Maintainance |  | x |  |  |  | •Door@100000x1 • Window@60000x1 • Painting@20000x1 •Workmanship@20000x5 •Branding@100000x1 •Floor tiles@2500x40 •Cement@2800x10 •Sand@3600x3 | 670800 | ANRiN
| procure and distribute Fe, Folic Acid and Fansidar |  | x |  |  |  | • Iron Tablets @2025000 • Folic Acid@2025000 • Fansidar@5400000 •Transport@56000 | 9506000 | ANRiN
2.1.11 | Reactivate/Establish Under Five U-5 Nutrition clinic (food demonstrations, GMP. Hand washing , Nutrition counselling) in 255 PHCs in 23 LGAs. (Procurement of cooking utensils, food stuffs, ) |  | x | x | x | x | • Food Demonstration Equipments@50000x255x1 • Food Items and fuel@5000x255x12 | 28050000 | Govt
| TOTAL | [6 empty] | 1291317999

## RUWASSA
KADRUWASSA 2021 PROPOSAL
KADUNA STATE COMMITTEE ON FOOD AND NUTRITION 2021 ANNUAL OPERATIONAL PLAN
|  | OBJECTIVE | Support Water Supply, Sanitation and Hygienein in Rural Area and interventions in emergency settings.
S/NO | KDSMPAN CODE | ACTIVITY | OUTPUT INDICATORS | RESPONSIBLE PERSON | TIME FRAME |  |  |  | COSTING | BUDGET | FUND SOURCE | REMARKS
[5 empty] | Q1 | Q2 | Q3 | Q4
1 | 1.1.13 | 1. Analysis of 150 triggered site in rural areas and small-towns across the state | 150 Number of Sites triggered and analysed in public schools, PHCs, Motor parks and Markets across the Water,Sanitation and Hygiene (WASH)/ Partinership for Expanded Water,Sanitation and Hygiene (PEWASH) LGAs in 243 Wards. | Director Sanitation and Hygiene KADRUWASSA | X | X | X | X | Site analysis @45,000x150 sites. | 6750000 | KDSG 2021 Counterpart funding and development partners (World Bank/UNICEF) | The cost for this activity is covered in the N622,831255.86 budgeted for the construction of 675 handpump boreholes in 2021 RUWASSA budget. 2. Procurement will be carried out especially in Schools and PHCs, Markets, Motor Parks and Communities in the rural areas and Small-towns across the 22LGAs/243 Wards in the First-Fouth quater. | Counter Fund
2 |  | 2. Geophysics assessment for 150 sites | Number of Geophysics assessment Conducted in Public Schools, PHCs, Motor parks and Markets across the Water,Sanitation and Hygiene (WASH)/ Partinership for Expanded Water,Sanitation and Hygiene (PEWASH) LGAs in 243 Wards. | Director Water Supply KADRUWASSA |  | X | X | X | Geophysics @40,000x150 sites | 6000000 | KDSG 2021 Counterpart funding and development partners (World Bank/UNICEF) | The Geophysic assessment will be carried out in the first- Forth quarter in line with activity 1 above. 2.The assessment will be determine by the number of sites triggered and found worthy for intervention in 2021. | Counter Fund
3 |  | 3. Drill and Construct 150 number of Handpump boreholes in rural areas and small-towns. | Number of hand pumpboreholes Constructed in public schools, PHCs, Motor parks and Markets across the Water,Sanitation and Hygiene (WASH)/ Partinership for Expanded Water,Sanitation and Hygiene (PEWASH) LGAs in 243 Wards. | Director Water Supply KADRUWASSA |  | X | X | X | Drill and Construction @ 700,000x150 | 105000000 | Kaduna State Government (KDSG) 2021 Counterpart fund and development partners (World Bank/UNICEF) | 1. The number of boreholes to be constructed was not provided in the coasted KDMSPAN, but since 150 sites was outlined for assessment, it is assumed that the number of boreholes to be constructed in the plan is 150. However, RUWASSA Planned to construct 675 handpump boreholes at the cost of N622,831255.86 in the 2021 budget. 2. The number of the HPBH to be constructed in public schools, PHCs, Motor parks and Markets will be determine by number of sites triggered and found worthy. | Counter Fund
4 |  | 4. Procure and intall GP tank of 300,000lts in public schools, PHCs, motor parks, markets and community. | Number of 300,000lts of GP tank Procured and installed in public schools, PHCs, Motor parks and Markets and communities across the Water,Sanitation and Hygiene (WASH)/ Partinership for Expanded Water,Sanitation and Hygiene (PEWASH) LGAs in 243 Wards. | Director Water Supply KADRUWASSA |  | X | X | X | Construction of 12,000ltrs at 25 Sites @ 9,000,000 each | 225000000 | Kaduna State Government (KDSG) 2021 Counterpart fund and development partners (World Bank/UNICEF) | The number of 300,000ltrs GP tanks to be procured was not provided in the coasted plan, as such no cost element was indicated. However, the number of the 300,000ltrs GP tank to be procured and installed will be determine by the number of solar-powered boreholes that will be constructed after the Geophysics assessment had been conducted to determine the needs of the site. | Counter Fund
5 |  | 5. Rehabilitation of 50 Pump Boreholes across the State. | Pump Boreholes Rehabilitated of across the State. | Director Water Supply KADRUWASSA | X |  | X |  | 50 @N200,000 | 10000000 | Kaduna State Government (KDSG) 2021 Counterpart fund and development partners (World Bank/UNICEF) | The rehabilitation includes Hand Pump Bore Hole and Solar Motorised Boreholes | Counter Fund
6 | 1.1.14 | 6. Construct 100 Blocks of Gender sensitive Sanition Facilities in Institution/Public Place | 100 Blocks of Gender Sensitive VIP Sanition Facilities constructed in Institution/Public Place conducted across the Water,Sanitation and Hygiene (WASH)/ Partinership for Expanded Water,Sanitation and Hygiene (PEWASH) LGAs in 243 Wards. | Director Sanitation and Hygiene KADRUWASSA |  | X | X | X | Construction of VIP @1,500,000 * 100 | 150000000 | Kaduna State Government (KDSG) 2021 Counterpart fund and development partners (World Bank/UNICEF) | The actual sum for the construction of VIP laterines on average is 1,500,000 per Block. each lot have two sites and each site has two blocks (one for female and one for male). this amount to 6,000,000 naira. Procurement will be carried out especially in Schools and PHCs, Markets and Motor Parks in the rural areas and Small-Towns across the 243 Wards /22LGAs in the first quater-Fouth quarter. However, RUWASSA Planned to construct 1,716 blocks of VIP at the cost of N262,388,028 in the 2021 budget. | Counter Fund
7 |  | 7. Conduct supervision for drilling/construction of 150 HPBH, 25 number of SMBH and 100 Blocks of Gender sensitive VIP latrines and hygiene facilities in Public schools, motor parks, markets and procurement of procurement of 300,000ltrs of GP tanks. | Supervision in all facilities across the WASH/PEWASH LGAs in 243 Wards conducted. | Director Planning ,Monitoring and Evaluation (PME) KADRUWASSA | X | X | X | X | 130 Supervisor *@400,000 | 52000000 | KDSG 2021 Counterpart funding and development partners (World Bank/UNICEF) |  | Counter Fund
8 |  | 8. Conduct campaign to promote effective hand washing in 23 LGAs | Campaign to promote effective hand washing in 23 LGAs Conduct | Director Sanitation/Hygiene KADRUWASSA | X | X | X | X | 23LGAs @N51,070.61 | 1174624 | KDSG 2021 public fund Budget. | This activitie is directed toward Sensitatsation on Nutrition. The Name is just coined for it to pass. | MDA Funded
9 |  | 9. Conduct a Workshop for Clean Nigeria "Use the Toilet" Campaign Desk officers (CNC) for wide ODF plan in 23LGAs | Workshop for Clean Nigeria "Use the Toilet" Campaign Desk officers (CNC) for wide Open Defication Free (ODF) plan in 23LGAs conducted | Director Sanitation/Hygiene KADRUWASSA | X |  |  |  | 30 Participant*165,476.67 | 4964300 | KDSG 2021 public fund Budget. | The cost includes 4days Accommodation, leaning Materials, DTA, Hall, Break fast and Lunch per person among other things. | MDA Funded
10 |  | 10. Conduct workshop for at least 414 CLTS Facilitators in the 23 LGAs | Workshop for at least 414 Community Level Total Sanitation (CLTS) Volunties Facilitators in the 23 LGAs Conducted | Director Sanitation/Hygiene KADRUWASSA |  | X | X |  | 414 facilitators*N11,271.60 | 4666442 | Kaduna State Government (KDSG) 2021 Counterpart fund and development partners (World Bank/UNICEF) | The cost includes leaning Materials, allowance, Hall , Break fast and Lunch per person among other things. | Counter Fund
11 | 3.1.5 | 11. Institutionalization of the Villaged Lead Operation and Maintenance (VLOM) Concept in 200 Communites for Sustainability of WASH Facilities | number of people trained in Institutionalization of the Villaged Lead Operation and Maintenance (VLOM ) Concept in Communites for Sustainability of WASH/PEWASH Facilities in there communities across 243 Wards in the WASH/PEWASH LGAs conducted. | Director Sanitation/Hygiene KADRUWASSA |  | X |  | X | VLOM Training @ 50,000*200 | 10000000 |  | The Cost of training of (VLOM ) Concept in 200 Communites across 255 Wards in 23LGAs for Sustainability of WASH Facilities. The cost was captured in RUWASSA 2021 Budget. | MDA Funded
|  |  |  | TOTAL N | [5 empty] | 575555366
Total Number of activity plan for 2021 |  |  | 11 Activity | REMARKS
Roll over activity from 2020 |  |  | 0
New Activity introduced (Clean Nigeria Campaign) |  |  | 1 | Capyured in 2021 Budget
Priority plan activities |  |  | 11
How many are solely MDA-funded? |  |  | 3 Activities | Capyured in 2021 Budget | 16138924
How many will be supported by partners? |  |  | 0 Activity
How many will be counterpart funded? |  |  | 8 Activities |  | 559416442
Total Activity |  |  | 11 Activities | Captured in 2021 Budget | 575555366

## SEMA
SEMA SECTOR ANNUAL OPERATIONAL PLAN FOR NUTRITION 2020
TIME FRAME
S/N | CODE | OBJECTIVE | ACTIVITIES | OUTPUT INDICATORS | Q1 | Q2 | Q3 | Q4 | COSTING ELEMENT | BUDGET | SOURCE OF FUNDS | REMARKS
1 | 2.1.20 | Training emergency managers on mainstreaming nutrition in feeding program targeted at the vulnerable group in emergency situations. | 1. To conduct ToT on Nutrition program for SEMA team and other relevant stakeholders on emergency response 2. Step down training on nutrition programmes to all staff of SEMA in the 3 zones. 3. Refresher training on nutrition programs in emergency to all staff of SEMA in three zones | No. of Emergency managers trained on mainstreaming nutrition | x |  |  |  | 1. Participants 20+2 resource persons i. Tea break 1200*22*3*1=79200 ii. Lunch 2500*22*3*1=165000 iii. Transport 3000*20=60000 iv. Honorarium 20000*2*3=120000 v. stationeries 700*22=50400 vi. Hall 70,000 2. Participants 60(20 in each zone), resource persons 6(2 in each zone) i. Tea break 1200*66*2=158400 ii. Lunch 2500*66*2=330000 iii. Transport 3000*66*2=396000 iv. Stationary 700*66=46200 3. Refresher Training i. Lunch 2500*66=165000 ii. Transport 3000*66=198000 iii. Hall 150,000 | 3052200 | Partners | Roll over from 2020, (budget of N1,380,200 KADSPAN) and N363,000 in 2021. KDMSPAN. Not budgeted in SEMA 2021, deficit of N1,309, 000 but going to be presented to the partners for Support (ANRiN)
2 | 2.1.20 | Promote MIYCN-E in all affected parts of the state in line with core humanitarian standard. | Conduct orientation on minimum preparedness on nutrition in emergency situation to vulnerable groups(PLWA, PWDs, IDPs) in selected 1 LGA in the 3 senetorial zones | No. of PWDs sensitized No.of PLWA sensitized No. of IDPs sensitized |  | x |  |  |  | 2965200 | Partners | (New activity) Not Budgeted in SEMA 2021. One LGA in the 3 senetorial zone.. Source by Partners (ANRIN)
33 |  | To ensure that Emergency actors on food intervention are sensitized on the benefits of embedding nutritional supplements in the course of intervention | Capacity Building Training on Mainstreaming Nutritional Supplements in Emergency plan and response for Stakeholders in the State | 80% of Stakeholders have become informed on the importance of including nutritional supplements on food intervention |  |  | x |  | 1. Participants 50+2 resource persons i. Tea break 1200*52*2=124,800.00 ii. Lunch 2500*52*2=260,000 iii. Transport 3000*52*2=312,000. iv. Facilitator fee 20000*2*2*1=80,000 v. Public adress system 50000*3=150,000 vi. Fueling 20,000*3=60,000 vii. Photograph and Video 30000*3=90,000 viii. Documentation 15000*3=45000 ix. Hall 150000*2=300000 | 1421800 | Partners | New Activity not in the KDMSPAN This training will be conducted for 2 days in the metropolis.
|  | Total | [7 empty] | 7439200
| Total Number of Activities plan for 2021 |  |  | 4
| How many are solely MDA funded |  |  | 0
| Piriority Plan Activity |  |  | 3
| How many will be supported by partners |  |  | 3
| How many will be counterpart funded |  |  | 0
| Total Costed Activities |  |  | 7439200

## LGAs
21
CODE | ACTIVITY | OUTPUT INDICATORS | TIME FRAME |  |  |  | COSTING | BUDGET (IN NGN) | FUND SOURCE | RESPONSIBLE PERSON | REMARKS
|  |  | Q1 | Q2 | Q3 | Q4
2.1.11 | Infant and Young Child Feeding (IYCF) | Reduction in the number of Malnurished children in the State | X | X | X | X | • ( ALLOWANCE FOR Community Volunteers @ N1,500 each x 45 = 67,500 X 12 = 729,000 • Refreshment for 45 CVs 5 WDCs, 20 H/Ws and 11 Monitors (6 from LGAs, 5 from the State) @ 750 each x 81 = 60,750 x12 = 729,000 • Transport for CVs & WDCS @ 1,500 each x 30 = 45,000 x 12 = 540,000 • Transport for H/Ws @ 1500 each x 20 = 30,000 x 12 = 360,000 • Refreshment for Monthly review meetings @ 750 x 30 = 22,500 x 12 = 270,000 • Transport allowance for H/W and WFPs @ 3000 each X 10 = 30,000 x 12 = 360,000 • Allowance for 6 Supervisors from LGAs @ 4,000 each X 6 = 24,000 x 12 = 288,000 • Transport Allowance for Monitors @ 3000 each X 11 = 33,000 x 12 = 396,000 • Monthly Supervision by WDC members @ 2,000 each X 5 = 10,000 x 12 = 120,000 • Suportive Supervision by health workers (Average 2000) @ 2000 X 10 = 20,000 x 12 = 240,000 • Food Demostration material for the 5 groups @ 5000 X 5 = 25,000 x 12 x 12 = 300,000 • Monthly LGAs Food & Nutrition Committee review meetings @ 10,000 X 2 = 20,000 x 12 = 240,000 • Printing, Photocopying and Stationery @ 32,250 x 12 = 387,000 • Fueling of Vehicles from pickup points to OTP sites @ 4,000 X 5 sites X 4(wks) = 80,000 x 12 = 960,000 | 6000000 | LGAs Budget | DPHC & NFP
3.1.9 | Community Management of Acute Malnutrition (CMAN) | Increase the number of treated Malnurished children in the State | X | X | X | X | • Supervision of CMAN activities by Spouses of LGA Chairmen @ 250,000 x 12 = 3,000,000 • Transport of RUTF from State to LGAS @ 50,000 x 12 = 600,000 • Transport of RUTF from State to LGAS @ 20,000 x 12 = 240,000 • Supportive drug procurement @ 70,000 x 12 = 840,000 •Transport for Supervisors ( M & E and NFP) 10,000 x 12 = 120,000 • Purchase of Sanitation items @ 15,000 x 12 = 180,000 • Review meeting with CV @ 35,000 x 12 = 420,000 • Transport for Care givers @ 50,000 x 12 = 600,000 | 6000000 | LGAs Budget | DPHC & NFP
| Food and Nutrition Program |  | X | X | X | X |  | 522521484.642 | LGAs Budget | DPHC & NFP
| TOTAL | [6 empty] | 534521484.642
Total Key Number of Activies Plan 2021 |  | 3
How many are solely MDA (LGAs) - Funded |  | 3
How many will be supported by partners |  | 0
How many will be counterpart funded |  | 0
Total Cost |  | 534521484.642