**NIGER STATE 2021 NUTRITION WORK PLAN**

OUTCOME 1: Children, adolescent mothers and women, particularly in vulnerable and deprived areas, have increased access to quality services and information, and adopt appropriate nutritional practices to prevent and treat malnutrition

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Outputs** | **Planned activities** | **Responsible person** | **Time Frame** | **Budget** |
|  |  | Q1 | Q2 | Q3 | Q4 | State | UNICEF | TOTAL |
| Output 1.1: Federal, state and local governments have enhanced institutional capacity and demonstrate strengthened commitment to scale-up quality nutrition services and interventions |
| Activity 1.1.1 | Strengthen coordination mechanism for food & Nutrition  | NSPC, MoA, MoE,  | x | x | x | x |  5,200,000  |  17,691,492  |  |
| Activity 1.1.2 | Development & Adaptation of Multisectoral strategy, plan & guidelines for Nutrition  | NSPC, SPHCDA |   | x |   |   |  2,300,000  |  7,536,412  |  |
| Activity 1.1.3 | Strengthen & Coordination of advocacy platform & network for leveraging resources for nutrition  | NSPC, MoA, MoE, SPHCDA | X |   |   |   |  1,500,000  |  3,726,000  |  |
| Activity 1.1.4 | Adaptation of Nutritional Policy/Plan on aneamia, reduction in adolescent girls/women & school age children | NSPC, & SPHCDA |   | X |   |   |  1,200,000  |  5,822,980  |  |
| Activity 1.1.5 | Development & Implementation of strategic plan for elimination of water and fluids to support increase in exclusive breastfeeding | NSPC, NOA, MOI&S & SPHCDA |   |   | X |   |  2,000,000  |  6,490,000  |  |
| Output 1.2: Government at all levels and key stakeholders have strengthened capacities and deliver improved access to nutrition services for children under 5 years, school-age children, adolescents, and women. |
| Activity 1.2.1 | Strengthen capacity of health workers & Nutrition worker in provision of Maternal, Infant & Young Child Nutrition (MIYCN) services  | NSPHCDA |   |   | x |   |  21,947,555  |  53,766,080  |  |
| Activity 1.2.2 | Expansion of facilities for increase access for SAM treatment  | NSPHCDA |   | x | x |   |  72,500,000  |  99,500,000  |  |
| Activity 1.2.3 | implementation of Iron Folate Acid (IFA) supplementation to adolescent (boys & girls) for prevention & reduction of aneamia  | NSPHCDA | x |   | x |   |  5,200,000  |  15,000,000  |  |
| Activity 1.2.4 | Procurement of Nutrition commodities for early childhood, school age, adolescent (boys & girls) and women IFA, deworming tablet & micro nutrient power  | NSPHCDA |   | x |   | x |  7,800,000  | 32,500,000  |  |
| Activity 1.2.4 | Pilot routine adolescent (boys & girls) supplementation school age deworming in selected communities, HFs, & LGAs | NSPHCDA |   | x |   |   |  4,000,000  |  12,500,000  |  |
| Activity 1.2.5 | Strengthen capacity of health facilities, HWs & community structure for increase service delivery  | NSPHCDA | x |   | x |   |  5,000,000  |  12,400,000  |  |
| Activity 1.2.6 | Procurement of RUTF, F75, F100 & Resomal, deworming tablet, heightometer | NSPHCDA | x |   |   |   |  9,000,000  | 20,000,000  |  |
| Activity 1.2.7 | Capacity building for Health Facilities & workers for implementation & promotion of Maternal Infant & Young Child Nutrition (MIYCN) | NSPHCDA |   | x |   |   |  3,500,000  |  7,400,000  |  |
| Output 1.3 Children and women in humanitarian situations have timely and sustained access to quality preventive and rehabilitative nutrition services and support |
| Activity 1.3.1 | Strengthen capacity of health facilities & HWs for provision of quality SAM treatment in flooded communities  | NSPHCDA |   | x |   | x |  5,350,000  |  8,635,000  |  |
| Activity 1.3.2 | Procurement of Nutrition commodities, equipment & materials for emergency preparedness & response  | NSPHCDA |   | x |   |   |  3,675,000  | 7,685,000  |  |
| Activity 1.3.3 | Development & implementation of Nutrition in emergency preparedness & response plan  | NSPHCDA |   | x |   |   |  6,787,200  |  7,555,000  |  |
| Activity 1.3.4 | Strengthen quality SAM service delivery in flooded LGAs | NSPHCDA |   | x |   |   |  10,006,200  |  5,657,000  |  |
| Activity 1.3.5 | Expansion of implementation of integrated quality comprehensive IYCF & SAM services in selected flooded LGAs  | NSPHCDA |   |   | x |   |  6,555,250  | 3,258,600  |  |
| Activity 1.3.6 | Strengthen the coordination of Nutrition Strategy for emergency response & preparedness plan  | NSPHCDA | x |   | x |   |  7,800,000  |  3,500,000  |  |
|  |  |  |  |  |  |  | **181,321,205** |  |  |